## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Formal order for the work of Supplying & aligning of HDPE distribution pipe line and allied works including Functional House Holds Tap connecting (FHTC ) and connection providing to Raghunathpur Mouza-39 and Paschim Gangarampur Mouza- JL-92 of Telipara block -Kanksa under TELIPARA piped W/s Scheme under DWSD, PHE Dte (Part-A) |  |  | ORD/000009/2022-2023 | 642/DWSD | 21/04/2022 | 16/05/2022 | M/S PROCHESTA ENTERPRISE | 98.21 | 98.21 | 100 | 85
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Formal order for the work of Construction of 200 M3 capacity , 20 mtr staging height RCC Over head Reservoir (OHR) at Jamdoba of Telipara piped W/s Scheme under Durgapur W/S Division, PHE Dte (SL-07) |  |  | ORD/000012/2022-2023 | 575/DWSD | 13/04/2022 | 28/05/2026 | M/S KALYANI ENTERPRISE | 62.35 | 19.72 | 31.63 | 100
3 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and other allied works under Telipara piped W/s Scheme of DWSD,PHE Dte (SL-06) |  |  | ORD/000103/2022-2023 | 786/DWSD | 18/05/2022 | 28/05/2022 | M/S MONDAL ENTERPRISE | 14.09 | 12.59 | 89.37 | 0
4 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Acceptance for the work of Supplying & aligning of HDPE distribution pipe line and allied works including Functional House Holds Tap connecting (FHTC ) and connection providing to Jamdoba Mouza-40 and Telipara Mouza- JL-41 of Telipara block -Kanksa under TELIPARA piped W/s Scheme under DWSD, PHE Dte (SL-03) |  |  | ORD/000008/2022-2023 | 554/DWSD | 11/04/2022 | 06/05/2022 | M/S SANTANU PALIT & CO. | 127.01 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Acceptance cum formal order for the work of Sinking of 2 No Tube well 250 mm X 150 mm big dia Tube well 210 mtr depth direct rotary rig method using PVC pipe & Pre packed resin bonded gravels filter for Telipara piped W/s Scheme under DWSD, PHE Dte (SL-10) |  |  | ORD/000107/2022-2023 | 739/DWSD | 06/04/2022 | 16/04/2022 | M/S. D. PALIT & CO. | 22.86 | 18.07 | 79.07 | 0
6 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Formal order for the work of Construction of Pump house cum Chlorine Room with Sanitary Plumbing arrangement at Jamdoba tube well No-1 or H/W Site of Telipara piped W/S Scheme under DWSD, PHE Dte (SL-05) |  |  | ORD/000010/2022-2023 | 576/DWSD | 13/04/2022 | 28/05/2022 | M/S KALYANI ENTERPRISE | 6.21 | 6.21 | 99.99 | 100
7 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Formal order for the work of Construction of Pump house cum Chlorine Room with Sanitary Plumbing arrangement at Jamdoba tube well No-2 or H/W Site of Telepara piped W/S Scheme under DWSD, PHE Dte (SL-06) |  |  | ORD/000011/2022-2023 | 641/DWSD | 21/04/2022 | 05/06/2022 | MUKHERJEE ENTERPRISE | 6.15 | 6.06 | 98.52 | 0
8 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Water supply arrangement to 6(Six) Nos AWC without electricity at Jamdoba,Telipara, Nabagram Majhiara & other allied works under Telipara Piped Water Supply Scheme.(TSM/004035) under DWSD,PHE Dte |  | Junior Engineer_3 | ORD/000665/2022-2023 | 625/A/DWSD | 21/04/2022 | 11/05/2022 | B. T. M. CONCERN | 34.06 | 32.79 | 96.28 | 100
9 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 330/DWSD | 15/03/2022 | 15/03/2022 | Resource Division | 37.85 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Acceptance cum formal order for the work Balance work for construction of pump house with approach road and others allied works at Jamdoba pump house No-II Telipara piped W/s Scheme under DWSD ,PHE Dte. |  |  | ORD/000595/2022-2023 | 579/DWSD | 10/03/2023 | 30/03/2023 | MUKHERJEE ENTERPRISE | 5.68 | 5.68 | 100.04 | 100
11 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex, Banskopa,DGP-12 (w.e.f 18.08.2023 to 17.02.2024). (SL-02) |  |  | ORD/000191/2023-2024 | 1364/DWSD | 11/08/2023 | 11/02/2024 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 289.47 | 100
12 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Acceptance cum formal order for the work of Construction of boundary wall at Jamdoba of Telipara W/s Scheme pump house No-II under DWSD ,PHE Dte |  |  | ORD/000567/2022-2023 | 481/DWSD | 22/03/2023 | 06/05/2023 | MUKHERJEE ENTERPRISE | 14.92 | 12.84 | 86.04 | 100
13 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex,Banskopa,DGP-12 (w.e.f 18.02.2023 to 17.08.2023). (SL-02) |  |  | ORD/000501/2022-2023 | 133/DWSD | 31/01/2023 | 31/07/2023 | PRAMIT CHATTERJEE | 0.82 | 2.39 | 289.74 | 80
14 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Quotation for Telipara W/S Scheme , Pump House No- 02 , Panagarh CCC |  |  | BILL/00206/2022-2023 | BP-2022-23-338 | 17/03/2023 | 17/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.13 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | New | Quotation for Telipara W/S Scheme , Pump House No- 01 , Panagarh CCC |  |  | BILL/00205/2022-2023 | BP-2022-23-337 | 17/03/2023 | 17/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.45 | 0 | 0 | 0
Total | [13 empty] | 445.62 | 216.95 | 48.68