## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | KOTALPUKUR PIPED WATER SUPPLY SCHEME | SM/10996 | New | Formal order for the work of Additional work of laying of HDPE distribution pipe line 75/90 mm dia and providing FHTC at Kotalpukur (JL-30),Nimtakuri(JL-32) & Masna(JL-31) mouzas of Kotalpukur piped W/s Scheme under DWSD,PHE Dte (SL-03) |  |  | ORD/000253/2022-2023 | 1426/DWSD | 08/10/2022 | 18/10/2022 | JOY GURU ENTERPRISE | 12.21 | 8.7 | 71.25 | 0
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | KOTALPUKUR PIPED WATER SUPPLY SCHEME | SM/10996 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Kotalpukur,Masna,Nimtikuri mouzas of Kotalpukur piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-02) |  |  | ORD/000165/2022-2023 | 773/DWSD | 17/05/2022 | 01/07/2022 | JOY GURU ENTERPRISE | 41.01 | 35.36 | 86.23 | 0
Total | [13 empty] | 53.22 | 44.06 | 82.79