## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | GARKILLA KHEROBARI PIPED WATER SUPPLY SCHEME. | SM/10998 | New | Quotation for Garkilla Kherobari W/S Scheme, P.H. No - 01, Gopalpur CCC |  |  | BILL/00181/2022-2023 | BP-2022-23-332 | 15/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.8 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | GARKILLA KHEROBARI PIPED WATER SUPPLY SCHEME. | SM/10998 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Garkilla-Kherobari,Gourangapur(28) mouzas of Garkilla-Kherobari piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-5) |  |  | ORD/000167/2022-2023 | 764/DWSD | 13/05/2022 | 27/06/2022 | BABA LOKENATH ENTERPRISE | 28.84 | 17.78 | 61.67 | 100
Total | [13 empty] | 31.64 | 17.78 | 56.21