## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | DHOBARU PIPED WATER SUPPLY SCHEME | SM/10999 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at DHOBARU mouza of Dhobaru piped W/s Scheme under DWSD, PHE Dte (Part-A ,B and C) (SL-01) |  |  | ORD/000166/2022-2023 | 774/DWSD | 17/05/2022 | 01/07/2022 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 44.99 | 0 | 0 | 100
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | DHOBARU PIPED WATER SUPPLY SCHEME | SM/10999 | New | Quotation for Dhobaru W/S Scheme , Pump House No- 01 , Panagarh CCC |  |  | BILL/00204/2022-2023 | BP-2022-23-335 | 17/03/2023 | 17/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.47 | 0 | 0 | 0
Total | [13 empty] | 49.46 | 0 | 0