## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | BANAGRAM PIPED WATER SUPPLY SCHEME | SM/11223 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distributing pipe line and providing FHTC at BONAGRAM Mouza of Bonagaram piped W/s Scheme under DWSD, PHE Dte(Part-A ,B & C)(SL-04) |  |  | ORD/000210/2022-2023 | 789/DWSD | 18/05/2022 | 02/07/2022 | BISHAL ENTERPRISE | 22.78 | 18.75 | 82.31 | 100
2 | PASCHIM BARDHAMAN | Kanksa | RCFA Division -I | BANAGRAM PIPED WATER SUPPLY SCHEME | SM/11223 | New | Acceptance cum work order Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Banagram PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer 7 | ORD/001077/2023-2024 | 693/RCD-I | 29/02/2024 | 27/08/2024 | B M ENTERPRISE | 1.6 | 0 | 0 | 0
Total | [13 empty] | 24.38 | 18.75 | 76.92