## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME | SM/11224 | New | Formal order for the work of laying distribution system ,Rising main ,constrcution of 250 M3 Reservoir with 20 mtr staing height including soil inverstigation ,construction of Pump house (5.4X3.60) with sanitary and Water supply arrangement and construction of Pump house (3.60 X 3.00 m) wiht FHTC for Birudiha piped W/s Scheme under DWSD ,PHE Dte (New Scheme). |  |  | ORD/000250/2022-2023 | 1437/DWSD | 13/10/2022 | 13/10/2023 | KHAN ENTERPRISE | 524.96 | 477.66 | 90.99 | 100
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME | SM/11224 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Birudiha piped W/s Scheme under DWSD ,PHE Dte (SL-04) |  |  | ORD/000225/2022-2023 | 1241/DWSD | 18/08/2022 | 02/09/2022 | MD AAMIR KHAN | 14.75 | 14.3 | 96.89 | 0
3 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME | SM/11224 | New | Dismantling of concrete road and bituminiou road and land development for constrution of 250 M3 OHR of 20 mtr staging height as per Deptt drawing ,laying alingining of rising main and provding FHTC connection of all mouzas under command area of Birudiha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000087/2023-2024 | 722/DWSD | 11/05/2023 | 05/06/2023 | M/S K.B.CONSTRUCTION | 30.05 | 29.88 | 99.41 | 100
4 | PASCHIM BARDHAMAN | Kanksa | Central Mechanical | BIRUDIHA PIPED WATER SUPPLY SCHEME | SM/11224 | New | Supply & Installation of Submersible Pumping Machinery, Voltages Stabilizer , Chlorination system and internal House wiring for Tube well for Tube well no:- 1 & 2 at Birudiha water supply scheme under CMD PHE Dte, Dist: Paschim Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000011/2023-2024 | 1657/CMD | 06/04/2023 | 06/05/2023 | MAA TARA ENTERPRISE | 21.19 | 20.56 | 97.03 | 100
5 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME | SM/11224 | New | New service connection charges for birudiha Water Supply scheme (TW-2) |  |  | BILL/00148/2023-2024 | BP-2023-24-89 | 17/07/2023 | 17/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.27 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME | SM/11224 | New | Quotation money for new electric service connection at Birudiha under Birudiha piped W/s Scheme. |  |  | BILL/00063/2023-2024 | BP-2023-24-38 | 01/06/2023 | 01/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.29 | 0 | 0 | 0
Total | [13 empty] | 593.53 | 542.4 | 91.39