## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Shyambazar Piped water Supply Scheme | SM/11228 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Shyambazar piped W/s Scheme under DWSD ,PHE Dte (SL-01) |  |  | ORD/000222/2022-2023 | 1233/DWSD | 17/08/2022 | 01/09/2022 | M/S. D. PALIT & CO. | 14.76 | 13.63 | 92.36 | 0
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Shyambazar Piped water Supply Scheme | SM/11228 | New | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Shyambazar ,Telipara piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000564/2022-2023 | 527/DWSD | 29/03/2023 | 13/04/2023 | MEASURE LAND | 5 | 5 | 100 | 0
3 | PASCHIM BARDHAMAN | Kanksa | Central Mechanical | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Shambazar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. |  |  | ORD/000006/2023-2024 | 1580/CMD | 04/04/2023 | 04/05/2023 | A.S. ENTERPRISE | 9.3 | 8.81 | 94.67 | 100
4 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Shyambazar Piped water Supply Scheme | SM/11228 | New | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 255/C/DWSD | 15/02/2023 | 15/02/2023 | Resource Division | 5.32 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Shyambazar Piped water Supply Scheme | SM/11228 | New | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 1231/DWSD | 17/08/2022 | 17/08/2022 | Resource Division | 18.93 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Shyambazar Piped water Supply Scheme | SM/11228 | New | Quotation for Shyambazar W/S Scheme , Pump House No- 01 , Panagarh CCC |  |  | BILL/00208/2022-2023 | BP-2022-23-340 | 17/03/2023 | 17/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.65 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Shyambazar Piped water Supply Scheme | SM/11228 | New | Quotation for Shyambazar W/S Scheme, P.H. No - 02, Panagarh CCC |  |  | BILL/00179/2022-2023 | BP-2022-23-331 | 15/03/2023 | 15/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.36 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN | Kanksa | Central Mechanical | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Shambazar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. |  |  | ORD/000005/2023-2024 | 1579/CMD | 04/04/2023 | 04/05/2023 | MS DAS ELECTRIC CO | 9.3 | 8.87 | 95.3 | 100
9 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Shyambazar Piped water Supply Scheme | SM/11228 | New | Formal order for the work of laying distribution system ,rising main construction of 150 M3 with 20 mtr staging height including soil investigation construction of Pump house (5.4X3.6 m) with sanitary and Water supply arrangement and construction of pump house (3.6X3.00 mtr) for Shyambazar W/s Scheme under DWSD ,PHE Dte (New Scheme) |  |  | ORD/000267/2022-2023 | 1648/DWSD | 02/12/2022 | 30/11/2028 | DUTTA ENTERPRISE | 213.72 | 194.67 | 91.09 | 100
10 | PASCHIM BARDHAMAN | Kanksa | Asansol Mechanical | Shyambazar Piped water Supply Scheme | SM/11228 | New | Lowering of column pipe including withdrawing, lowring and other allied works at Shyambazar, TW No.-01, under Block - Kanksa, Dist - Paschim Bardhaman under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-3 | ORD/000390/2025-2026 | 1959/AE-II/AMD | 10/12/2025 | 20/12/2025 | MITRA ENTERPRISE | 0.34 | 0 | 0 | 100
Total | [13 empty] | 282.68 | 230.97 | 81.71