## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | New | Formal order for the work of laying distribution system rising main construction of 150 M3 reservoir with 20 mtrs staging height including soil investigation construction of Pump house (5.4 m X 3.60 m) with sanitary and water supply arrangement and construction of pump house(3.60 X 3.00 m) with FHTC for Dandeswar water Supply schme under DWSD ,PHE Dte (NS) |  |  | ORD/000264/2022-2023 | 1614/DWSD | 21/11/2022 | 21/11/2023 | POWER TOOLS AND ENGINEERING | 164.79 | 139.27 | 84.52 | 80
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | New | Acceptance cum formal order for the work Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Dandeswar piped W/s Scheme under DWSD ,PHE Dte (SL-03) |  |  | ORD/000224/2022-2023 | 1240/DWSD | 18/08/2022 | 02/09/2022 | M/S BADAL GHOSH | 14.75 | 13.3 | 90.16 | 0
3 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | New | 1 (One) No Trial bore by DR method using rig machine at Dwandeswar ,Block-Kanksa under Augmentation of Dandeswar PWSS under DWSD,PHE Dte |  |  | ORD/000214/2023-2024 | 1446/DWSD | 25/08/2023 | 09/09/2023 | M/S BADAL GHOSH | 1 | 1 | 100 | 100
4 | PASCHIM BARDHAMAN | Kanksa | Central Mechanical | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Dandeshwar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000008/2023-2024 | 1654/CMD | 06/04/2023 | 06/05/2023 | P.K. ENGINEERING | 21.21 | 20.57 | 96.98 | 80
5 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | New | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 255/B/DWSD | 15/02/2023 | 15/02/2023 | Resource Division | 4.24 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | New | New service connection charges for Dandeswar piped Water supply scheme TW-I |  |  | BILL/00062/2023-2024 | BP-2023-24-37 | 01/06/2023 | 01/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.62 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | New | Electricity service charges for Kanchanpur TW-III under Kanksa block of Dandeswar piped W/s Scheme |  |  | BILL/00158/2023-2024 | BP-2023-24-99 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.67 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | New | Electricity service charges for Dandeswar TW-II under Dandeswar piped W/s Scheme |  |  | BILL/00159/2023-2024 | BP-2023-24-100 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.83 | 0 | 0 | 0
Total | [13 empty] | 212.1 | 174.14 | 82.1