## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Formal order for the work of Supplying and laying of different dia UPVC pipe line with necessary allied works at Rangamatia (JL-10),Benebandhi(JL-11) Maheshpur(JL-12) Mouza of Augmentation of RCFA Part-III Piped W/s Scheme (Zone-I) (Part-B) W/s Scheme under DWSD,PHE Dte (SL-07) |  |  | ORD/000180/2022-2023 | 874/DWSD | 26/05/2022 | 20/06/2022 | BASANTI TRADERS | 22.24 | 18.46 | 82.99 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal work order for the work of Withdrawing existing damaged 150 mm dia AC pipe line and laying 160 mm dia (OD) HDPE pipe in the same trench from Madhaiganj OHR site towards Rangamati village under RCFA Pt-III W/S Scheme under DWSD, PHE Dte (SL-24) |  |  | ORD/000350/2020-2021 | 69/DWSD | 13/01/2021 | 28/01/2021 | KARMAKAR CONSTRUCTION | 2.31 | 2.31 | 100 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Formal order for the work of Construction of 500 M3 capacity 20 mtr staging height RCC Over Head Reservoir (OHR) at Mohal under Augmentation of RCFA Part-III (Zone-I/Part-B) W/s Scheme under DWSD, PHE Dte (SL_14) |  |  | ORD/000207/2022-2023 | 278/DWSD | 16/05/2022 | 16/11/2022 | RANJIB GHATAK | 96.93 | 82.66 | 85.28 | 85
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Supplying and laying of different dia UPVC pipe line with necessary allied works at Rangamatia (JL-10),Benebandhi(JL-11) ,Maheshpur(JL-12) mouza of Augmentation of RCFA Part-III W/s Scheme (Zone-I)/Part-A) W/S Scheme under DWSD,PHE Dte.(SL-02) |  |  | ORD/000266/2022-2023 | 1005/DWSD | 28/06/2022 | 13/07/2022 | KIRON ENTERPRISE | 19.46 | 16.77 | 86.18 | 85
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle for site vigit against JJM related scheme) for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.01.2023 to 30.06.2023).(Sl-01) |  |  | ORD/000438/2022-2023 | 1801/DWSD | 30/12/2022 | 30/06/2023 | PRAMIT CHATTERJEE | 0.82 | 0.8 | 96.73 | 0
6 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Providing And Installation of Submersible pumping Machineries, PDB-Cum-MCC Panel and other Electro-Mechanical accessories at Head Works site at Pansuli under Augmentation of RCFA Part-III (Zone-I) Water Supply Scheme, Block-Faridpur-Durgapur, Dist.-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000392/2022-2023 | 252/AMD | 02/02/2023 | 04/03/2023 | INDUSTRIAL ELECTRICAL CORPORATION | 33.68 | 30.8 | 91.44 | 0
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Additional work for rest portion UPVC pipe line and FHTC at Benabandhi (JL-11) and Maheshpur(JL-12) mouza under Augmentaiton of RAFA Part-III Zone-I piped W/S Scheme under DWSD,PHE Dte |  |  | ORD/000033/2023-2024 | 739/DWSD | 22/05/2023 | 21/07/2023 | KIRON ENTERPRISE | 51.72 | 48.44 | 93.67 | 100
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Formal order for the work of Construction of 150 M3 capacity 20 mtr staging height RCC over Head Reservoir (OHR) at Nutandanga under Augmentation of RCFA Part-III W/s Scheme (Zone-I/Part-B) under DWSD, PHE Dte (SL-13) |  |  | ORD/000181/2022-2023 | 875/DWSD | 26/05/2022 | 26/11/2022 | M/S PROCHESTA ENTERPRISE | 64.33 | 56.33 | 87.56 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Laying of CI Pipe line ,sluice valves ,UPVC pipe line and allied works at Madhaiganj H/W Site under Modified RCFA Part-III W/s Scheme under DWSD, PHE Dte (SL-03) |  |  | ORD/000358/2021-2022 | 75/DWSD | 21/01/2022 | 05/02/2022 | KARMAKAR CONSTRUCTION | 2.57 | 2.5 | 97.14 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Continuation order for the work of extension of pipe line from the existing pipe line from command area of Gourbazar-Ichhapur piped W/s Scheme of Ichhapur area fro providing of FHTC at Ichhapur mouza(JL-50) under DWSD ,PHE Dte |  |  | ORD/000476/2021-2022 | 192/DWSD | 15/02/2022 | 02/03/2022 | SHWET BARANI | 4.45 | 4.45 | 99.99 | 100
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Additional work at RCC OHR site at NUTANDANGA under Augmentation of RCFA Part-III (Zone-I) Piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000041/2023-2024 | 766/DWSD | 22/05/2023 | 06/06/2023 | M/S PROCHESTA ENTERPRISE | 4.49 | 4.48 | 99.86 | 100
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 16,17,18 Ext ) to combat drought like situation at Pansiuli head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-02) |  |  | ORD/000127/2023-2024 | 11/SPOT/DWSD | 16/06/2023 | 20/06/2023 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No -11,12 Ext & 4 New ) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-03) |  |  | ORD/000128/2023-2024 | 12/SPOT/DWSD | 16/06/2023 | 20/06/2023 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 7,9,10 Ext) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-03) |  |  | ORD/000117/2023-2024 | 06/SPOT/DWSD | 16/06/2023 | 20/06/2023 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Laying additional distribution pipeline with necessary allied works for providing FHTC work under Durgapur-Faridpur Block of Augmentation of RCFA Part-III W/s Scheme (Zone-I) under DWSD,PHE Dte |  |  | ORD/000666/2022-2023 | 1146/DWSD. | 04/07/2022 | 24/07/2022 | SHWET BARANI | 5.69 | 5.64 | 99.3 | 100
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Instalation of Water Level Indicater at Loudoha head work site under RCFA,Part-III ,Zone -I W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-07) |  |  | ORD/000132/2023-2024 | 16/SPOT/DWSD | 16/06/2023 | 23/06/2023 | KARMAKAR CONSTRUCTION | 0.77 | 0.77 | 100 | 100
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Drawing ,design and surveying work for proposed piped W/s Scheme of Sarpi W/S Scheme under DWSD, PHE Dte(SL-02) |  |  | ORD/000154/2022-2023 | 1022/DWSD | 04/07/2022 | 14/07/2022 | APEX ENGINEERING | 4.09 | 4.09 | 100 | 100
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No -10,13 Ext & 14 New ) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-04) |  |  | ORD/000129/2023-2024 | 13/SPOT/DWSD | 16/06/2023 | 20/06/2023 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 1,3,4 Ext) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-01) |  |  | ORD/000137/2023-2024 | 1254/DWSD | 02/08/2023 | 12/08/2023 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
20 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 3,4,5 Ext) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-01) |  |  | ORD/000105/2023-2024 | 04/SPOT/DWSD | 16/06/2023 | 20/06/2023 | KARMAKAR CONSTRUCTION | 1 | 1 | 100 | 100
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of RCFA Part - III Zone - I (PART - B) under Durgapur Faridpur Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 03) |  |  | ORD/000184/2023-2024 | 1201/DWSD | 27/07/2023 | 03/08/2023 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
22 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 255/A/DWSD | 15/02/2023 | 15/02/2023 | Resource Division | 30.8 | 0 | 0 | 0
23 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1377/DWSD | 22/09/2022 | 22/09/2022 | Resource Division | 61.6 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 256/DWSD | 15/02/2023 | 15/02/2023 | Resource Division | 61.6 | 0 | 0 | 0
25 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 1228/DWSD | 17/08/2022 | 17/08/2022 | Resource Division | 9.52 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Urgent Repairing of 250 dia pipe line with necessary alid works at Nabaghanapur to Jhanjra Project Portion under Augmentation 0f RCFA ,Pt-III, Zone -I W/S Scheme (JJM) Under Durgapur Water Supply Division, P.H.E. Dte. (Sl-02) |  |  | ORD/000054/2023-2024 | 838/DWSD | 05/06/2023 | 20/06/2023 | RUBY CONSTRUCTION | 0.75 | 0 | 0 | 100
27 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum formal order for the work of Providing FHTC work at Rangamati Mouza(JL-10) under Augmentation of RCFA Part-III(Zone-I) piped W/S Scheme under DWSD,PHE Dte (SM/11454) |  |  | ORD/000069/2023-2024 | 1066/DWSD | 12/07/2023 | 11/08/2023 | BASANTI TRADERS | 18.67 | 11.68 | 62.53 | 50
28 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Additioinal work for rest portion UPVC pipe line at Rangamati mouza under Augmentation of RCFA Part-III(Zone-I) piped W/S Scheme under DWSD,PHE Dte (SM/11454) |  |  | ORD/000084/2023-2024 | 1073/DWSD | 12/07/2023 | 06/08/2023 | BASANTI TRADERS | 9.56 | 6.54 | 68.35 | 100
29 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum work order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. jack Pushing Method etc) for crossing of NH-60 near Pandabeswar H/W Site to carry 350 mm dia distribution & 250 mm dia rising main pipe line under RCFA Part-III Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 3 |  | ORD/000018/2024-2025 | 1521/RCD-I | 14/06/2024 | 29/07/2024 | HIRANMAY GHOSH | 14.09 | 0 | 0 | 0
30 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Formal order for the work of Sinking of 4 Nos 200 mm dia river bed tube wells with collecting main in river Ajoy at Pansuili H/W under Augmentation of RCFA Part-III(Zone-I)(Part-B) W/S Scheme under DWSD,PHE Dte. (SL_09) |  |  | ORD/000208/2022-2023 | 856/DWSD | 24/05/2022 | 03/06/2022 | RANAJOY ENTERPRISE | 19.57 | 14.03 | 71.72 | 100
31 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Formal order for the work of of Sinking of 4 Nos 200 mm dia river bed tube wells with collecting main in river Ajoy at Pansuili H/W under Augmentation of RCFA Part-III(Zone-I)(Part-A) W/S Scheme under DWSD,PHE Dte. (SL_15) |  |  | ORD/000209/2022-2023 | 857/DWSD | 24/05/2022 | 08/06/2022 | RANAJOY ENTERPRISE | 18.48 | 14.81 | 80.16 | 100
32 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Formal order for the work of Augmentation of RCFA Part-III )Zone-I/Part-B) piped W/s Scheme by construction of 250 M3 RCC OHR of 20 mtr staging height with necessary interconnection soil investigation including laying distribution network and Functional House Tap Connection (FHTC) under DWSD,PHE Dte ,Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (Sl-01 |  |  | ORD/000373/2022-2023 | 1779/DWSD | 23/12/2022 | 04/01/2023 | UMWELT ENGINEER PVT LTD | 919.36 | 917.39 | 99.79 | 90
33 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Continuation order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle for site vigit against JJM related scheme) for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.07.2023 to 31.12.2023).(Sl-01) |  |  | ORD/000102/2023-2024 | 944/DWSD | 28/06/2023 | 28/12/2023 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 288.57 | 100
34 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Quotation for natundanga O.H.R. under RCFA-III(Zone-I) Water supply scheme. |  |  | BILL/00481/2024-2025 | BP-2024-25-43 | 05/09/2024 | 05/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.09 | 0 | 0 | 0
35 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Formal order for the work of augmentation at Madhaiganj of RCFA Part-III (Zone-I/C) piped W/s Scheme including laying distribution network and functional household tap connection (FHTC) under Durgapur W/S Division, PHE Dte Block-Durgapur-Faridpur ,Dist.-Paschim Bardhhaman. |  |  | ORD/000380/2022-2023 | 05/DWSD | 02/01/2023 | 02/05/2023 | IJABUL SEKH | 279.99 | 236.03 | 84.3 | 100
36 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum Work Order for Construction of Sub-Station Building at Ramnagar H/W Site within Pandabeswar Block under RCFA Part-III (Zone-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 3,Assistant Engineer 4 | Junior Engineer | ORD/000373/2024-2025 | 3101/RCD-I | 13/12/2024 | 01/10/2025 | RANJIB GHATAK | 36.86 | 0 | 0 | 90
37 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia Horizontal River Bed Tube Well with fitting of 200 mm dia Strainer (12.2 mtr) in river Ajay & Collecting line under RCFA Part-III Zone-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer,Junior Engineer 7 | ORD/000020/2024-2025 | 1523/RCD-I | 14/06/2024 | 29/07/2024 | T M CONCRETE CREATION PVT.LTD | 14.42 | 0 | 0 | 100
38 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum work order for Laying of Rising main and other allied works from Panshuili H/W Site to Natundanga OHR of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | Assistant Engineer 3,Assistant Engineer 4 | Junior Engineer | ORD/000224/2024-2025 | 2556/RCD-I | 29/10/2024 | 27/04/2025 | UNITED CONSTRUCTION | 36.87 | 2.57 | 6.96 | 70
39 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum work order for Additional pipe line with of HDPE pipe with at Pratappur and Kalikapur with re-connection of existing FHTC and other allied works of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer 9 | ORD/000291/2024-2025 | 2628/RCD-I | 14/11/2024 | 15/05/2025 | SIMA ENTERPRISE | 57.5 | 9.31 | 16.19 | 80
40 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum work order for Allied work of Replacement of A.C pipe of Main Distribution pipeline from Madhaiganj OHR to RANGAMATI Village including ROAD Restoration of Rangamati Village Of Augmentation of RCFA part III Zone I under RCFA Div- I, PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000217/2024-2025 | 2547/RCD-I | 29/10/2024 | 01/04/2025 | BASANTI TRADERS | 32.79 | 4.65 | 14.17 | 40
41 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum work order for HDPE distribution pipe line laying for Gourbazar and Bhabanandapur village and other allied works under Augmentation of RCFA Part-III (Zone-I) PWSS under RCFA Davison-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000263/2025-2026 | 1485/RCD-I | 15/05/2025 | 12/09/2025 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 34.41 | 0 | 0 | 80
42 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Acceptance cum work order for Supplying laying HDPE distribution pipe line at JhanjraPaschim Para at Durgapur Faridpur Block under Augmentation of RCFA Part-III Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer,Junior Engineer 9 | ORD/000325/2025-2026 | 1511/RCD-I | 20/05/2025 | 15/08/2025 | UNITED CONSTRUCTION | 22.25 | 0 | 0 | 60
43 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | Augmentation | Formal order for the work of Augmentation at Natundanga of RCFA Part-III (Zone--I/A) piped W/s Scheme including laying distribution network (LDS) and functinal household tap connection (FHTC) under Durgapur W/s Division, PHE Dte ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman (SL-02) |  |  | ORD/000372/2022-2023 | 1778/DWSD | 23/12/2022 | 31/12/2024 | ALOK ENTERPRISE | 634.56 | 448.32 | 70.65 | 75
Total | [13 empty] | 2634.88 | 1952.96 | 74.12