## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | New | Quotation for Napara W/S Scheme, P.H. No - 1, Gopalpur CCC |  |  | BILL/00177/2022-2023 | BP-2022-23-329 | 15/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.02 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Napara piped W/s Scheme under DWSD ,PHE Dte (SL-08) |  |  | ORD/000230/2022-2023 | 1255/DWSD | 23/08/2022 | 07/09/2022 | SK. ALIM | 14.76 | 14.73 | 99.78 | 0
3 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | New | Quotation for Napara W/S Scheme, P.H. No - 02, Gopalpur CCC |  |  | BILL/00178/2022-2023 | BP-2022-23-330 | 15/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.8 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | New | Acceptance cum formal order for the work of Dismantling of concrete road for laying distribution system rising main construction of 350 M3 reservoir with 20 mtr staging height including soil investigation construction of pump house (5.40 X 3.60 m) with sanitary and construction of pump house 3.60 X 3.00 m) for Napara piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000570/2022-2023 | 489/DWSD | 23/03/2023 | 12/04/2023 | SK. ABDUL HALIM | 4.39 | 4.39 | 99.97 | 0
5 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 789/DWSD | 25/05/2023 |  | Resource Division | 47.9 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | New | Formal order for the work of laying distribution system, Rising main construction of 350 M3 Over Head Reservoir with 20 Mtr staging height including soil investigation ,construction of Pump House (5.4X3.6mtr) with Sanitary and water supply arrangement & construction of Pump house (3.6X3.00 m) with FHTC for NAPARA piped W/s Scheme under DWSD,PHE Dte ,Dist.-Paschim Bardhhaman. |  |  | ORD/000221/2022-2023 | 1174/DWSD | 02/08/2022 | 14/08/2022 | SK. ALIM | 522.15 | 514.4 | 98.51 | 100
7 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.03.2023 to 31.08.2023). (Sl-01) |  |  | ORD/000502/2022-2023 | 134/DWSD | 31/01/2023 | 30/07/2023 | BIPLAB BANERJEE | 0.82 | 2.4 | 291.2 | 80
8 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.09.2023 to 29.02.2024). (Sl-01) |  |  | ORD/000174/2023-2024 | 1397/DWSD | 17/08/2023 | 13/02/2024 | BIPLAB BANERJEE | 0.82 | 0.6 | 72.7 | 30
9 | PASCHIM BARDHAMAN | Kanksa | RCFA Division -I | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | New | Acceptance cum work order for Trial run & special Maintenance of Rising main & Distribution system with operating of valve within command area under Augmentation of Napara PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months. | Assistant Engineer 2 |  | ORD/001065/2023-2024 | 683/RCD-I | 29/02/2024 | 27/08/2024 | NATIONAL CONSTRUCTION | 2.21 | 0 | 0 | 0
Total | [13 empty] | 604.87 | 536.51 | 88.7