## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 694/DWSd | 08/05/2023 |  | Resource Division | 21.35 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | New | New service connection charges for jatgoria piped W/s Scheme |  |  | BILL/00082/2023-2024 | BP-2023-24-54 | 08/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.22 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | New | New service connection charges for jatgoria water supply scheme TW-2 |  |  | BILL/00083/2023-2024 | BP-2023-24-55 | 08/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.17 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Jatgoria piped W/s Scheme under DWSD ,PHE Dte(SL-07) |  |  | ORD/000229/2022-2023 | 1254/DWSD | 23/08/2022 | 07/09/2022 | RANJIB GHATAK | 14.75 | 14.03 | 95.11 | 100
5 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | New | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 255/E/DWSD | 15/02/2023 |  | Resource Division | 3.88 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN | Kanksa | Central Mechanical | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Jatgaria Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000010/2023-2024 | 1655/CMD | 06/04/2023 | 06/05/2023 | CHOUDHURY ENTERPRISE | 21.07 | 15.26 | 72.4 | 40
7 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex, Banskopa,DGP-12 (w.e.f 18.02.2024 to 29.02.2024). (SL-02) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000314/2023-2024 | 186/DWSD | 15/02/2024 | 27/02/2024 | PRAMIT CHATTERJEE | 0.05 | 0 | 0 | 100
8 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | New | Formal order for the work laying distribution system rising main ,construction of 100M3 reservoir with 20mtr staging height including soil investigation construction of pump house (5.40X3.60 m) with sanitary and water supply arrangement and construction of pump house (3.6 X 3.00 m) for Jatgoria W/s Scheme ,Kanksa block under DWSD,PHE Dte (NS) |  |  | ORD/000269/2022-2023 | 1656/DWSD | 05/12/2022 | 30/11/2023 | SUPER SKILL | 170.87 | 98 | 57.35 | 45
Total | [13 empty] | 240.38 | 127.29 | 52.95