## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | GARADAHA PIPED WATER SUPPLY SCHEME. | SM/11934 | New | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distributing pipe line and providing FHTC at Garadaha Mouza of Garadaha piped W/s Scheme under DWSD, PHE Dte (Part-A ,B & C) (SL-03) |  |  | ORD/000237/2022-2023 | 775/DWSD | 17/05/2022 | 01/07/2022 | SHWET BARANI | 38.51 | 19.92 | 51.72 | 0
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | GARADAHA PIPED WATER SUPPLY SCHEME. | SM/11934 | New | Quotation for Garadaha W/S Scheme, P.H. No - 01, Panagarh CCC |  |  | BILL/00180/2022-2023 | BP-2022-23-328 | 15/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.75 | 0 | 0 | 0
Total | [13 empty] | 44.26 | 19.92 | 45