## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Amlajora, Birudiha piped W/s Scheme and Kataberia PWSS under DWSD, PHE Dte |  |  | ORD/000565/2022-2023 | 528/DWSD | 29/03/2023 | 13/04/2023 | MEASURE LAND | 7.53 | 7.53 | 100 | 0
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Acceptance cum formal order for the work of sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Amlajora piped W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000223/2022-2023 | 1234/DWSD | 17/08/2022 | 01/09/2022 | JOY GURU ENTERPRISE | 14.68 | 14.14 | 96.32 | 0
3 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 255/F/DWSD | 15/02/2023 | 15/02/2023 | Resource Division | 10.47 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 787/DWSD | 25/05/2023 | 25/05/2023 | Resource Division | 25.85 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Electricity service connection for Amlajora H/W site under Amlajora piped W/s Scheme |  |  | BILL/00156/2023-2024 | BP-2023-24-97 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Electricity service connection charges for Amlajora H/W Site TW-II under Amlajora Piped W/s Scheme |  |  | BILL/00157/2023-2024 | BP-2023-24-98 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.52 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Formal order for the work of laying distribution system rising main construction of 250 M3 Over Head Reservoir with 20 Mtr staging height including soil investigation ,construction of Pump House (5.4X3.6mtr) with FHTC for Amlajora piped W/s Scheme under DWSD,PHE Dte ,Dist-Paschim Bardhaman. |  |  | ORD/000220/2022-2023 | 1175/DWSD | 02/08/2022 | 14/08/2022 | RANADHIR SINHA | 426.89 | 287.14 | 67.26 | 100
8 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.09.2023 to 29.02.2024). (Sl-01) |  |  | ORD/000174/2023-2024 | 1397/DWSD | 17/08/2023 | 17/02/2024 | BIPLAB BANERJEE | 0.82 | 1.58 | 192.52 | 30
9 | PASCHIM BARDHAMAN | Kanksa | Asansol Mechanical | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Supply & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Tube Well No-II at Amlajora Water Supply Scheme, under Asansol Mechanical Division, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000632/2023-2024 | 531/AMD | 12/03/2024 | 10/06/2024 | M/S SAJAHAN CHOWDHURY | 11.46 | 11.46 | 100 | 100
10 | PASCHIM BARDHAMAN | Kanksa | Asansol Mechanical | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | New | Supply & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Tube Well No-I at Amlajora Water Supply Scheme, under Asansol Mechanical Division, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000631/2023-2024 | 530/AMD | 12/03/2024 | 10/06/2024 | P.K.ENGINEERING | 11.43 | 11.15 | 97.57 | 100
Total | [13 empty] | 511.32 | 333.01 | 65.13