## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 12 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000314/2022-2023 | 271/DWSD | 16/02/2023 | 02/04/2023 | SHWET BARANI | 32.57 | 14.8 | 45.43 | 100
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A(From New. OHR Ramnagar )(Part - 6 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000282/2022-2023 | 45/DWSD | 11/01/2023 | 25/02/2023 | RANJIB GHATAK | 21.38 | 16.28 | 76.12 | 85
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar ) (Part - 1B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte.(DL-02) |  |  | ORD/000271/2022-2023 | 272/DWSD | 16/02/2023 | 02/04/2023 | GHOSH ENTERPRISE | 31.84 | 15.06 | 47.31 | 100
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 6 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000289/2022-2023 | 1696/DWSD | 09/12/2022 | 23/01/2023 | HIRANMAY GHOSH | 30.39 | 29.96 | 98.59 | 68
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 13 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000321/2022-2023 | 29/DWSD | 09/01/2023 | 23/02/2023 | PRAVAT SARKAR | 28.7 | 16.11 | 56.14 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 16 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000332/2022-2023 | 28/DWSD | 09/01/2023 | 23/02/2023 | M/S MONDAL ENTERPRISE | 23.8 | 21.49 | 90.27 | 90
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 17 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000333/2022-2023 | 27/DWSD | 09/01/2023 | 23/02/2023 | M/S BADAL GHOSH | 38.49 | 18.77 | 48.78 | 0
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II B (From Mahal OHR) (Part - 14 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000322/2022-2023 | 1710/DWSD | 09/12/2022 | 23/01/2023 | CHATTERJEE CONSTRUCTION | 20.6 | 19.56 | 94.94 | 85
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 14 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000323/2022-2023 | 1711/DWSD | 09/12/2022 | 23/01/2023 | SAIKAT RAY | 21.33 | 14.24 | 66.79 | 85
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 7 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000290/2022-2023 | 1697/DWSD | 09/12/2022 | 23/01/2023 | JAYANTA DATTA | 51.74 | 38.7 | 74.8 | 65
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From Ext. OHR Ramnagar )(Part - 4 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte |  |  | ORD/000278/2022-2023 | 46/DWSD | 11/01/2023 | 25/02/2023 | RANJIB GHATAK | 36.4 | 29.81 | 81.91 | 0
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 15 B) Under Augmentation of RCFA Pt - III, Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000325/2022-2023 | 73/DWSD | 18/01/2023 | 04/03/2023 | SARKAR AGENCY | 24.19 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From Ext. OHR Ramnagar )(Part - 3 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte.. |  |  | ORD/000276/2022-2023 | 26/DWSD | 09/01/2023 | 23/02/2023 | KIRON ENTERPRISE | 39.5 | 26.2 | 66.34 | 100
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar )(Part - 2 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme(JJM) under Durgapur Water Supply Division, PHE Dte.(Sl-4) |  |  | ORD/000273/2022-2023 | 427/DWSD | 13/03/2023 | 27/04/2023 | TARA PRASAD SARKAR | 34.36 | 22.91 | 66.67 | 100
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From Ext. OHR Ramnagar )(Part - 4 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000277/2022-2023 | 1690/DWSD | 09/12/2022 | 23/01/2023 | RANJIB GHATAK | 52.17 | 47.46 | 90.97 | 70
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From New. OHR Ramnagar )(Part - 7 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000302/2022-2023 | 426/DWSD | 13/03/2023 | 27/04/2023 | DIP CONSTRUCTION | 34.53 | 14.98 | 43.39 | 65
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From Ext. OHR Ramnagar )(Part - 5 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte |  |  | ORD/000281/2022-2023 | 270/DWSD | 16/02/2023 | 02/04/2023 | D. S. ENTERPRISE | 27.65 | 12.83 | 46.39 | 100
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From New OHR Ramnagar) (Part - 10 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000298/2022-2023 | 1701/DWSD | 09/12/2022 | 23/01/2023 | BABA LOKENATH ENTERPRISE | 58.48 | 50.06 | 85.6 | 75
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar )(Part - 2 A) Under Augmentation of RCFA Pt - III Zone - II W/S (JJM) Scheme under Durgapur Water Supply Division, PHE Dte.(S-3) |  |  | ORD/000272/2022-2023 | 1686/DWSD | 09/12/2022 | 23/01/2023 | AMAR CONSTRUCTION | 45.34 | 42.47 | 93.66 | 80
20 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A(From New. OHR Ramnagar )(Part - 10 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000300/2022-2023 | 391/DWSD | 01/03/2023 | 15/04/2023 | BISHAL ENTERPRISE | 38.7 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 11 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000303/2022-2023 | 1704/DWSD | 09/12/2022 | 23/01/2023 | AMARANJALI CONSTRUCTION | 37.9 | 31.57 | 83.3 | 65
22 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 16 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000327/2022-2023 | 1715/DWSD | 09/12/2022 | 23/01/2023 | M/S MONDAL ENTERPRISE | 29.3 | 28.85 | 98.46 | 100
23 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 12 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000313/2022-2023 | 1706/DWSD | 09/12/2022 | 23/01/2023 | SUJAY KUMAR RAY | 50.44 | 45.54 | 90.28 | 85
24 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From New. OHR Ramnagar )(Part - 8 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000293/2022-2023 | 1698/DWSD | 09/12/2022 | 23/01/2023 | ASHA CONSTRUCTION | 35.77 | 23.48 | 65.65 | 85
25 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 9 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000294/2022-2023 | 1699/DWSD | 09/12/2022 | 23/01/2023 | JOY GURU ENTERPRISE | 49.65 | 43.58 | 87.77 | 90
26 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From New. OHR Ramnagar )(Part - 9 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte |  |  | ORD/000295/2022-2023 | 387/DWSD | 01/03/2023 | 15/04/2023 | JOY GURU ENTERPRISE | 26.58 | 17.48 | 65.79 | 100
27 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 15 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000324/2022-2023 | 1712/DWSD | 09/12/2022 | 23/01/2023 | MAITO MAA ENTERPRISE | 33.13 | 28.92 | 87.29 | 100
28 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 11 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000304/2022-2023 | 428/DWSD | 13/03/2023 | 27/04/2023 | AMARANJALI CONSTRUCTION | 31.13 | 12.76 | 41.01 | 80
29 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 13 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000315/2022-2023 | 1708/DWSD | 09/12/2022 | 23/01/2023 | B.M. SARKAR | 40.19 | 27.41 | 68.2 | 0
30 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II B (From Mahal OHR) (Part - 17 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000326/2022-2023 | 1714/DWSD | 09/12/2022 | 23/01/2023 | M/S BADAL GHOSH | 58.47 | 54.83 | 93.78 | 85
31 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Supply, delivery and installation of Electro-Mechanical equipment at Mahal & ECL Head Works site in the basis for ''Augmentation of Ramnagar Head Works site under R.C.F.A.-III(Zone-II) water supply scheme" under Asansol Mechanical Division, P.H.E. Dte., Block-Pandabeswar, District-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000413/2022-2023 | 362/AMD | 09/02/2023 | 10/05/2023 | R.N.S TRADING | 83.82 | 52.68 | 62.85 | 62
32 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Additional work at RCC Over Head Reservoir (OHR) Site at Ramnagar H/W Site under Augmentation 0f RCFA, Pt- III , Zone- II Water Supply Scheme (JJM) under Durgapur Water Supply Division, P.H.E. Dte. (Sl- 01) |  |  | ORD/000053/2023-2024 | 839/DWSD | 05/06/2023 | 20/06/2023 | RANJIB GHATAK | 0.95 | 0 | 0 | 0
33 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Additional work for connection of OHR to distribution main and supplying and laying of UPVC pipe line and laying of 600 mm dia RCC NP3 hume pipe modern hydraulic Jack pushing method including laying of 250 mm dia MS pipe with necessary allied works at Mohal OHR to Gobindapur under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000213/2023-2024 | 1448/DWSD | 25/08/2023 | 24/09/2023 | SAIKAT RAY | 11.66 | 0 | 0 | 0
34 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Repairing and road restoration side drainage system and other allied FHTC related works at Patseura village under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD. |  |  | ORD/000278/2023-2024 | 1564/DWSD | 20/09/2023 | 05/10/2023 | SHWET BARANI | 3.66 | 0 | 0 | 0
35 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar) (Part - 1A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000270/2022-2023 | 1684/DWSD | 09/12/2022 | 23/01/2023 | M/S KALYANI ENTERPRISE | 43.17 | 41.37 | 95.83 | 100
36 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works for shifting of existing line due to ROB at Pandabeswar under RCFA Pt-III (Zone-II) W/s Scheme under DWSD,PHE Dte. (SL-6) |  |  | ORD/000280/2021-2022 | 1571/DWSD | 27/10/2021 | 16/11/2021 | RANJIB GHATAK | 3.59 | 3.59 | 99.77 | 0
37 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of demarcation of new land for mahal OHR site and repairing of UPVC pipe line and allied works at Konda ,Gobindapur village under Modified RCFA Part-III W/s Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000136/2022-2023 | 952/DWSD | 16/06/2022 | 26/06/2022 | RANJIB GHATAK | 3.19 | 3.19 | 100 | 0
38 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Laying of 600 mm dia RCC (NP3) Hume pipe by modern Hydraulic Jack pushing method including laying 150 mm dia MS pipe line at DVC More over Suri road (NH-60) for ROB under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD, PHE Dte (SL_12) |  |  | ORD/000261/2022-2023 | 872/DWSD | 26/05/2022 | 10/06/2022 | RANJIB GHATAK | 13.63 | 13.49 | 98.97 | 100
39 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | formal order for the work of Repairing ,shifting and replacing of UPVC pipe line and allied works at Fulbagan More to WBSEDCL office under Augmentation of RCFA Part-III (Zone-II) piped W/S Scheme under DWSD ,PHE Dte |  |  | ORD/000449/2022-2023 | 388/DWSD | 01/03/2023 | 21/03/2023 | RANJIB GHATAK | 6.59 | 6.58 | 99.83 | 0
40 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 1,2,3 Ext) to combat drought like situation at Ramnagar head work site under Augmentation of RCFA,Part-III (Zone-II) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-01) |  |  | ORD/000126/2023-2024 | 10/SPOT/DWSD | 16/06/2023 | 20/06/2023 | RANJIB GHATAK | 0.99 | 0.99 | 100 | 100
41 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 4,5 ,6 Ext ) to combat drought like situation at Ramnagari head work site under Augmentation of RCFA,Part-III (Zone-II) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-02) |  |  | ORD/000111/2023-2024 | 05/SPOT/DWSD | 16/06/2023 | 20/06/2023 | RANJIB GHATAK | 0.99 | 0.99 | 100 | 100
42 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 12,14,15 Ext ) to combat drought like situation at Ramnagari head work site under Augmentation of RCFA,Part-III (Zone-II) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-04) |  |  | ORD/000118/2023-2024 | 07/SPOT/DWSD | 16/06/2023 | 20/06/2023 | RANJIB GHATAK | 0.99 | 0.99 | 100 | 100
43 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Repairing of existing concrete road restoration and other allied works at Konda ,Gobindapur mouza under Augmentation of RCFA Part-III (Zone-I) piped W/s Scheme under DWSD,PHE Dte (Part-A) |  |  | ORD/000167/2023-2024 | 1299/DWSD | 07/08/2023 | 22/08/2023 | SAIKAT RAY | 9.62 | 8.22 | 85.39 | 100
44 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Additional work supplying and laying of UPVC pipe le and laying with necessary allied works at Mohal ,Gobindapur under Augmentation of RCFA Part-III (Zone-II) (Part-B) Piped W/s Scheme under DWSD,PHE Dte |  | JUNIOR ENGINEER-2 | ORD/000216/2023-2024 | 1452/DWSD | 25/08/2023 | 19/09/2023 | M/S BADAL GHOSH | 9.78 | 9.72 | 99.42 | 100
45 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Continuation order for the work of ''Laying of 600 mm dia RCC (NP3) Hume pipe by modern Hydraulic Jack pushing method including laying 150 mm dia MS pipe line at DVC More over Suri road (NH-60) for ROB under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD, PHE Dte (SL_12)'' |  |  | ORD/000175/2023-2024 | 748/DWSD | 18/05/2023 | 02/06/2023 | RANJIB GHATAK | 1.51 | 1.5 | 99.42 | 100
46 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of RCFA Part - III Zone - II (PART - B) under Durgapur Faridpur Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-04) |  |  | ORD/000185/2023-2024 | 1235/DWSD | 31/07/2023 | 07/08/2023 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
47 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Additional work at Danya under Augmentation of RCFA Part-III (Zone-II) W/S Scheme (JJM) under DWSD,PHE Dte |  |  | ORD/000275/2023-2024 | 1562/DWSD | 20/09/2023 | 05/10/2023 | MAITO MAA ENTERPRISE | 2.99 | 0 | 0 | 100
48 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 402/DWSD | 03/03/2023 | 03/03/2023 | Resource Division | 271.47 | 0 | 0 | 0
49 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 786/DWSD | 25/05/2023 | 25/05/2023 | Resource Division | 172.1 | 0 | 0 | 0
50 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From Ext. OHR Ramnagar )(Part - 5 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000279/2022-2023 | 1692/DWSD | 09/12/2022 | 23/01/2023 | BASANTI TRADERS | 32.47 | 23.73 | 73.09 | 1
51 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Repairing of existing concrete road restoration and other allied works at Baidhayanathpur mouza under Augmentation of RCFA Part-III (Zone-II) piped W/s Scheme under DWSD,PHE Dte (Part-B) |  |  | ORD/000168/2023-2024 | 1300/DWSD | 07/08/2023 | 01/09/2023 | BASANTI TRADERS | 8.92 | 0 | 0 | 70
52 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Hiring of Maxi Cab (Non Air Conditional ) Bharat Stage-iii/BS-ii purchased on or after 01.05.2008 with Diesel /LPG /CNG Engine for the supervision work of Durgapur W/S Division for office use of Assitant Engineer, RCFA Division-I Public Helth Engineering Directorate, Govt of West Bengal ( w.e.f 01.12.2023. to 31.05.2024) Consumption of Diesel,12 km per litre, Mobil 05 litre per 2500 km. | Assistant Engineer 3 | Junior Engineer 9 | ORD/000727/2023-2024 | 3514/RCD-I | 30/11/2023 | 30/05/2024 | SUBHA TOUR & TRAVELS | 0.89 | 0 | 0 | 35
53 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance order for the work of Supply ,Installation and fabrication of 5 Nos 50 cum./Hr capacity pressure type Iron Elimination Plant which consist of one filter chamber ( dia- 3 m,height -1.5 mtr ) and one oxidation chamber ( dia -1.00 m height -1.2 m) each and Construction of Blower Room (6.50m X 4.00m) With I.E.P. Platform, Plinth, Roof Top Treatment, Plinth Protection and Side Drain at Ramnagar H/W site under Augmentation 0f RCFA, Pt- III (Zone- II) W/S Scheme (JJM) under D.W.S.D., P.H.E. Dte. |  |  | ORD/000334/2022-2023 | 1718/DWSD | 09/12/2022 | 23/01/2023 | ALOK ENTERPRISE | 86.64 | 31.31 | 36.13 | 100
54 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Sinking of 5 Nos 200 mm dia river bed tube wells with collecting main with manifold in river Ajoy at Ramnagar H/W site (Part-A) under Augmentation of RCFA Part-III (Zone-II/JJM) piped W/S Scheme under DWSD,PHE Dte. |  |  | ORD/000446/2022-2023 | 389/DWSD | 01/03/2023 | 16/03/2023 | RANJIB GHATAK | 35.85 | 31.77 | 88.62 | 100
55 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Formal order for the work of Sinking of 6 Nos 200 mm dia river bed tube wells with collecting main with manifold in river Ajoy at Ramnagar H/W site (Part-B) under Augmentation of RCFA Part-III (Zone-II/JJM) piped W/S Scheme under DWSD,PHE Dte. |  |  | ORD/000447/2022-2023 | 390/DWSD | 01/03/2023 | 21/03/2023 | RANJIB GHATAK | 42.39 | 38.97 | 91.93 | 100
56 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Emergent Road restoration dismanttled road of Paranganj mouza of Jemua Piped Water supply scheme under DWSD ,PHE Dte |  |  | ORD/000123/2023-2024 | 1197/DWSD | 27/07/2023 | 31/08/2023 | MAK CONSTRUCTION CO. | 14.52 | 0 | 0 | 100
57 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanksa of Kanksa Block under Augmentation of Kanksa (Zone-II) (Part-C) piped W/S Scheme under DWSD,PHE Dte |  |  | ORD/000156/2023-2024 | 1287/DWSD | 07/08/2023 | 21/09/2023 | MOTIONMASS TECHNO (OPC) PVT LTD | 6.75 | 0 | 0 | 100
58 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Repairing of existing concrete road restoration and other allied works at Dalubandh mouza under Augmentation of RCFA Part-III (Zone-II) piped W/s Scheme under DWSD,PHE Dte (Part-D) |  |  | ORD/000158/2023-2024 | 1289/DWSD | 07/08/2023 | 01/09/2023 | PRAKRITI CONSTRUCTION | 7.82 | 6.54 | 83.58 | 80
59 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Additional work for UPVC pipe line and laying with necessary allied works at Ramnagar (existing OHR Part-2A) under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000219/2023-2024 | 1447/DWSD | 25/08/2023 | 19/09/2023 | RANJIB GHATAK | 9.61 | 0 | 0 | 100
60 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Additional work for collecting main with manifold for IEP at Ramnagar H/W site and DI distribution line at ROB new culvert portion under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000222/2023-2024 | 1499/DWSD | 04/09/2023 | 19/09/2023 | RANJIB GHATAK | 19.4 | 0 | 0 | 100
61 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Quotation for new connection at Natundanga OHR under RCFA Part-III(Zone-II) water supply scheme. |  |  | BILL/00131/2024-2025 | BP-2024-25-20 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.09 | 0 | 0 | 0
62 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Road restoration of work 03 nes location (Reghunathpur Kantaberia via Molandihi, Muchipara Shibpur, Reghunathpur Kantaberna via Molandihi) |  |  | BILL/00544/2024-2025 | 275/24-25 | 06/09/2024 | 06/09/2024 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 26.8 | 0 | 0 | 0
63 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum work order for Laying and pushing by adopting trenchless technology (jack pushing method) additional for distribution network for Augmentation of RCFA part-III (Zone-II) PWSS including FHTC and allied works under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000339/2024-2025 | 2779/RCD-I | 28/11/2024 | 27/05/2025 | MAK CONSTRUCTION CO | 35.16 | 0 | 0 | 68
64 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum work order for Additional work for Jemua Water Supply Scheme at Gopalpur within Durgapur Faridpur Block for Augmentation of RCFA Part-III (Zone-II) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000019/2024-2025 | 1522/RCD-I | 14/06/2024 | 02/04/2025 | ASHA CONSTRUCTION | 22.23 | 0 | 0 | 100
65 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum work order for Supplying laying HDPE distribution pipe line at JhanjraPurbapara at Durgapur Faridpur Block under Augmentation of RCFA Part-III Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer,Junior Engineer 9 | ORD/000323/2025-2026 | 1509/RCD-I | 20/05/2025 | 01/08/2025 | DAWN CONSTRUCTION | 23.41 | 0 | 0 | 40
66 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 8A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000292/2022-2023 | 1695/DWSD | 09/12/2022 | 30/10/2025 | RUBY CONSTRUCTION | 51.35 | 33.7 | 65.62 | 70
67 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From Ext. OHR Ramnagar )(Part - 3 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000275/2022-2023 | 1688/DWSD | 09/12/2022 | 01/08/2025 | MAK CONSTRUCTION CO. | 75.68 | 62.05 | 81.98 | 100
68 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Supply, delivery and installation of Electro-Mechanical equipments in existing Ramnagar Pump House in the basis of "Augmentation of Ramnagar Head works Site under R.C.F.A.-III(Zone-II)" Water Supply Scheme under Asansol Mechnical Division,P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-5 | ORD/000412/2022-2023 | 361/AMD | 09/02/2023 | 30/04/2025 | SUNRISE ENGINEERING CORPORATION | 65.77 | 51.13 | 77.74 | 100
69 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Additional work supplying and laying of alternative rute for extra rising main of 250 mm dia DI (K9) and 200 mm dia HDPE pipe line with necessary allied works from Ramnagar H/W site to Mohal OHR under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000215/2023-2024 | 1449/DWSD | 25/08/2023 | 25/06/2024 | RANJIB GHATAK | 67.61 | 0 | 0 | 100
70 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | Augmentation | Acceptance cum work order for Detailed study of Households/Habitations of Barabani, Faridpur-Durgapur, Jamuria, Kanksa, Ondal, Pandabeswar, Raniganj and Salanpur blocks under Paschim Barddhaman District under the jurisdiction of RCFA Division-I, PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/001073/2023-2024 | 803/RCD-I | 13/03/2024 | 15/04/2030 | HORIZEN | 67.79 | 0 | 0 | 80
Total | [13 empty] | 2427.4 | 1189.41 | 49