## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of Construction of boundary wall at Akandara Pump house site TW No-2 site under Jemua piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000515/2022-2023 | 332/DWSD | 20/02/2023 | 22/03/2023 | DARPAN DAS & CO. | 15.05 | 8.45 | 56.17 | 100
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of providing FHTC connection and connection providing to Jemua Mouza (JL-80) under Jemua piped W/S Scheme under DWSD,PHE Dte (SM/06274) (Part-A) |  |  | ORD/000068/2023-2024 | 1065/DWSD | 12/07/2023 | 06/08/2023 | B.M. SARKAR | 9.67 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of providing FHTC connection and connection providing to Jemua Mouza (JL-80) under Jemua piped W/S Scheme under DWSD,PHE Dte (SM/06274)(Part-C) |  |  | ORD/000071/2023-2024 | 1058/DWSD | 12/07/2023 | 06/08/2023 | B.M. SARKAR | 9.82 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of Sinking of 2 Nos 300X200 mm dia TW 210 mtr deep by DR rig method using UPVC pipe CD and UPVC deep well screen (RDS) at Jemua H/W site and 1 No TW site of Faridpur block of retrofitting of Jemua piped W/s Scheme under DWSD ,PHE Dte (SL-19) |  |  | ORD/000025/2023-2024 | 757/DWSD | 19/05/2023 | 08/06/2023 | M/S BADAL GHOSH | 31.47 | 22.07 | 70.14 | 100
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of additional work for providing FHTC in connection with JJM for Nachan Mouza(JL-47) under Retrofitting of Jemua piped W/s Scheme under DWSD,PHE Dte (SM/13685) |  |  | ORD/000077/2023-2024 | 1064/DWSD | 12/07/2023 | 06/08/2023 | M/S MONDAL ENTERPRISE | 14.55 | 13.65 | 93.85 | 100
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of Jemua PWSS under Durgapur-Faridpur Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-01) |  |  | ORD/000176/2023-2024 | 914/DWSD | 22/06/2023 | 29/06/2023 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Additional repairing and replacement and restoration due to pipe line laying and pavers block and making platform including extra deapth of TW at Jamuna village and other allied works under providing water supply under Retrofitting of Jemua piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000218/2023-2024 | 1445/DWSD | 25/08/2023 | 09/09/2023 | SATYAM POWER | 3.43 | 3.43 | 100 | 100
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of providing FHTC in connection with JJM for Jemua mouza (JL-80) under Retrofitting of Jemua piped W/s Scheme of Durgapur-Faridpur Block (SM/16249) (Part-D) |  |  | ORD/000076/2023-2024 | 1071/DWSD | 12/07/2023 | 06/08/2023 | KIRON ENTERPRISE | 9.93 | 7.63 | 76.85 | 70
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of Construciton of 5.4 m X 3.60 m swtich room with plinth height (600 mm to 20000 mm ) with sanityary and water supply arrangment at Jemua tube well no -III site of retrofitting of Jemua Piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000014/2023-2024 | 678/DWSD | 03/05/2023 | 02/06/2023 | SIL ENTERPRISE | 6.92 | 6.92 | 100 | 100
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of Sinking of 2 Nos 300X200 mm dia TW 210 mtr deep by DR rig mehtod using UPVC pipe CD and UPVC deep well screen (RDS) at Jemua H/W site and 1 No TW site of Faridpur block of retrofitting of Jemua piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000016/2023-2024 | 680/DWSD | 03/05/2023 | 19/08/2024 | RANJIB GHATAK | 31.43 | 30.86 | 98.19 | 100
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of providing FHTC connection and connection providing to Jemua Mouza (JL-80) under Jemua piped W/S Scheme under DWSD,PHE Dte (SM/06274) (Part-B) |  |  | ORD/000074/2023-2024 | 1068/DWSD | 12/07/2023 | 01/08/2023 | ASHA CONSTRUCTION | 10.5 | 0 | 0 | 100
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | Retrofitting | Acceptance cum formal order for the work of Construction of 5.4 m X 3.60 m swtich room with plinth height (600 mm to 20000 mm ) with sanitary and water supply arrangement at Jemua tube well no -II site of retrofitting of Jemua Piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000017/2023-2024 | 681/DWSD | 03/05/2023 | 22/07/2025 | RANA ENTERPRISE | 6.84 | 0 | 0 | 51
Total | [13 empty] | 150.38 | 93.8 | 62.37