## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Ground Water based Mini piped W/S Scheme (Maximum 100 House hold)for Banagram Village,GP-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD ,PHE Dte (Part-E) | SM/13866 | New | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna |  |  | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 30/10/2022 | MONDAL PRECISION PVT LTD | 275.32 | 44.64 | 16.21 | 100
Total | [13 empty] | 275.32 | 44.64 | 16.21