## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15659 | Augmentation | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Garkilla-Kherobari,Gourangapur(28) mouzas of Garkilla-Kherobari piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-5) |  |  | ORD/000167/2022-2023 | 764/DWSD | 13/05/2022 | 27/06/2022 | BABA LOKENATH ENTERPRISE | 28.84 | 0 | 0 | 100
2 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15659 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Garkilla Khorobari Water Supply Scheme of Paschim Bardhaman under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000922/2022-2023 | 1222/CMD | 16/03/2023 | 15/04/2023 | SOUVIK HALDER | 10.21 | 0 | 0 | 70
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15659 | Augmentation | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Garkilla -Kherobari (JL-27),Gourangapur(JL-28) mouzas of Garkilla-Kherobari piped W/S scheme under DWSD,PHE Dte |  |  | ORD/000022/2023-2024 | 735/DWSD | 15/05/2023 | 14/07/2023 | BABA LOKENATH ENTERPRISE | 104.15 | 0 | 0 | 85
4 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15659 | Augmentation | Supply & Delivery of Pump Motor Set at TW No: 01 of Garkilla Khorobari water supply scheme under CMD, PHE, | Driller In-Charge | Junior Engineer | ORD/001166/2023-2024 | 110/DIC/BMSD(D) | 04/10/2023 | 19/10/2023 | SOUVIK HALDER | 0.52 | 0 | 0 | 100
Total | [13 empty] | 143.7 | 0 | 0