## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15663 | Augmentation | Formal order for the work of Additional work of laying of HDPE distribution pipe line 75/90 mm dia and providing FHTC at Kotalpukur (JL-30),Nimtakuri(JL-32) & Masna(JL-31) mouzas of Kotalpukur piped W/s Scheme under DWSD,PHE Dte (SL-03) |  |  | ORD/000253/2022-2023 | 1426/DWSD | 08/10/2022 | 18/10/2022 | JOY GURU ENTERPRISE | 12.21 | 3.51 | 28.74 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15663 | Augmentation | Acceptance cum formal order for the work of Route survey and preparation of DPr for Augmentation of Garkilla-Kherobari,Banagram, Kotalpur, Dhobaru piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000562/2022-2023 | 525/DWSD | 29/03/2023 | 13/04/2023 | MEASURE LAND | 9.24 | 9.24 | 100 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15663 | Augmentation | Quotation for Kotalpukur W/S Scheme , Pump House No- 01 , Panagarh CCC |  |  | BILL/00207/2022-2023 | BP-2022-23-339 | 17/03/2023 | 17/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.47 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15663 | Augmentation | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Kotalpukur,Masna,Nimtikuri mouzas of Kotalpukur piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-02) |  |  | ORD/000165/2022-2023 | 773/DWSD | 17/05/2022 | 01/07/2022 | JOY GURU ENTERPRISE | 41.01 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15663 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and internal House Wiring for Tube Well No. -01 at Kotalpukur (Nimtikuri) Water Supply Scheme under CMD, PHE Dte., Paschim-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000001/2023-2024 | 1575/CMD | 04/04/2023 | 04/05/2023 | SAIKAT ENTERPRISE | 8.99 | 8.48 | 94.32 | 100
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15663 | Augmentation | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Kotalpukur(JL-30) ,Nimtakuri(JL-30),Masna(JL-31) mouzas of Kotalpukur piped W/S scheme under DWSD,PHE Dte (SL-22) |  |  | ORD/000021/2023-2024 | 733/DWSD | 15/05/2023 | 31/10/2024 | JOY GURU ENTERPRISE | 146.29 | 94.38 | 64.51 | 100
7 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15663 | Augmentation | Supply delivery and installation of submersible pumping machinery, chlorination system and internal house wiring for tube well no-2 at augmentation of ground water based water supply scheme for Kotalpukur under Asansol Mechanical Division. PHE Dte. | Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3 | ORD/000500/2024-2025 | 2202/AMD | 27/12/2024 | 08/04/2025 | SAIKET SINHA | 5.93 | 0 | 0 | 100
Total | [13 empty] | 229.14 | 115.61 | 50.46