## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of laying and aligning of DI K9 R/M pipe line supplying DI specials valves and allied works under Command area of Kataberia piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000603/2022-2023 | 500/DWSD | 27/03/2023 | 26/04/2023 | KANJILAL & CO. | 18.3 | 0 | 0 | 60
2 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Constructions of 5.40 X 3.6 m switch room with plinth height (600 X 2000 mm ) with sanitary and water supply arrangement at Kataberia TW no -II of Kataberia piped W/s Scheme under DWSD PHE Dte |  |  | ORD/000581/2022-2023 | 495/DWSD | 24/03/2023 | 08/05/2023 | M/S MONDAL ENTERPRISE | 6.84 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Balance work for water supply arrangement for 1(One) No SLWM center at Bargoria and burning ghat at Bargoria ,Block-Durgapur-Faridpur for having no electricity with solar power connection including pipe line works and other allied works under proposed piped W/S Scheme for Kataberia under DWSD,PHE Dte |  |  | ORD/000044/2023-2024 | 770/DWSD | 22/05/2023 | 21/06/2023 | BHUMIKA ENTERPRISE | 7.46 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and allied works including FHTC and connection providing to Khatgoria mouzas JL-29 (Part-B) under command area of Kataberia piped W/s Scheme under DWSD ,PHE Dte |  | Junior Engineer_3 | ORD/000002/2023-2024 | 580/DWSD | 10/04/2023 | 20/05/2023 | SAIKAT RAY | 96.67 | 0 | 0 | 100
5 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Sinking of 2 (Two) Nos 300X200X210 m depth by Direct reverse rotary method using UPVC pipe (CD) deep well screen (RDS) at Kataberia H/W site TW No-I site of Durgapur-Faridpur Block under PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM(SM/16249) |  |  | ORD/000073/2023-2024 | 1072/DWSD | 12/07/2023 | 11/08/2023 | KIRON ENTERPRISE | 29.66 | 0 | 0 | 60
6 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Supplying installation of 4(Four) Nos Centrifugal pumping machinery of 1 Hp for providing port water for existing Stand alon at Labnapara under Kataberia piped W/s Scheme under DWSD,PHE Dte. (Sl- 01) |  |  | ORD/000133/2023-2024 | 1179/DWSD | 24/07/2023 | 08/08/2023 | GHOSH & ROY ENTERPRISE | 1 | 0 | 0 | 100
7 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Supplying installation of 4(Four) Nos Centrifugal pumping machinery of 1 Hp for providing port water for existing Stand alon at Kataberia under Kataberia piped W/s Scheme under DWSD,PHE Dte. (Sl- 02) |  |  | ORD/000134/2023-2024 | 1191/DWSD | 25/07/2023 | 09/08/2023 | GHOSH & ROY ENTERPRISE | 1 | 0 | 0 | 100
8 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Supplying installation of 4(Four) Nos Centrifugal pumping machinery of 1 Hp for providing port water for existing Stand alon at Jamgora under Kataberia piped W/s Scheme under DWSD,PHE Dte. (Sl- 03) |  |  | ORD/000135/2023-2024 | 1178/DWSD | 24/07/2023 | 08/08/2023 | GOUTAM GHOSH | 1 | 0 | 0 | 100
9 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Sinking of 1 no Tubewell for Triat Bore 150 mm. big dia. Tube wel 90 mtr deep by Direct Rotary Rig methed at Akandara for Jem Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte.(Sl-02) |  |  | ORD/000226/2023-2024 | 48-SPOT/DWSD | 03/07/2023 | 18/07/2023 | M/S BADAL GHOSH | 1 | 0 | 0 | 100
10 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Cleaning the chokage of different dia pipeline at Gourbazar area under Durgapur W/S Divn,PHE Dte (Sl- 02) |  |  | ORD/000227/2023-2024 | 1392/DWSD | 16/08/2023 | 26/08/2023 | GHOSH & ROY ENTERPRISE | 0.99 | 0 | 0 | 100
11 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | QUOTATION MONEY FOR NEW CONNECTION AT KHATGORIA |  |  | BILL/00025/2023-2024 | BP-2023-24-4 | 19/05/2023 | 19/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | QUOTATION MONEY FOR NEW CONNECTION AT KANTABERIA. |  |  | BILL/00024/2023-2024 | BP-2023-24-3 | 19/05/2023 | 19/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.3 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Supplying ,laying and aligning of Hoped distribution pipe line and allied works including FHTC tap connection and connection & providing to Khatgoria Mouzas JL-29 (Part-C) under Command area of Kataberia pipe W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000006/2023-2024 | 586/DWSD | 11/04/2023 | 26/05/2023 | TARA PRASAD SARKAR | 94.91 | 0 | 0 | 80
14 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Providing of lighting luminaries, electrical wiring of chlorine room with yard lighting arrangement of Kantaberia O.H.R. premises under Katabera W/S Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000280/2024-2025 | 1673/AMD | 04/10/2024 | 03/11/2024 | SARVATAH PROJECTS PRIVATE LIMITED | 6.28 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Construction of boundary wall at Khatgoria of Kataberia piped W/s Scheme pump house -II under DWSD ,PHE Dte |  |  | ORD/000005/2023-2024 | 585/DWSD | 11/04/2023 | 26/05/2023 | SIL ENTERPRISE | 14.8 | 0 | 0 | 100
16 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Constructions of 5.40 X 3.6 m witch room with plinth height (600 X 2000 mm ) with sanitary and water supply arrangement at Kataberia TW no -I of Kataberia piped W/s Scheme under DWSD PHE Dte |  |  | ORD/000003/2023-2024 | 581/DWSD | 10/04/2023 | 25/05/2023 | MAJI DEVELOPERS | 6.92 | 0 | 0 | 100
17 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Construction of boundary wall at Khatgoria H/W (OHR) site of land development approach road and others allied works of Kantaberia Piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000580/2022-2023 | 491/DWSD | 24/03/2023 | 08/05/2023 | GHOSH & ROY ENTERPRISE | 33.88 | 0 | 0 | 100
18 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Constructions of 5.40 X 3.6 m switch room with plinth height (600 X 2000 mm ) with sanitary and water supply arrangement at Kataberia TW no -II of Kataberia piped W/s Scheme under DWSD PHE Dte (SL-11) |  |  | ORD/000001/2023-2024 | 578/DWSD | 10/04/2023 | 25/05/2023 | M/S MANDAL ENTERPRISE | 6.84 | 0 | 0 | 100
19 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and allied works including FHTC and connection providing to Kataberia mouzas JL-50 part-A under command area of augmentation of Kantaberia & Bistupur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000606/2022-2023 | 504/A/DWSD | 28/03/2023 | 07/05/2023 | BISHAL ENTERPRISE | 78.86 | 0 | 0 | 100
20 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Service Connection Charge at Khatagoria under Katabera. |  |  | BILL/00940/2023-2024 | BP-2023-24-85 | 14/03/2024 | 14/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.75 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | New Connection at Kantabeira RBTW |  |  | BILL/00840/2024-2025 | BP-2024-25-74 | 09/12/2024 | 09/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.37 | 0 | 0 | 0
22 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Service Connection Charge at Kantaberia. |  |  | BILL/00939/2023-2024 | BP-2023-24-84 | 14/03/2024 | 14/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.28 | 0 | 0 | 0
23 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution system with construction of 150 M3 capacity 20 mtr staging height RCC OHR including pipe connection and soil investigation at Kataberia piped W/s Scheme under DWSD PHE Dte (SL-9) |  |  | ORD/000594/2022-2023 | 499/DWSD | 27/03/2023 | 01/07/2025 | M/S K.B.CONSTRUCTION | 99.75 | 0 | 0 | 55
24 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | SUPPLY & INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-05 AND OTHER ALLIED WORKS FOR T/W-01 AT KANTABERIA PIPED WATER SUPPLY SCHEME UNDER ASSANSOL MECHANICAL DIVISION, PHE DTE.,BLOCK-DURGAPUR-FARIDPUR, DIST.- PASCHIM-BARDHAMAN | Assistant Engineer-I | Junior Engineer-5 | ORD/000278/2024-2025 | 1680/AMD | 04/10/2024 | 10/03/2025 | M/S SWAPAN BANERJEE | 18.46 | 0 | 0 | 90
25 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Withdrawing and lowering of submersible pump motor set at Kantaberia T/W No-2 & 3 under Kantaberia Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000403/2025-2026 | 1993/AE-I/AMD | 15/12/2025 | 25/12/2025 | M/S SWAPAN BANERJEE | 0.89 | 0 | 0 | 100
26 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Supply, delivery & installation of Submersible Pumping Machineries, Chlorinator and other allied materials for TubeWell No-I, II under Kantaberia Piped Water Supply Scheme, Block-Faridpur-Durgapur, District-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000040/2023-2024 | 1023/AMD | 19/04/2023 | 02/04/2025 | M/S SWAPAN BANERJEE | 22.85 | 0 | 0 | 100
27 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | SUPPLY, DELIVERY AND INSTALLATIONF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-6 AT AUGMENTATION KANTABERIA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-I | Junior Engineer-5 | ORD/000359/2024-2025 | 1924/AMD | 19/11/2024 | 08/09/2025 | R.M.D. TRADING | 11.76 | 0 | 0 | 100
28 | PASCHIM BARDHAMAN | Faridpur Durgapur | RCFA Division -I | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | New | Shifting of office of the Executive Engineer, Durgapur W/s Division, PHE Dte, ADDA Administrative Building, EPIP Complex, Banskopa, Durgapur-12 to Nababhat, PHE Complex, Purba Bandhaman under Augmentation of Kataberia PWSS, Augmentation of Telipara under RCFA Division-I, PHE Dte. | Assistant Engineer 3 | Junior Engineer 15,Junior Engineer 7 | ORD/001150/2023-2024 | 3516/RCD-I | 01/12/2023 | 16/12/2023 | AMARANJALI CONSTRUCTION | 3.83 | 0 | 0 | 100
Total | [13 empty] | 584 | 0 | 0