## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte |  |  | ORD/000472/2021-2022 | 1631/DWSD | 18/11/2021 | 03/12/2021 | SHWET BARANI | 3.99 | 0 | 0 | 100
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Acceptance cum formal order for the work of modernization of the existing Gopalpur Lab for NABL accreditation of Sub-district water testing lab at Kanksa of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000363/2021-2022 | 87/DWSD | 27/01/2022 | 11/02/2022 | BASANTI TRADERS | 4.39 | 4.12 | 93.83 | 100
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Formal order for the work of Supplying & aligning of HDPE distribution pipe line and allied works including Functional House Holds Tap connectin (FHTC ) and connection providing to Jamdoba Mouza-40 and Telipara Mouza- JL-41 of Telipara block -Kanksa under TELIPARA piped W/s Scheme under DWSD, PHE Dte (SL-03) |  |  | ORD/000097/2022-2023 | 648/DWSD | 21/04/2022 | 16/05/2022 | M/S SANTANU PALIT & CO. | 127.01 | 20.48 | 16.12 | 75
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at DHOBARU mouza of Dhobaru piped W/s Scheme under DWSD, PHE Dte (Part-A ,B and C) (SL-01) |  |  | ORD/000166/2022-2023 | 774/DWSD | 17/05/2022 | 01/07/2022 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 44.99 | 2.01 | 4.46 | 100
5 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Telipara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000155/2022-2023 | 3143/CMD | 29/11/2022 | 29/12/2022 | M/S. SWAPAN BANERJEE | 9.56 | 9.22 | 96.47 | 100
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Acceptance cum formal order for the work of Balance work for supplying laying and aligning of HDPE distribution pipe line and allied works including FHTC and connection providing to JAMDOBA mouzas JL-40 and Paschim Telipara mouzas JL-41 of Augmentation of Telipara W/s Scheme under DWSD under |  |  | ORD/000604/2022-2023 | 501/DWSD | 27/03/2023 | 26/05/2023 | M/S SANTANU PALIT & CO. | 93.42 | 16.88 | 18.07 | 80
7 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Telipara Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000002/2023-2024 | 1576/CMD | 04/04/2023 | 04/05/2023 | C.M. ENTERPRISE | 9.49 | 9.26 | 97.5 | 100
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Balance work for installation of solar pumping machineries including solar pannel and other allied works for 6 Nos ICDS/AWC/School at Labnapara Bouripara,Pratabpur ICDS ,Jamgora Nichupara Bagdipara,Pratabpur Bus stands and pangar FP school ICDS and Kailashpur 52 ICDS under providng running water supply to ICDS/School ,HCF and other Public Ins of Kanksa and Durgapur-Faridpur Block under Retrofitting of Jemua Piped W/S Scheme. |  |  | ORD/000072/2023-2024 | 1059/DWSD | 12/07/2023 | 11/08/2023 | JOY GURU ENTERPRISE | 19.4 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Acceptance cum formal order for the work of Supplying aligning and laying of 150/250 mm dia MS pipe at Telipara under Augmentation of Telipara piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000273/2023-2024 | 1560/DWSD | 20/09/2023 | 30/09/2023 | M/S MONDAL ENTERPRISE | 3.55 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Formal order for the work of Balance work for supplying laying and aligning of HDPe distribution pipe line and allied works including FHTC and connection providing to Raghunathpur mouzas JL-39 and Paschim Gangarampur mouzas JL-92 of Augmentation of Telipara W/s Scheme under DWSD under DWSD ,PHE Dte (SL-15) |  |  | ORD/000019/2023-2024 | 713/DWSD | 11/05/2023 | 10/07/2023 | M/S PROCHESTA ENTERPRISE | 171.21 | 145.6 | 85.04 | 100
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Supplying aligning and laying of 150/250 mm dia MS pipe at Telipara under Augmentation of Telipara piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000231/2023-2024 | 1559/DWSD | 20/09/2023 | 30/09/2023 | M/S MONDAL ENTERPRISE | 3.55 | 1.01 | 28.5 | 100
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Acceptance cum formal order for the work of 1(One) No PWD road crossing at JAMDOBA under command area of Telipara distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Telipara piped W/s Scheme under DWSD ,PHE Dte (Part-C) |  |  | ORD/000144/2023-2024 | 1273/DWSD | 07/08/2023 | 22/08/2023 | SK. ALIM | 8.74 | 8.74 | 100 | 100
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Acceptance cum formal order for the work of Balance work for supplying laying and aligning of HDPE distribution pipeline and allied works including FHT C and connection providing to Jamdoba mouzaJLNo-40 andTelipara MouzaJL-41of Telipara W/s Scheme udner DWSD ,PHE Dte |  |  | ORD/000210/2023-2024 | 1089/DWSD. | 13/07/2023 | 27/08/2023 | MAK CONSTRUCTION CO. | 93.52 | 90.71 | 97 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Acceptance cum work order for Allied work of laying distribution system, New FHTC and re connection of FHTC at Shibpur of Augmentation of Telipara PWSS under RCFA Division-I PHE Dte. |  |  | ORD/000455/2025-2026 | 2010/RCD-I | 11/07/2025 | 10/08/2025 | M/S KALYANI ENTERPRISE | 18.97 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Acceptance cum work order for additional work of supplying ,laying and aligning of HDPE Distribution pipeline & allied works including functional household tap connection (FHTC) at Pathanpara command area for Augmentation of Ground Water Based Water Supply Scheme for Telipara under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000385/2025-2026 | 1759/RCDI | 18/06/2025 | 01/12/2025 | MAK CONSTRUCTION CO | 76.14 | 0 | 0 | 50
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | Augmentation | Acceptance cum work order for Construction of Switch Room (5.4 m x 3.6 m) at Shibpur of Augmentation of Telipara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 |  | ORD/000615/2025-2026 | 2011/RCD-I | 11/07/2025 | 09/10/2025 | MOUMITA ENTERPRISE | 6.73 | 0 | 0 | 0
Total | [13 empty] | 694.66 | 308.01 | 44.34