## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16900 | Augmentation | Supply and Installation of Submersible Pumping Machinery and Internal House Wiring for Tube Well No-02 At augmentation of Garadaha Piped Water Supply Scheme under Asansol Mechanical Division, PHE Dte, Block- Kanksa, Dist- Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000448/2024-2025 | 2115/AMD | 16/12/2024 | 15/01/2025 | V. P. CONCERN | 4.93 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16900 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Garadaha Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. |  |  | ORD/000003/2023-2024 | 1577/CMD | 04/04/2023 | 04/05/2023 | RAJIB COMPANY | 8.97 | 8.17 | 91.12 | 100
3 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16900 | Augmentation | Supply & Delivery of Pump Motor Set at TW No: 01 of Garadaha water supply scheme under CMD, PHE, Dte. | Driller In-Charge | Junior Engineer | ORD/001164/2023-2024 | 112/DIC/BMSD(D) | 04/10/2023 | 19/10/2023 | RAJIB COMPANY | 0.52 | 0.52 | 100 | 100
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16900 | Augmentation | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Garadaha mouzas of Garadaha piped W/S scheme under DWSD,PHE Dte |  |  | ORD/000023/2023-2024 | 734/DWSD | 15/05/2023 | 01/04/2025 | SHWET BARANI | 102.39 | 44.95 | 43.9 | 45
Total | [13 empty] | 116.8 | 53.64 | 45.92