## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16902 | Augmentation | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Dhobaru mouzas of Dhobaru piped W/S scheme under DWSD,PHE Dte |  |  | ORD/000104/2023-2024 | 1133/DWSD | 20/07/2023 | 19/08/2023 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 109.55 | 70.62 | 64.47 | 80
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16902 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of DHOBARU (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 02) |  |  | ORD/000183/2023-2024 | 1194/DWSD | 25/07/2023 | 01/08/2023 | CARTO | 0.78 | 0.78 | 100 | 100
3 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16902 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Dhobaru Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000004/2023-2024 | 1578/CMD | 04/04/2023 | 04/05/2023 | DUTTA ENTERPRISE | 8.97 | 8.5 | 94.81 | 100
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16902 | Augmentation | Additional quotation for effecting NSC under revised estimate for Dhobaru W/S Scheme |  |  | BILL/00746/2023-2024 | BP-2023-24-366 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.76 | 0 | 0 | 0
Total | [13 empty] | 122.06 | 79.9 | 65.46