## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16903 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Banagram Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. |  |  | ORD/000932/2022-2023 | 1309/CMD | 22/03/2023 | 21/04/2023 | K.S.P. ENTERPRISE | 9.99 | 8.45 | 84.61 | 70
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16903 | Augmentation | Balance work for construction of Pump house /Chlorine room sinking of 150 X80X120 mtr depth TW ,supplying laying of HDPE distribution pipe line and providing FHTC at Banagram mouza of Augmentation of Banagram piped W/s Scheme under DWSD,PHE Dte.(SM/16903) |  |  | ORD/000192/2023-2024 | 1606/DWSD | 21/08/2023 | 02/01/2026 | BISHAL ENTERPRISE | 47.01 | 0 | 0 | 100
3 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16903 | Augmentation | Supply & Delivery of Pump Motor Set at TW No: 01 of Banagram water supply scheme under CMD, PHE, Dte. | Driller In-Charge | Junior Engineer | ORD/001165/2023-2024 | 111/DIC/BMSD(D) | 04/10/2023 | 19/10/2023 | K.S.P. ENTERPRISE | 0.52 | 0 | 0 | 100
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16903 | Augmentation | Quotation money for new electric connection for Augmentation of ground water based water supply scheme for Banagarm part under Durgapur W/s Division, PHE Dte,Block -Kanksa,Dist-Paschim Bardhaman. |  |  | BILL/00038/2023-2024 | BP-2023-24-25 | 18/05/2023 | 18/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.87 | 0 | 0 | 0
Total | [13 empty] | 60.39 | 8.45 | 13.99