## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of SARPI PWSS under DURGAPUR-FARIDPUR Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -06) |  |  | ORD/000181/2023-2024 | 924/DWSD | 23/06/2023 | 30/06/2023 | CARTO | 0.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Acceptance cum formal order for the work of Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission for Pratabpur Mouza (JL-48) under retrofitting of Jemua Piped Water Supply Scheme under Durgapur Faridpur Block under DWSD PHE Dte.(Sl-04) |  |  | ORD/000229/2023-2024 | 1394/DWSD | 16/08/2023 | 26/08/2023 | GHOSH & ROY ENTERPRISE | 0.96 | 0 | 0 | 100
3 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1833/DWSD | 06/12/2023 | 06/12/2023 | Resource Division | 236.81 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1665/DWSD | 12/10/2023 | 12/10/2023 | Resource Division | 922.9 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Quotation Money for New Connection under Sharpi Water Supply Scheme. |  |  | BILL/00535/2023-2024 | BP-2023-24-44 | 03/11/2023 | 03/11/2023 | WEST BENGAL ENGINEERING CO. | 3.65 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Quotation Money for new connection under Sharpi Water Supply Scheme. |  |  | BILL/00534/2023-2024 | BP-2023-24-45 | 03/11/2023 | 03/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Supply,delivery & installation of Electro-Mechanical equipment and other allied works at New Bhaburia Head Works Site and Madhaiganj Boosting Station under Sharpi Piped Water Supply Scheme under Asansol Mechanical Division,P.H.E Dte. Block-Durgapur-Faridpur, District-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000178/2023-2024 | 1402/AMD | 19/07/2023 | 19/07/2024 | MACHINE SUPPLIERS SYNDICATE(P) LTD. | 338.11 | 0 | 0 | 60
8 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Supplying,laying and alingining of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman.(Part-B). |  |  | ORD/000093/2023-2024 | 1098/DWSD | 14/07/2023 | 13/08/2023 | UNITED CONSTRUCTION | 93.32 | 0 | 0 | 45
9 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Sinking of 2Nos 200 mm dia River bed tube well with collecting main with manifold in river "AJOY" at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-A) |  |  | ORD/000091/2023-2024 | 1095/DWSD | 14/07/2023 | 13/08/2023 | CHANDAN HAZRA | 18.32 | 0 | 0 | 82
10 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Supplying,laying and alingining of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman.(Part-F). |  |  | ORD/000094/2023-2024 | 1099/DWSD | 14/07/2023 | 13/08/2023 | M/S BADAL GHOSH | 99.72 | 0 | 0 | 100
11 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Supplying, laying and aligning of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-A) |  |  | ORD/000095/2023-2024 | 1100/DWSD | 14/07/2023 | 13/08/2023 | A CONSTRUCTION CO. | 98.78 | 0 | 0 | 42
12 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Madhaiganj Boosting Station under Sharpi & adjoining mouzs Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000441/2024-2025 | 2099/AMD | 12/12/2024 | 11/01/2025 | M/S SWAPAN BANERJEE | 19.61 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte |  |  | ORD/000474/2021-2022 | 180/DWSD | 11/02/2022 | 26/02/2022 | SHWET BARANI | 4.12 | 0 | 0 | 100
14 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Sinking of 3 Nos 200 mm dia River bed tube well with collecting main with manifold in river "AJOY" at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-A) |  |  | ORD/000100/2023-2024 | 1105/DWSD | 14/07/2023 | 18/08/2023 | BISHAL ENTERPRISE | 27.47 | 0 | 0 | 90
15 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Construction of 100 M3 capacity Clear Water Reservoir (CWR) at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. |  |  | ORD/000090/2023-2024 | 1094/DWSD | 14/07/2023 | 12/09/2023 | KALPANA BUILDERS | 32.52 | 0 | 0 | 100
16 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Sinking of 3 Nos 200 mm dia River bed tube well with collecting main with manifold in river "AJOY" at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-B) |  |  | ORD/000098/2023-2024 | 1103/DWSD | 14/07/2023 | 18/08/2023 | MAK CONSTRUCTION CO. | 27.48 | 0 | 0 | 100
17 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Sinking of 2Nos 200 mm dia River bed tube well with collecting main with manifold in river AJOY at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-C) |  |  | ORD/000099/2023-2024 | 1104/DWSD | 14/07/2023 | 13/08/2023 | MAITO MAA ENTERPRISE | 18.32 | 0 | 0 | 100
18 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Load Enhancement for Natundanga Zone under Sharpi PWSS |  |  | BILL/00574/2024-2025 | BP-2024-25-59 | 26/09/2024 | 26/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 21.33 | 0 | 0 | 0
19 | PASCHIM BARDHAMAN | Faridpur Durgapur | RCFA Division -I | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Restoration of damaged road surface due to the cause of earthwork in connection with placement of under ground water pipe line in stretches at Pandabeswar-Natundanga Road from Chainage 0.000 km to 2.00 Km 2.500 to 3.000 Km 5.500 to 5.800 km, 7.900 km to 8.141 km in the district of Paschim Bardhaman under Asansol Division PWD |  |  | BILL/01547/2023-2024 | 629/23-24 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 33.26 | 0 | 0 | 0
20 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Supplying, laying and aligning of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-E). |  |  | ORD/000096/2023-2024 | 1101/DWSD | 14/07/2023 | 02/05/2025 | KALPANA BUILDERS | 99.89 | 0 | 0 | 65
21 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Supplying, laying and aligning of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-G). |  |  | ORD/000097/2023-2024 | 1102/DWSD | 14/07/2023 | 31/10/2025 | HIRANMAY GHOSH | 97.54 | 0 | 0 | 80
22 | PASCHIM BARDHAMAN | Faridpur Durgapur | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Supplying,laying and alingining of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman.(Part-C). |  |  | ORD/000092/2023-2024 | 1096/DWSD | 14/07/2023 | 01/08/2025 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 93.43 | 0 | 0 | 70
23 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Supply delivery and installation of submersible pumping machinery in the newly sunk ground bored tubewell, lighting arrangement at new Bhaburia headworks site and corresponding sharpi O.H.R under RBTW water based water supply scheme for sharpi and adjoining areas under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-I | Junior Engineer-5 | ORD/000023/2025-2026 | 943/AMD | 16/05/2025 | 15/06/2025 | M/S JIT ENTERPRISE | 14.96 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN | Faridpur Durgapur | Asansol Mechanical | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | New | Providing & Installation of Centrifugal Pumping Machineries(No-04) at Amdahi Boosting Station under Augmentation of Sharpi Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000071/2025-2026 | 1110/AMD | 16/06/2025 | 16/07/2025 | WEST BENGAL ENGINEERING CO. | 32.17 | 0 | 0 | 0
Total | [13 empty] | 2340.46 | 0 | 0