## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance order for the work of Construction of of 500 M3 capacity ,20 Mtr staging height RCC Over Head Reservoir at Molandighi of Bistupur piped W/S Scheme under Durgapur W/S Division, PHE Dte .(SL-01) |  | JUNIOR ENGINEER-1 | ORD/000256/2021-2022 | 1650/DWSD | 25/11/2021 | 25/03/2022 | MRITYUNJOY MUKHERJEE AND CO | 92.97 | 18.1 | 19.47 | 100
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte |  |  | ORD/000473/2021-2022 | 1632/DWSD | 18/11/2021 | 03/12/2021 | SHWET BARANI | 3.99 | 3.99 | 100 | 100
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Continuation order for the work of Providing FHTC in connection with JJM for Gourbazar-Ichhapur W/s Scheme mouza-Patsaora(JL-53) Part-A block-Durgapur-Faridpur block, Dist.- Paschim Bardhaman under DWSD, PHE Dte |  |  | ORD/000278/2021-2022 | 1596/DWSD | 08/11/2021 | 18/11/2021 | SHWET BARANI | 4.52 | 4.46 | 98.76 | 100
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum formal order for the work of Supplying, laying & aligning of UPVC distribution pipe line (Distribution system Part-A) and allied works including functional house holds tap connection (FHTC) and connection providing to Akandara(JL No-47) ,Molandighi(JL No-48),Kandarakona (JL_51),Rakhitpur(JL-42,Chua(JL-43),Bhagaabanpur(JL-45),Hariki(JL No-50) Mouzas under command area of Aug of Bistupur piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000342/2021-2022 | 81/DWSD | 25/01/2022 | 31/03/2022 | MACHINO TECHNO | 377.99 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Formal order for the work of laying of distribution system and providing FHTC including reconnection of exiting FHTC from AC pipe line to newly laid different dia HDPE pipe line for Augmentation of Kanksa (Zone-II/Part-C) piped W/S Scheme under DWSD ,PHE Dte (SL-05) |  |  | ORD/000211/2022-2023 | 1161/DWSD | 01/08/2022 | 05/08/2022 | BRINDABAN KONAR | 216.66 | 15.54 | 7.17 | 80
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna |  |  | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 01/10/2024 | MONDAL PRECISION PVT LTD | 275.32 | 0 | 0 | 100
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte |  |  | ORD/000475/2021-2022 | 179/DWSD | 11/02/2022 | 26/02/2022 | SHWET BARANI | 3.99 | 3.99 | 100 | 100
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Formal order for the work of Supplying, laying & aligning of UPVC distribution pipe line (Distribution system Part-A) and allied works including functional house holds tap connection (FHTC) and connection providing to Akandara(JL No-47) ,Molandighi(JL No-48),Kandarakona (JL_51),Rakhitpur(JL-42,Chua(JL-43),Bhagaabanpur(JL-45),Hariki(JL No-50) Mouzas under command area of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000354/2021-2022 | 149/DWSD | 07/02/2022 | 13/04/2022 | MACHINO TECHNO | 377.24 | 133.19 | 35.31 | 100
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum formal order for the work of Construction of boundary wall at Bistupur H/W Site PH No-1 ,TW No-1 site under Augmentation Bistupur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000517/2022-2023 | 334/DWSD | 20/02/2023 | 12/03/2023 | M/S SHYAM KANTA GHOSH | 27.51 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Balance work for installation of solar pumping machineries including solar pannel and other allied works for 6 Nos ICDS/AWC/School at Labnapara Bouripara,Pratabpur ICDS ,Jamgora Nichupara Bagdipara,Pratabpur Bus stands and pangar FP school ICDS and Kailashpur 52 ICDS under providng running water supply to ICDS/School ,HCF and other Public Ins of Kanksa and Durgapur-Faridpur Block under Retrofitting of Jemua Piped W/S Scheme. |  |  | ORD/000072/2023-2024 | 1059/DWSD | 12/07/2023 | 11/08/2023 | JOY GURU ENTERPRISE | 19.4 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Additional work of supplying and laying of different dia HDPE distribution pipe line and allied works under command area of Augmentation of Bistupur piped W/S scheme under DWSD,PHE Dte (SM/08877) |  |  | ORD/000079/2023-2024 | 1079/DWSD | 12/07/2023 | 11/08/2023 | MRITYUNJOY MUKHERJEE AND CO | 9.9 | 9.75 | 98.51 | 99
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Additional work of supplying and laying of different dia HDPE distribution pipe line and allied works under command area of Augmentation of Bistupur piped W/S scheme under DWSD,PHE Dte (SM/08877) (Part-B) |  |  | ORD/000080/2023-2024 | 1078/DWSD | 12/07/2023 | 01/08/2023 | MRITYUNJOY MUKHERJEE AND CO | 9.91 | 9.86 | 99.45 | 99
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum formal order for the work of Creating a separate zone for PATHANPARA and Bagdipara of Kanksa (Zone-II/Part-C) with construction of Pump house /Chlorine room Sinking of 150 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Paragraph Mouza under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000108/2023-2024 | 1139/DWSD | 20/07/2023 | 03/09/2023 | JOY GURU ENTERPRISE | 95.5 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Additional works for supplying laying of HDPE pipe line including MS pipe lying and fabricating and other allied works at Bistupur under Augmentation of Bistupur piped W/s Scheme under DWSD,PHEDte . |  |  | ORD/000217/2023-2024 | 1453/DWSD | 25/08/2023 | 19/09/2023 | MRITYUNJOY MUKHERJEE AND CO | 18.95 | 18.93 | 99.89 | 100
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | 1(One) No PWD road crossing at Bistupur under command area of Bistupur distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Augmentation of Bistupur piped W/s Scheme under DWSD ,PHE Dte (Part-A) |  |  | ORD/000163/2023-2024 | 1294/DWSD | 07/08/2023 | 22/08/2023 | MRITYUNJOY MUKHERJEE AND CO | 10.91 | 10.91 | 100 | 100
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum formal order for the work of Sinking of 1 No tube well 250 mm X 150 mm tube well of 210 mtrs depth by Direct rotary rig method using PVC pipe and prepacked resin bonded gravel filter at Tilackchandrapur barobandh Adibasipara,Block-Kanksa under Augmentation of Bistupur piped W/s Scheme under DWD ,PHE Dte |  |  | ORD/000172/2023-2024 | 1303/DWSD | 07/08/2023 | 06/09/2023 | MONDAL PRECISION PVT LTD | 10.8 | 10.71 | 99.24 | 100
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum formal order for the work of Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Bistupur piped W/s Scheme (Part-A & B) |  |  | ORD/000153/2023-2024 | 1284/DWSD | 07/08/2023 | 22/08/2023 | AHS R INFRA PRIVATE LIMITED | 9.08 | 9.04 | 99.57 | 100
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | 1(One) No PWD road crossing at Bistupur under command area of Bistupur distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Augmentation of Bistupur piped W/s Scheme under DWSD ,PHE Dte (Part-B) |  |  | ORD/000154/2023-2024 | 1285/DWSD | 07/08/2023 | 22/08/2023 | MACHINO TECHNO | 10.92 | 10.92 | 100 | 100
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Water supply arrangement for guard shed with solar power connection to provide water supply block -Kanksa under Augmentation of Bistupur Piped W/s scheme under DWSD,PHE Dte |  |  | ORD/000162/2023-2024 | 1290/DWSD | 07/08/2023 | 27/08/2023 | SUNDAR CONSTRUCTION | 5.95 | 5.95 | 99.95 | 100
20 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Balance work of providing water supply to Molandighi Junior Grills H.S. Molandighi Adivasi para SSK Arraha library and Bistupur brahmin para ICDS for providing Water supply to school under Durgapur-Faridpur/Kanksa Block under DWSD, PHE Dte |  |  | ORD/000169/2023-2024 | 1297/DWSD | 07/08/2023 | 22/08/2023 | MUKHERJEE ENTERPRISE | 3.94 | 3.94 | 100 | 100
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Balance work for laying and alinging of DI K9 rising main pipe line supplying DI specials valves andallied works under command area of Bistupur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000089/2023-2024 | 720/DWSD | 11/05/2023 | 10/06/2023 | MAK CONSTRUCTION CO. | 21.57 | 19.05 | 88.33 | 100
22 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum formal order for the work for installation and fabrication of MS structural work and solar panel at Biharpur and Babnabera FP school under Augmentation of Bistupur piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000220/2023-2024 | 1454/DWSD | 25/08/2023 | 09/09/2023 | M/S MONDAL ENTERPRISE | 5.35 | 5.35 | 100 | 100
23 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum formal order for the work of renovation and modification of administrative office at PHE complex Nababhat (2nd Floor) in connection with Augmentation of Bistupur PWSS under DWSD,PHE Dte. |  |  | ORD/000223/2023-2024 | 1510/DWSD | 07/09/2023 | 02/10/2023 | SANDIPAN SENGUPTA | 14.99 | 13.91 | 92.77 | 80
24 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum formal order for the work of 1(One) No PWD road crossing at Bistupur under command area of Bistupur distribution main by modern trenches less technology through JACK Pushing method Note- 46 and node point 64,65 under Augmentation of Bistupur piped W/s Scheme under DWSD ,PHE Dte (Part-C) |  |  | ORD/000151/2023-2024 | 1282/DWSD | 07/08/2023 | 22/08/2023 | MRITYUNJOY MUKHERJEE AND CO | 10.92 | 10.92 | 100 | 100
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Kanksa Zone II/Part B under Augmentation of Bistupur Piped W/S Scheme. | Assistant Engineer 3 | Junior Engineer 7 | ORD/001233/2023-2024 | 1292/DWSD | 07/08/2023 | 21/09/2023 | PRAKRITI CONSTRUCTION | 6.02 | 6.02 | 100 | 100
26 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum formal order for the work of Balance work of providing FHTC in connection with JJM for Kanksa (Zone-II) Part-B for Augmentation of BISTUPUR W/S Scheme (JJM) under DWSD,PHE Dte. |  |  | ORD/000277/2023-2024 | 1563/DWSD | 20/09/2023 | 01/08/2025 | MD AAMIR KHAN | 30.61 | 0 | 0 | 100
27 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Road restoration with demand of fund for different road stretches within Bistupur under Augmentation of Bistupur piped W/s Scheme under Durgapur W/S Division, PHE Dte |  |  | BILL/00205/2023-2024 | BP-2023-24-114 | 28/07/2023 | 28/07/2023 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 28.83 | 0 | 0 | 0
28 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Formal work order for creating separate zone for Amlajora, supplying, laying of HDPE distribution pipeline and other allied works at Sarpi, Repairing of existing cement concrete road restoration and other allied works (Part- A & B), construction of 5.40 X 3.6 meter switch room including additional concreting of exition dismantled road after extension of pipeline and retrofitting of existing distribution system under RBT Sarpi PWSS, Augmentation of Gopalpur & Bistupur PWSS and Amlajora PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3,Assistant Engineer 4 | Junior Engineer,Junior Engineer 6 | ORD/001013/2023-2024 | 548/RCD-I | 20/02/2024 | 11/10/2025 | HIRANMAY GHOSH | 200.38 | 59.65 | 29.77 | 40
29 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Construction of Separate Zone at Rakshitpur with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer,Junior Engineer 7 | ORD/000293/2024-2025 | 2627/RCD-I | 14/11/2024 | 01/11/2025 | MACHINO TECHNO | 70.46 | 0 | 0 | 20
30 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Creating separate zone with pipe & additional FHTC including Water sources at Chua Adhibasipara under Augmentation of Bistupur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer,Junior Engineer 7 | ORD/000296/2024-2025 | 2639/RCD-I | 14/11/2024 | 01/11/2025 | MRITYUNJOY MUKHERJEE & CO. | 20.41 | 2.35 | 11.53 | 50
31 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Balance work of Laying distribution system within distribution network for Rangamati of Augmentation of Ground Water Based Water Supply Scheme for Bistupur under Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000044/2024-2025 | 1645/RCD-I | 04/07/2024 | 18/08/2024 | BASANTI TRADERS | 18.35 | 4.71 | 25.67 | 50
32 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Formal Work Order for Construction of 450 cum OHR, Laying, Aligning of DI (K9) Rising main (22 km) Pipe line and interconnection between rising main with OHR 2 nos House at Madhaiganj and Bhaburia H/W site and other allied works of RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC under Augmentation of Bistupur PWSS in Durgapur-Faridpur Block, Dist-Paschim Bardhaman under Durgapur W/S Division PHE Dte. | Assistant Engineer 3,Assistant Engineer 4 | Junior Engineer,Junior Engineer 15,Junior Engineer 7 | ORD/001232/2023-2024 | 126_RCD_I | 16/01/2024 | 29/04/2026 | GITA CONSTRUCTION | 305.57 | 124.71 | 40.81 | 100
33 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum Work Order for Construction Boundary Wall at Bistupur H/W Site Pump House no 1 Tube well No. 1 under Augmentation of Bistupur Water Supply Scheme under RCFA Division-I PHE Dte. |  |  | ORD/000376/2024-2025 | 3104/RCD-I | 13/12/2024 | 11/02/2025 | RANA ENTERPRISE | 15.43 | 0 | 0 | 0
34 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Construction of Separate Zone at Pathardiha with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000369/2024-2025 | 3097/RCD-I | 13/12/2024 | 22/10/2025 | T M CONCRETE CREATION PVT.LTD | 45.89 | 0 | 0 | 40
35 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Supply And Installation Of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System And Internal House Wiring For Tube Well No-4, Tube Well No-5 and Tube Well No-6 At Augmentation Of Bistupur Piped Water Supply Scheme Under Asansol Mechanical Division, PHE. Dte. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-3 | ORD/000453/2024-2025 | 2119/AMD | 16/12/2024 | 29/10/2028 | M/S SAJAHAN CHOWDHURY | 34.81 | 0 | 0 | 47
36 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum Work Order for Construction of CWR (200 cum capacity) and allied work at Madhaiganj OHR site under Augmentation of Ground Water Based Water Supply Scheme for Bistupur under RCFA Division-I PHE Dte | Assistant Engineer 3 | Junior Engineer | ORD/000023/2024-2025 | 1538/RCD-I | 19/06/2024 | 01/04/2025 | B.T.M. CONCERN | 37.18 | 0 | 0 | 100
37 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Construction of Separate Zone at Kuldiha with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer 11 | ORD/000218/2024-2025 | 2551/RCD-I | 28/10/2024 | 25/06/2025 | TARA CONSTRUCTION | 50.54 | 0 | 0 | 25
38 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | SUPPLY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-7 (MALANDIGHI) & TUBE WELL NO-8 (RAKSHITPUR) AT AUGMENTATION OF BISTUPUR PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE., BLOCK- KANKSA, DIST- PASCHIM BARDHAMAN. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-3 | ORD/000031/2025-2026 | 951/AMD | 16/05/2025 | 15/06/2026 | M/S SAJAHAN CHOWDHURY | 23.47 | 0 | 0 | 16
39 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Construction of Separate Zone at Keshabpur with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000632/2024-2025 | 318/RCD-I | 12/02/2025 | 01/11/2025 | MRITYUNJOY MUKHERJEE & CO. | 22.9 | 0 | 0 | 80
40 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Additional work of Supplying, laying and aligning of HDPE distribution pipe line / rising main & allied works at Bistupur Head Works Site and Saraswatingunj command area of Bistupr PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000246/2025-2026 | 1468/RCD-I | 15/05/2025 | 01/11/2025 | MRITYUNJOY MUKHERJEE & CO. | 79.35 | 0 | 0 | 70
41 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Additional work of supplying laying and aligning of HDPE distribution pipe line & allied works including Function House Hold Tap Connection (FHTC) and re concoction at Ghatakdanga, Akandara and Saraswatigunj under command area of Bistupur under Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000266/2025-2026 | 1488/RCD-I | 15/05/2025 | 01/11/2025 | MACHINO TECHNO | 44.86 | 0 | 0 | 50
42 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Additional 1 no sinking of 300 x 200 mm dia& distribution pipe line with interconnection for GopalpurNamoparaAdibasipara at ChatallidangaGosaidanga, Dangapara, Dhoadanga for Augmentation of Ground Water Based Water Supply Scheme for Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer 3,Assistant Engineer 8 | Junior Engineer | ORD/000256/2025-2026 | 1478/RCD-I | 15/05/2025 | 14/07/2025 | RANJIB GHATAK | 73.79 | 0 | 0 | 0
43 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Crossing 200 mm dia MS pipes under Highway by Jack Pushing Technology at different spots pushing different dia MS pipe at Bistupur under Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000265/2025-2026 | 1487/RCD-I | 15/05/2025 | 14/07/2025 | MRITYUNJOY MUKHERJEE & CO. | 67.58 | 0 | 0 | 100
44 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Additional work for separate distribution pipe line with inter connection for Gopalpur Left including Paschim Para Bauripara General para of Gopalpur W/S Scheme for Augmentation of ground water based supply scheme for Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000330/2025-2026 | 1516/RCD-I | 20/05/2025 | 19/07/2025 | UNITED CONSTRUCTION | 70.8 | 0 | 0 | 100
45 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Additional work for laying of pipe line (Left out) with HDPE pipe including FHTC within command area of Kanksa Zone-I PWSS with reconnection of existing FHTC and other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer,Junior Engineer 7 | ORD/000705/2024-2025 | 445/RCD-I | 12/03/2025 | 11/05/2025 | MAK CONSTRUCTION CO | 78.15 | 0 | 0 | 72
46 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Separate distribution pipe with interconnection for Gopalpur Bazar (Left Side) of Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme for Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000188/2025-2026 | 1363-RCD-I | 15/05/2025 | 01/08/2025 | DAWN CONSTRUCTION | 40.06 | 0 | 0 | 100
47 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Separate distribution pipe with interconnection for Gopalpur (Right Side) including Paschimpara, Bauripara, Generalparaof Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme of Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000329/2025-2026 | 1515/RCD-I | 20/05/2025 | 02/01/2026 | UNITED CONSTRUCTION | 38.56 | 0 | 0 | 80
48 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Acceptance cum work order for Additional work for separate distribution pipe line with inter connection for Gopalpur Right including Paschim Para Bauripara General para of Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme of Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000189/2025-2026 | 1362-RCD-I | 15/05/2025 | 14/07/2025 | UNITED CONSTRUCTION | 61.57 | 0 | 0 | 100
49 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Quotation as per WBSEDCL procedure-A(2010) on turn-key/ full deposit basis for the site of Bistupur, TW No.-07, near Malandighi. |  |  | BILL/00978/2024-2025 | BP-2024-25-81 | 12/03/2025 | 12/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.61 | 0 | 0 | 0
50 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Quotation as per wbsedcl procedure-A (2010) on turn-key/full deposit basis for the site of Bistupur, Pump house no-06, Pathardiha, near Essar oil plant. |  |  | BILL/00905/2024-2025 | BP-2024-25-76 | 21/01/2025 | 21/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.18 | 0 | 0 | 0
51 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Quotation as per WBSEDCL procedure-A (2010) on Turn-key / Full deposit basis for the site of Bistupur, Pump House No.-05, Kuldiha, Near Dangapara ICDS. |  |  | BILL/00906/2024-2025 | BP-2024-25-77 | 21/01/2025 | 21/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0 | 0
52 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | Augmentation | Quotation as per WBSEDCL Procedure-A (2010) on Turn-Key/ Full deposit basis for the site of Bistupur, TW No.-04, Chua, Rakhitpur, near Primary School. |  |  | BILL/00979/2024-2025 | BP-2024-25-80 | 12/03/2025 | 12/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.38 | 0 | 0 | 0
Total | [13 empty] | 3119.36 | 515.97 | 16.54