## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 (Hat tola) & TUBE WELL NO-4 (H/W Site) AT AUGMENTATION OF BIRUDIHA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-3 | ORD/000326/2024-2025 | 1819/AMD | 29/10/2024 | 28/11/2024 | SUNRISE ENGINEERING CORPORATION | 22.13 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | Acceptance cum Work Order for Balance work of distribution pipe line of Kanska Zone-II (Part-B)from OHR to Pathanpara under Augmentation of Birudiha W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer 7 | ORD/001178/2023-2024 | 1019/RCD-I | 16/03/2024 | 30/04/2024 | MD AAMIR KHAN | 35.4 | 0 | 0 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 134/RCD-I | 18/01/2024 | 18/01/2024 | Resource Division | 130.63 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | Quotation payment as per WBSEDCL Procedure-A (2010) for Pump House No 5, under Augmentation of Birudiha Water Supply Scheme, Block- Kanksa, Paschim Bardhaman. |  |  | BILL/00836/2024-2025 | BP-2024-25-73 | 03/12/2024 | 03/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.76 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | Quotation payment as per WBSEDCL Procedure-A (2010) for Pump House No 3, under Augmentation of Birudiha Water Supply Scheme, Block- Kanksa, Paschim Bardhaman. |  |  | BILL/00835/2024-2025 | BP-2024-25-72 | 03/12/2024 | 03/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.94 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | Augmentation | Acceptance cum formal order for the work of creating a separate zone for BIRUDIHA of Birudiha piped W/S Scheme with construction of Pump house /Chlorine room Sin king of 1500 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Birudiha, Manikara Mouza under Augmentation of BIRUDIHA piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000109/2023-2024 | 1136/DWSD | 20/07/2023 | 01/07/2025 | M/S K.B.CONSTRUCTION | 98.43 | 0 | 0 | 100
Total | [13 empty] | 292.27 | 0 | 0