## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18825 | Augmentation | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 AT AUGMENTATION OF JATGORIA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer-3 | ORD/000473/2024-2025 | 2181/AMD | 26/12/2024 | 25/01/2025 | SAIKET SINHA | 11.61 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18825 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of JATGARIA (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -09) |  |  | ORD/000190/2023-2024 | 1192/DWSD | 25/07/2023 | 01/08/2023 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18825 | Augmentation | Acceptance cum Work Order for balance work for Construction of site office at Panagarh of RCFA Division-I PHE Dte. under Augmentation of Jatgoria W/S Scheme JJm Fund. | Assistant Engineer 2 |  | ORD/000911/2023-2024 | 211/RCD-I | 29/01/2024 | 29/03/2024 | BASANTI TRADERS | 32.98 | 32.76 | 99.34 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18825 | Augmentation | Acceptance cum work order for Additional works for distribution main pipe line including Road Restoration under Augmentation of Jatgoria Water Supply Scheme Distribution System of Jatgoria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Assistant Engineer 5,Junior Engineer 6 | ORD/000235/2024-2025 | 2607/RCD-I | 12/11/2024 | 10/02/2025 | SUPERSKILL | 84.46 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18825 | Augmentation | Acceptance cum work order for Construction of Guard Room at Jatgoria Head Works Site under Augmentation of Jatgoria Water Supply Distribution System of Jatgoria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Assistant Engineer 5,Junior Engineer 6 | ORD/000314/2024-2025 | 2730/RCD-I | 26/11/2024 | 24/02/2025 | IMPULSE INTERNATIONAL | 5.53 | 0 | 0 | 40
Total | [13 empty] | 135.36 | 33.54 | 24.78