## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Supplying laying and testing of HDPE pipeline and other allied works from Ajodhya village to Satkahania under Augmentation of Shyambazar piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000242/2023-2024 | 1617/DWSD | 03/10/2023 | 02/11/2023 | BASANTI TRADERS | 9.94 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of SHYAMBAZAR (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -06) |  |  | ORD/000187/2023-2024 | 1238/DWSD | 31/07/2023 | 07/08/2023 | MEASURE LAND | 0.78 | 0.39 | 50 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area Shyambazar under Augmentation Shyambazar piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-14) | Assistant Engineer 1 | Junior Engineer 15,Junior Engineer 8 | ORD/001210/2023-2024 | 795/DWSD | 12/09/2023 | 12/10/2023 | MAJI DEVELOPERS | 98.7 | 47.57 | 48.2 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Formal order for the work of Balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Shyambazar piped W/s Scheme under DWSD, PHE Dte. |  |  | ORD/000241/2023-2024 | 1527/DWSD | 13/09/2023 | 12/11/2023 | DUTTA ENTERPRISE | 208.13 | 132.73 | 63.77 | 95
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Acceptance cum work order for Allied works of Gopalpur site office including construction of pump house, premises development under Augmentation of Shyambazar water supply scheme of RCFA Division-I, PHE Dte. |  |  | ORD/000086/2024-2025 | 2111/RCD-I | 27/08/2024 | 25/11/2024 | BASANTI TRADERS | 33.72 | 0 | 0 | 0
Total | [13 empty] | 351.27 | 180.68 | 51.44