## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of SHYAMBAZAR (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -06) |  |  | ORD/000187/2023-2024 | 1238/DWSD | 31/07/2023 | 07/08/2023 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
2 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied work at Pump House No- 01 under Shymbazar Water Supply Scheme, Block-Kanksa, Dist- Paschim Bardhaman under Asansol Mechanical Division,P.H.E Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000282/2024-2025 | 1676/AMD | 04/10/2024 | 03/11/2024 | M/S JIT ENTERPRISE | 4.11 | 0 | 0 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area Shyambazar under Augmentation Shyambazar piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-14) | Assistant Engineer 1 | Junior Engineer 15,Junior Engineer 8 | ORD/001210/2023-2024 | 795/DWSD | 12/09/2023 | 12/10/2023 | MAJI DEVELOPERS | 98.7 | 95.14 | 96.39 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Acceptance cum work order for Allied works of Gopalpur site office including construction of pump house, premises development under Augmentation of Shyambazar water supply scheme of RCFA Division-I, PHE Dte. | Assistant Engineer 3 | Assistant Engineer 5,Junior Engineer 6 | ORD/000086/2024-2025 | 2111/RCD-I | 27/08/2024 | 24/02/2025 | BASANTI TRADERS | 33.72 | 4.06 | 12.03 | 65
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | Augmentation | Supply & Installation Of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System And Internal House Wiring For Tube Well No-3 At Augmentation Of Ground water based water supply scheme for Shyambazar Under Asansol Mechanical Division, Phe Dte., Block- Kanksa, Dist- Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000032/2025-2026 | 952/AMD | 16/05/2025 | 15/06/2025 | PESTCO INDIA | 11.61 | 0 | 0 | 0
Total | [13 empty] | 148.91 | 99.97 | 67.13