## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18877 | Augmentation | SUPPLY, DELIVERY AND INSTALLATIONOF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 AT AUGMENTATION OF BASUDHA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer-3 | ORD/000325/2024-2025 | 1818/AMD | 29/10/2024 | 28/11/2024 | M/S A.D.ENTERPRISE | 11.61 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18877 | Augmentation | Formal work order for sinking of 02(two) nos TW. FHTC,laying Rising main & laying distribution system(LDS) construction of boundary wall, pump house and restoration of road & and other allied works for Augmentation of ground water based W/S scheme for Basudha under RCFA Division-I, PHE Dte. Block-Kanksa, Dist- Paschim Bardhaman, | Assistant Engineer 1,Assistant Engineer 3 | Junior Engineer,Junior Engineer 15,Junior Engineer 7 | ORD/001015/2023-2024 | 559/RCD-I | 21/02/2024 | 30/06/2024 | MRITYUNJOY MUKHERJEE & CO. | 209.86 | 164.5 | 78.38 | 90
3 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18877 | Augmentation | Quotation Payment for Basudha T/W No-3, under Kanksa Block, Paschim Bardhaman as per WBSEDCL Procedure-A(2010) on Turn-Key/Full Deposit Basis. |  |  | BILL/00025/2024-2025 | BP-2024-25-6 | 24/04/2024 | 24/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.7 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18877 | Augmentation | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Basudha Pump House No-03 (OHR Site) under Augmentation of Basudha Water Supply Scheme, Block-Kanksa, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000026/2025-2026 | 946/AMD | 16/05/2025 | 15/06/2025 | CIEMENICS | 4.4 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18877 | Augmentation | Acceptance cum work order for Sinking of 4 nos 200 mm dia River bed tube wells in the river Ajoy at Bhaburia Head Work Site under Augmentation of ground water based water supply scheme for Basudha Piped Water Supply Scheme (JJM) under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer 3 | Junior Engineer,Junior Engineer 7 | ORD/000191/2024-2025 | 2443/RCD-I | 30/09/2024 | 15/03/2025 | MACHINO TECHNO | 12.11 | 3.04 | 25.13 | 100
6 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18877 | Augmentation | Supply and installation of submersible pumping machinery, voltage stabilizer, chlorination system and internal house wiring of augmentation of basudha water supply scheme p/h no-03 under Asansol Mechanical Division, PHE Dte., Dist.- Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000136/2024-2025 | 1321/AMD | 21/08/2024 | 01/01/2025 | PESTCO INDIA | 12.03 | 0 | 0 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18877 | Augmentation | Acceptance cum work order for Improvement & Overhauling of 2 nos Iron Removal Plant (pressure type), each capacity 50 cum/Hr at Basusha H/W site & at Krishnapur of Augmentation of Ground Water Based Water Supply Scheme for Basudha under RCFA W/S Division-I, PHE Dte. | Assistant Engineer 3 | Junior Engineer 7 | ORD/000251/2024-2025 | 2614/RCD-I | 13/11/2024 | 13/12/2024 | RUPALI ELECTRONICS | 12.85 | 12.78 | 99.45 | 100
Total | [13 empty] | 265.57 | 180.32 | 67.9