## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18886 | Augmentation | Acceptance cum formal order for the work of Emergency repairing and etc allied works at different places within Basudha area,Domra area ,Tilakchandrapur area ,Krikrishnapur and Roopganj area under DWSD,PHE Dte |  |  | ORD/000276/2023-2024 | 1562/A/DWSD | 20/09/2023 | 05/10/2023 | GHOSH ENTERPRISE | 3.29 | 3.28 | 99.53 | 100
2 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18886 | Augmentation | Quotation as per WBSEDCL Procedure-A (2010) ON Turn key/ Full deposit basis for the site of Trilockchandrapur Pump House no-4, Trilockchandrapur under Kanksa Block under Panagarh CCC supply office. |  |  | BILL/00076/2024-2025 | BP-2024-25-12 | 17/05/2024 | 17/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.48 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18886 | Augmentation | Quotation Payment for Trilockchandrapur T/W No-3, under Kanksa Block, Paschim Bardhaman as per WBSEDCL Procedure-A(2010) on Turn-Key/Full Deposit Basis. |  |  | BILL/00038/2024-2025 | BP-2024-25-11 | 06/05/2024 | 06/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.79 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18886 | Augmentation | Formal order for the work of Sinking of 2(Two) Nos TW,FHTC,laying Rising main and laying distribution system (LDS) ,construction of boundary wall ,Pump House and restoration of road another allied works for Augmentation of ground water based W/s Scheme for Trilakchandrapur under DWSD,Block-Kanksa,Dist-Paschim Bardhhaman |  |  | ORD/000281/2023-2024 | 1826/DWSD | 05/12/2023 | 02/12/2025 | SHWET BARANI | 243.78 | 111.4 | 45.7 | 100
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18886 | Augmentation | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND YARD LIGHTING INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 & TUBE WELL NO-4 AT AUGMENTATION OF TILAKCHANDRAPUR PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer-3 | ORD/000322/2024-2025 | 1820/AMD | 29/10/2024 | 21/02/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 26.65 | 0 | 0 | 93
Total | [13 empty] | 290.98 | 114.68 | 39.41