## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Supply and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube Well No-03 At augmentation of Krishnapur Piped Water Supply Scheme under Asansol Mechanical Division, PHE Dte, Block- Kanksa, Dist- Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000411/2024-2025 | 1982/AMD | 27/11/2024 | 27/12/2024 | M/S JIT ENTERPRISE | 11.63 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Acceptance cum Work Order for Construction of Boundary wall and allied works at Krishnapur tube well No-02 under Augmentation of Krishnapur Piped water Supply scheme under Kanksa Block under RCFA Division-I,PHE Dte | Assistant Engineer 3 | Junior Engineer 7 | ORD/001188/2023-2024 | 1007/RCD-I | 16/03/2024 | 15/04/2024 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 7.12 | 5.54 | 77.78 | 80
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Acceptance cum work order for Creating separate zone with pipe line & additional FHTC including Water sources at Sibpur Ruidaspara under Augmentation of Krishnapur Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 3 | Assistant Engineer 5,Junior Engineer 6 | ORD/000366/2024-2025 | 3066/RCD-I | 10/12/2024 | 10/03/2025 | HIRANMAY GHOSH | 26.47 | 17.27 | 65.25 | 100
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Supply Delivery and Installation Of Voltage Stabilizer, PDB Cum MCC Panel and other Allied Electrical Works For Tube Well No- I & II At Augmentation Of Krishnapur Water Supply Scheme Under Asansol Mechanical Division, PHE. Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000454/2024-2025 | 2120/AMD | 16/12/2024 | 15/01/2025 | SINHA ELECTRICALS | 14.52 | 0 | 0 | 100
Total | [13 empty] | 59.73 | 22.81 | 38.19