## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Supply and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube Well No-03 At augmentation of Krishnapur Piped Water Supply Scheme under Asansol Mechanical Division, PHE Dte, Block- Kanksa, Dist- Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000411/2024-2025 | 1982/AMD | 27/11/2024 | 27/12/2024 | M/S JIT ENTERPRISE | 11.63 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Acceptance cum Work Order for Construction of Boundary wall and allied works at Krishnapur tube well No-02 under Augmentation of Krishnapur Piped water Supply scheme under Kanksa Block under RCFA Division-I,PHE Dte | Assistant Engineer 3,Assistant Engineer 8 | Junior Engineer,Junior Engineer 7 | ORD/001188/2023-2024 | 1007/RCD-I | 16/03/2024 | 15/04/2024 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 7.12 | 5.54 | 77.78 | 80
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Acceptance cum work order for Creating separate zone with pipe line & additional FHTC including Water sources at Sibpur Ruidaspara under Augmentation of Krishnapur Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 3 | Assistant Engineer 5,Junior Engineer 6 | ORD/000366/2024-2025 | 3066/RCD-I | 10/12/2024 | 10/03/2025 | HIRANMAY GHOSH | 26.47 | 17.27 | 65.25 | 100
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Supply Delivery and Installation Of Voltage Stabilizer, PDB Cum MCC Panel and other Allied Electrical Works For Tube Well No- I & II At Augmentation Of Krishnapur Water Supply Scheme Under Asansol Mechanical Division, PHE. Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000454/2024-2025 | 2120/AMD | 16/12/2024 | 15/01/2025 | SINHA ELECTRICALS | 14.52 | 0 | 0 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Acceptance cum work order for Emergency provision of AC Photovoltaic Submersible Solar within the bore well / tube well along with 2400 watt peak capacity Solar Photovoltaic array on MS structure with the sinking of 150 mm dia tube well 150 meter deep by DR Rig method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at Jhinukguri Adibasipara under Augmentation of Krishnapur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000253/2025-2026 | 1475/RCD-I | 15/05/2025 | 14/06/2025 | MAK CONSTRUCTION CO | 16.37 | 0 | 0 | 100
6 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | Augmentation | Load Extension at Pump house No-1 and 2 under Sub Surface Water Based Water Supply Scheme, Block-kanksa, Paschim bardhaman. |  |  | BILL/01625/2025-2026 |  | 25/09/2025 | 25/09/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.35 | 0 | 0 | 0
Total | [13 empty] | 79.45 | 22.81 | 28.71