## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18888 | Augmentation | Acceptance cum formal order for the work of Creating a separate zone for PATHANPARA and Bagdipara of Kanksa (Zone-II/Part-C) with construction of Pump house /Chlorine room Sinking of 150 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Paragraph Mouza under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000108/2023-2024 | 1139/DWSD | 20/07/2023 | 03/09/2023 | JOY GURU ENTERPRISE | 95.5 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18888 | Augmentation | Repairing and replacement and installation of Water supply arrangement at Kanchanpur FP School to provide water supply to school ,Block-Kanksa,Dist-Paschim Bardhhaman under Augmentation of Kanchanpur piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000243/2023-2024 | 1619/DWSD | 03/10/2023 | 02/11/2023 | BISHAL ENTERPRISE | 2.23 | 0 | 0 | 100
3 | PASCHIM BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18888 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for tube well No. - 3 at Kanchanpur Water Supply Scheme of (Kanksa Block, Paschim-Bardhaman) | Driller In-Charge | Junior Engineer | ORD/001269/2023-2024 | 17/CMD | 03/01/2024 | 02/02/2024 | S.P. CONSTRUCTION | 12.36 | 0 | 0 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18888 | Augmentation | Acceptance cum work order for additional work of construction of IEP, drain and platform and other allied works at Kanchanpur under Augmentation of Kanchanpur Piped water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer | ORD/000395/2025-2026 | 1761/RCDI | 18/06/2025 | 18/07/2025 | RUPALI ELECTRONICS | 15.48 | 0 | 0 | 0
Total | [13 empty] | 125.57 | 0 | 0