## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Kanyapur (near Durgamandir) under Nuni Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I |  | ORD/000398/2021-2022 | 145/AMD | 11/02/2022 | 18/02/2022 | M/S SWAPAN BANERJEE | 2.46 | 2.45 | 99.52 | 0
2 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Kapatiya Village & Saroda Pally within Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I |  | ORD/000399/2021-2022 | 146/AMD | 11/02/2022 | 18/02/2022 | UNIQUE ENTERPRISE | 3.25 | 3.22 | 99.2 | 0
3 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Choto Nuni (Majhi Para) and Upadhya Para withih Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I |  | ORD/000400/2021-2022 | 147/AMD | 11/02/2022 | 18/02/2022 | ANANYA CONSTRUCTION | 3.72 | 3.7 | 99.48 | 0
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Monoharbohal Village under Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I |  | ORD/000406/2021-2022 | 153/AMD | 11/02/2022 | 18/02/2022 | PESTCO INDIA | 2.93 | 2.91 | 99.41 | 0
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Nuni village within Nuni and Adjoining Mouzas and Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I |  | ORD/000402/2021-2022 | 149/AMD | 11/02/2022 | 18/02/2022 | HINDUSTHAN CONSULTANT FIRM | 1.29 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Sen-Raliegh B. Block within Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I |  | ORD/000401/2021-2022 | 148/AMD | 11/02/2022 | 18/02/2022 | VIKING TRADERS | 1.3 | 1.29 | 99.4 | 0
7 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Nuni Namo Para within Nuni and Adjoining Mouzas and Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I |  | ORD/000403/2021-2022 | 150/AMD | 11/02/2022 | 18/02/2022 | PESTCO INDIA | 3.74 | 3.72 | 99.46 | 0
8 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Nadiha Market (Gandhinagar) under Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I |  | ORD/000404/2021-2022 | 151/AMD | 11/02/2022 | 18/02/2022 | M/S SWAPAN BANERJEE | 3.22 | 3.2 | 99.37 | 0
9 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | Augmentation | Additional work related to Providing House to House Connection from existing distribution system at Nayabasti (Gandhinagar) under Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I |  | ORD/000405/2021-2022 | 152/AMD | 11/02/2022 | 18/02/2022 | M/S JIT ENTERPRISE | 4.56 | 1.59 | 34.94 | 0
Total | [13 empty] | 26.45 | 22.08 | 83.46