## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | SM/16775 | Augmentation | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site at Pansuli under RCFA-III(Zone-I) Water Supply Scheme, Block: Faridpur-Durgapur, Dist. Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000002/2023-2024 | 873/AMD | 04/04/2023 | 04/04/2024 | INDUSTRIAL ELECTRICAL CORPORATION | 137.21 | 0 | 0 | 73
2 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | SM/16775 | Augmentation | Withdrawing and lowering of Submersible pumping machineries at RBTW No-9 & 14 with Other allied works at Pansuli Head Works Site under RCFA Part-III(Zone-I) Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000034/2024-2025 | 1036/AMD | 16/07/2024 | 15/08/2024 | CIEMENICS | 4.05 | 0 | 0 | 100
3 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | SM/16775 | Augmentation | Providing of lighting luminaries, with yard lighting arrangement of Laudoha O.H.R. premises under Improvement of RCFA Part-I W/S Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000045/2024-2025 | 1131/AMD | 30/07/2024 | 13/01/2025 | V. P. CONCERN | 3.84 | 0 | 0 | 100
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | SM/16775 | Augmentation | Supply, delivery & installation of Electro-Mechanical equipment and other allied works at Pansuli Head Works Site under improvement of RCFA Part-III(Zone-I) Water Supply Scheme, Asansol Mechanical Division, P.H.E Dte. Block-Faridpur-Durgapur, District-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000320/2024-2025 | 1814/AMD | 29/10/2024 | 02/08/2025 | SUNRISE ENGINEERING CORPORATION | 48.22 | 0 | 0 | 100
Total | [13 empty] | 193.3 | 0 | 0