## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | SM/16775 | Augmentation | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site at Pansuli under RCFA-III(Zone-I) Water Supply Scheme, Block: Faridpur-Durgapur, Dist. Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000002/2023-2024 | 873/AMD | 04/04/2023 | 04/04/2024 | INDUSTRIAL ELECTRICAL CORPORATION | 137.21 | 136.29 | 99.33 | 73
2 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | SM/16775 | Augmentation | Withdrawing and lowering of Submersible pumping machineries at RBTW No-9 & 14 with Other allied works at Pansuli Head Works Site under RCFA Part-III(Zone-I) Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000034/2024-2025 | 1036/AMD | 16/07/2024 | 15/08/2024 | CIEMENICS | 4.05 | 4 | 98.99 | 100
Total | [13 empty] | 141.25 | 140.3 | 99.32