## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. | SM/16777 | Augmentation | New Power Connection at Damalia Pumping Station. |  |  | BILL/00021/2023-2024 | BP-2023-24-12 | 19/05/2023 |  | INDIA POWER CORPN. LTD. | 24.34 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. | SM/16777 | Augmentation | Providing and Installation of Sub-Station Equipments and other accessories at Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block : Raniganj, Dist -Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000001/2023-2024 | 872/AMD | 04/04/2023 | 29/03/2024 | EASTERN INDIA SALES AND SERVICE | 166.24 | 60.62 | 36.47 | 73
3 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. | SM/16777 | Augmentation | Allied Works Corresponding to "Providing and Installation of Sub-Station Equipments and other accessories at Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block : Raniganj, Dist -Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000074/2024-2025 | 1205/AMD | 07/08/2024 | 21/09/2024 | EASTERN INDIA SALES AND SERVICE | 12.75 | 0 | 0 | 0
Total | [13 empty] | 203.34 | 60.62 | 29.81