## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. | SM/18889 | Augmentation | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head Works Site Under RCFA Part-III (Zone-II) Water Supply Scheme, Block: Pandabeswar, Dist. Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000520/2023-2024 | 8/AMD | 02/01/2024 | 02/01/2025 | R.N.S TRADING | 145.04 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. | SM/18889 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house & Substation Buliding with Yard lighting arrangement and other allied works at Mahal & ECL Pump House under RCFA Part-III(Zone-II) Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000449/2024-2025 | 2116/AMD | 16/12/2024 | 15/01/2025 | SUNRISE ENGINEERING CORPORATION | 20.39 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. | SM/18889 | Augmentation | Deposition of earnest money for the proposed enhancement of the load at your premises at Dalurbandh, Pandabeswar |  |  | BILL/00024/2024-2025 | BP-2024-25-7 | 24/04/2024 | 24/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. | SM/18889 | Augmentation | Allied Works Corresponding to "Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head Works Site Under RCFA Part-III (Zone-II) Water Supply Scheme, Block: Pandabeswar, Dist. Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000524/2024-2025 | 145/AMD | 05/02/2025 | 07/03/2025 | BENGAL CONSTRUCTION | 8.18 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. | SM/18889 | Augmentation | Providing & Installation of Sub-Mersible Pumping Machineries at RBTW No-20,21,22 & 23 other allied works at Ramnagar Pump House under RCFA Part-III(Zone-II) Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000440/2024-2025 | 2098/AMD | 12/12/2024 | 22/08/2025 | SUNRISE ENGINEERING CORPORATION | 12.41 | 0 | 0 | 100
Total | [13 empty] | 186.07 | 0 | 0