## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 |  |  | Resource | Annual Maintenance Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission |  |  | Name of Work: Annual Service Contract (ASC) for The Instruments & Equipments of 217 Water Testing Laboratories located In different blocks of West Bengal Under Public Health Department, Govt. of West Bengal. |  |  | ORD/000726/2021-2022 | 1290/RS | 29/12/2021 | 29/03/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 73.64 | 27.4 | 37.2 | 0
2 |  |  | Resource | Annual Maintenance Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission |  |  | Name of Work: Annual Service Contract (ASC) for The Instruments & Equipments of 217 Water Testing Laboratories located In different blocks of West Bengal Under Public Health Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000021/2023-2024 | 1347/RS | 26/04/2023 | 27/07/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 73.64 | 72.99 | 99.12 | 100
3 |  |  | Resource | Annual Maintenance Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission |  |  | Annual Maintenance Contract (AMC) including supply of Spare Parts for On-site Mobile Analysis System (OMAS) installed in various Water Testing Laboratories of PHE Dte., Govt. of West Bengal . |  | Junior Engineer | ORD/000674/2022-2023 | 4854/RS | 29/08/2022 | 29/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 132.97 | 84.23 | 63.34 | 63
4 |  |  | Resource | Annual Maintenance Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission |  |  | Supply of Spare Parts including Calibration & regular upkeep of On-site Mobile Analysis System (OMAS) used for drinking water quality monitoring in Arsenic & Iron Removal Plants (AIRPs) related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. |  | Junior Engineer | ORD/000678/2022-2023 | 5548/RS | 14/10/2022 | 14/10/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 80.83 | 35.99 | 44.53 | 45
5 |  |  | Resource | Annual Maintenance Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission |  |  | Name of Work: Annual Service Contract (ASC) for The Instruments & Equipments of 217 Water Testing Laboratories located In different blocks of West Bengal Under Public Health Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000053/2023-2024 | 2223/RS | 11/07/2023 | 10/07/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 294.56 | 0 | 0 | 50
Total | [13 empty] | 655.64 | 220.61 | 33.65