## List of schemes approved in SlS
List of schemes approved in SlSSC (Rs. in Lakh)
District - HOOGHLY
SL No | District | Division | Block | SlSSC No. | Scheme Type | Scheme | Scheme SM Code | TSM code | Parent SM code | Scheme IMIS Code | No. of Villages | Total Households | FHTCs approved | Corrected FHTCs | Estimated Cost | Modified Cost | AAFS Status | AAFS Date | AAFS No. | Scheme coverage type | AAFS code | Current Status | Current Position | Tender Status | Tender Cost | WO Status | WO Cost | SlSSC Date
1 | HOOGHLY | Hooghly Division | Pandua | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme | SM/06991 | TSM/006273 | SM/00620 | 8136271 | 5 | 2079 | 1287 | 1287 | 83.37 | 83.37 | Yes | 11/11/2020 | GO2021002518PH | MVS |  | Administrative Approval Issued | N/A | Yes | 77.28 | Yes | 77.28 | 25/09/2020
2 | HOOGHLY | Hooghly Division | Serampur Uttarpara | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | TSM/007125 | SM/05819 | 7597918 | 2 | 843 | 745 | 745 | 48.29 | 48.29 | Yes | 21/01/2021 | GO2021004973PH | MVS |  | Administrative Approval Issued | N/A | Yes | 60.53 | Yes | 60.53 | 08/01/2021
3 | HOOGHLY | Hooghly Division | Tarakeswar | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | TSM/007136 | SM/02554 | 8197040 | 8 | 3696 | 3727 | 3727 | 203.01 | 203.01 | Yes | 21/01/2021 | GO2021004980PH | MVS |  | Administrative Approval Issued | N/A | Yes | 181.94 | Yes | 181.94 | 08/01/2021
4 | HOOGHLY | Hooghly Division | Haripal | 2nd (2020-2021) | Retrofitting | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | SM/06765 | TSM/005642 | SM/04710 | 8136209 | 3 | 1497 | 1089 | 1089 | 89.54 | 89.54 | Yes | 18/09/2020 | GO2021001274PH | MVS |  | Administrative Approval Issued | N/A | Yes | 9.13 | Yes | 75 | 28/08/2020
5 | HOOGHLY | Hooghly Division | Jangipara | 2nd (2020-2021) | Retrofitting | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | SM/06766 | TSM/005639 | SM/04218 | 8136198 | 14 | 3720 | 1236 | 3814 | 93.4 | 93.4 | Yes | 18/09/2020 | GO2021001275PH | MVS |  | Administrative Approval Issued | N/A | Yes | 21.01 | Yes | 157.17 | 28/08/2020
6 | HOOGHLY | Hooghly Division | Pursura | 6th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAOTA WATER SUPPLY SCHEME. | SM/08737 | TSM/007385 | SM/06279 | 7940569 | 6 | 3601 | 2836 | 2836 | 163.87 | 163.87 | Yes | 09/09/2021 | GO2122003172PH | MVS |  | Administrative Approval Issued | N/A | Yes | 74.89 | Yes | 74.89 | 10/02/2021
7 | HOOGHLY | Hooghly Division | Pursura | 6th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | SM/08738 | TSM/007386 | SM/06267 | 7940555 | 1 | 2663 | 2305 | 2305 | 134.58 | 134.58 | Yes | 09/09/2021 | GO2122003172PH | SVS |  | Administrative Approval Issued | N/A | Yes | 26.15 | Yes | 125.13 | 10/02/2021
8 | HOOGHLY | Hooghly Division | Arambag | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. | SM/09068 | TSM/008204 | SM/06272 | 7940560 | 6 | 1808 | 1287 | 1287 | 80.21 | 80.21 | Yes | 28/10/2021 | GO2122004569PH | MVS | TPH212243392M003 | Administrative Approval Issued | N/A | Yes | 31.19 | Yes | 31.19 | 19/08/2021
9 | HOOGHLY | Hooghly Division | Pandua | 7th (2021-2022) | Retrofitting | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area Rameswarpur Water Supply Scheme of Pandua Block Under Hooghly Division, P.H.E Dte | SM/10132 | TSM/009779 | SM/04051 | 40004906 | 5 | 2699 | 2111 | 2111 | 126.17 | 126.17 | Yes | 08/02/2022 | GO2122009348PH | MVS | PH212248596S000 | Administrative Approval Issued | N/A | Yes | 84.89 | Yes | 84.89 | 16/12/2021
10 | HOOGHLY | Hooghly Division | Goghat - I | 10th(2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11003 | TSM/010356 | SM/05383 | 7355467 | 3 | 1563 | 800 | 800 | 51.92 | 51.92 | Yes | 01/06/2022 | GO2223003717PH | MVS | PH222354630S000 | Administrative Approval Issued | N/A | Yes | 31.88 | Yes | 31.88 | 16/03/2022
11 | HOOGHLY | Hooghly Division | Khanakul - I | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | SM/12002 | TSM/010980 | SM/06356 | 7940671 | 5 | 5614 | 3383 | 3383 | 217.2 | 217.2 | Yes | 01/09/2022 | GO2223006915PH | MVS | PH222361821S000 | Administrative Approval Issued | N/A | Yes | 13.87 | Yes | 127.18 | 05/07/2022
12 | HOOGHLY | Hooghly Division | Khanakul - I | 5th (2022-2023) | Retrofitting | RETROFITTING WORKS OF GHOSHPUR PWSS FOR PROVIDING 4709 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13354 | TSM/010506 | SM/00336 | 40027946 | 3 | 4817 | 4709 | 4709 | 295.6 | 295.6 | Yes | 19/10/2022 | GO2223008937PH | MVS | PH222362256S000 | Administrative Approval Issued | N/A | Yes | 190.61 | Yes | 96.22 | 22/08/2022
13 | HOOGHLY | Hooghly Division | Pandua | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | SM/07440 | TSM/006686 | SM/04553 | 8191532 | 6 | 3874 | 3860 | 3860 | 230.1 | 230.1 | Yes | 30/12/2020 | GO2021003858PH | MVS |  | Administrative Approval Issued | N/A | Yes | 8.49 | Yes | 155.48 | 04/12/2020
14 | HOOGHLY | Hooghly Division | Dhaniakhali | 11th(2022-2023) | Retrofitting | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Hasampur Water Supply Scheme Under Dhaniakhali Block | SM/18111 | TSM/020538 | SM/06040 | 40066224 | 7 | 1595 | 160 | 160 | 20.53 | 20.53 | Yes | 27/03/2023 | GO2223017779PH | MVS | PH222375478S000 | Administrative Approval Issued | N/A | Yes | 3.46 | Yes | 90.96 | 10/03/2023
15 | HOOGHLY | Hooghly Division | Haripal | 10th(2022-2023) | Retrofitting | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | TSM/020287 | SM/00327 | 40053395 | 7 | 5360 | 1550 | 1550 | 99.14 | 99.14 | Yes | 14/03/2023 | GO2223015929PH | MVS | PH222372599S000 | Administrative Approval Issued | N/A | Yes | 151.54 | Yes | 7.38 | 28/12/2022
16 | HOOGHLY | Hooghly Division | Goghat - II | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HAZIPUR WATER SUPPLY SCHEME | SM/11998 | TSM/010984 | SM/05717 | 7573630 | 8 | 2664 | 2241 | 2241 | 140.93 | 140.93 | Yes | 01/09/2022 | GO2223006914PH | MVS | PH222361817S000 | Administrative Approval Issued | N/A | Yes | 20.37 | Yes | 20.37 | 05/07/2022
17 | HOOGHLY | Hooghly Division | Arambag | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | SM/07463 | TSM/006269 | SM/04552 | 8190797 | 3 | 2966 | 2123 | 2123 | 130.74 | 130.74 | Yes | 30/12/2020 | GO2021003869PH | MVS |  | Administrative Approval Issued | N/A | Yes | 214.25 | Yes | 214.25 | 25/09/2020
18 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | TSM/006678 | SM/05377 | 8190882 | 3 | 5818 | 5056 | 5421 | 288.46 | 288.46 | Yes | 30/12/2020 | GO2021003878PH | MVS |  | Administrative Approval Issued | N/A | Yes | 33.72 | Yes | 285.95 | 04/12/2020
19 | HOOGHLY | Hooghly Division | Pandua | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme | SM/06993 | TSM/006266 | SM/03893 | 8136260 | 4 | 2016 | 1259 | 1259 | 79.51 | 79.51 | Yes | 11/11/2020 | GO2021002515PH | MVS |  | Administrative Approval Issued | N/A | Yes | 53.03 | Yes | 53.03 | 25/09/2020
20 | HOOGHLY | Hooghly Division | Dhaniakhali | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | TSM/007130 | SM/00338 | 8196833 | 3 | 3927 | 2534 | 2534 | 99.58 | 99.58 | Yes | 21/01/2021 | GO2021004959PH | MVS |  | Administrative Approval Issued | N/A | Yes | 110.27 | Yes | 110.27 | 08/01/2021
21 | HOOGHLY | Hooghly Division | Pandua | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AYMA NABABPUR WATER SUPPLY SCHEME. | SM/07957 | TSM/007137 | SM/03056 | 8197306 | 5 | 3249 | 2936 | 2936 | 163.57 | 163.57 | Yes | 21/01/2021 | GO2021004978PH | MVS |  | Administrative Approval Issued | N/A | Yes | 47.68 | Yes | 47.68 | 08/01/2021
22 | HOOGHLY | Hooghly Division | Jangipara | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | TSM/008317 | SM/05546 | 7401863 | 5 | 2026 | 1577 | 1577 | 95.96 | 95.96 | Yes | 30/11/2021 | GO2122006246PH | MVS | TPH212243254M002 | Administrative Approval Issued | N/A | Yes | 2.34 | Yes | 111.76 | 19/08/2021
23 | HOOGHLY | Hooghly Division | Pursura | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF CHILADANGI WATER SUPPLY SCHEME | SM/12014 | TSM/011091 | SM/06258 | 7940552 | 3 | 3862 | 3119 | 3119 | 197.98 | 197.98 | Yes | 01/09/2022 | GO2223006909PH | MVS | PH222361862S000 | Administrative Approval Issued | N/A | Yes | 189.23 | Yes | 94.38 | 05/07/2022
24 | HOOGHLY | Hooghly Division | Goghat - II | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | SM/11990 | TSM/011098 | SM/00332 | 40026375 | 11 | 6088 | 5823 | 5823 | 376.63 | 376.63 | Yes | 01/09/2022 | GO2223006906PH | MVS | PH222360766S000 | Administrative Approval Issued | N/A | Yes | 255.56 | Yes | 270.22 | 05/07/2022
25 | HOOGHLY | Hooghly Division | Goghat - I | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME | SM/07541 | TSM/006699 | SM/04627 | 8197916 | 3 | 1046 | 893 | 893 | 56.68 | 56.68 | Yes | 31/12/2020 | GO2021003914PH | MVS |  | Administrative Approval Issued | N/A | Yes | 52.15 | Yes | 52.15 | 04/12/2020
26 | HOOGHLY | Hooghly Division | Haripal | 6th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | TSM/007388 | SM/06138 | 7813939 | 6 | 4245 | 4056 | 4056 | 230.84 | 230.84 | Yes | 09/09/2021 | GO2122003172PH | MVS |  | Administrative Approval Issued | N/A | Yes | 246.32 | Yes | 246.32 | 10/02/2021
27 | HOOGHLY | Hooghly Division | Arambag | 6th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. | SM/08742 | TSM/007390 | SM/06292 | 7940587 | 1 | 5171 | 3011 | 3011 | 176.84 | 176.84 | Yes | 09/09/2021 | GO2122003172PH | SVS |  | Administrative Approval Issued | N/A | Yes | 18.02 | Yes | 89.3 | 10/02/2021
28 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. | SM/07437 | TSM/006703 | SM/00621 | 8192790 | 5 | 4357 | 4968 | 4968 | 278.22 | 278.22 | Yes | 30/12/2020 | GO2021003872PH | MVS |  | Administrative Approval Issued | N/A | Yes | 14.93 | Yes | 346.95 | 04/12/2020
29 | HOOGHLY | Hooghly Division | Jangipara | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar Mouza of Borhol Zone-II Water Supply Scheme | SM/06988 | TSM/006259 | SM/04218 |  | 4 | 1061 | 1189 | 1189 | 75.19 | 75.19 | Yes | 11/11/2020 | GO2021002509PH | MVS |  | Administrative Approval Issued | N/A | Yes | 46.41 | Yes | 46.41 | 25/09/2020
30 | HOOGHLY | Hooghly Division | Chanditala - II | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | TSM/006270 | SM/04220 | 8190834 | 2 | 3112 | 3233 | 3233 | 184.15 | 184.15 | Yes | 30/12/2020 | GO2021003871PH | MVS |  | Administrative Approval Issued | N/A | Yes | 109.36 | Yes | 177.85 | 25/09/2020
31 | HOOGHLY | Hooghly Division | Arambag | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | SM/07945 | TSM/007126 | SM/05563 | 7401878 | 3 | 1500 | 1203 | 1203 | 74.37 | 74.37 | Yes | 21/01/2021 | GO2021004952PH | MVS |  | Administrative Approval Issued | N/A | Yes | 20.86 | Yes | 75.48 | 08/01/2021
32 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 2nd (2020-2021) | Retrofitting | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 502 nos Functional Household Tap Connection(FHTC) | SM/06760 | TSM/005633 | SM/03961 | 8136095 | 3 | 1109 | 502 | 1263 | 43.92 | 43.92 | Yes | 18/09/2020 | GO2021001279PH | MVS |  | Administrative Approval Issued | N/A | Yes | 13.77 | Yes | 13.77 | 28/08/2020
33 | HOOGHLY | Hooghly Division | Pandua | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. | SM/07542 | TSM/006695 | SM/04697 | 8197903 | 8 | 1979 | 1488 | 1488 | 95.57 | 95.57 | Yes | 31/12/2020 | GO2021003913PH | MVS |  | Administrative Approval Issued | N/A | Yes | 110.24 | Yes | 110.24 | 04/12/2020
34 | HOOGHLY | Hooghly Division | Khanakul - II | 6th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | TSM/007387 | SM/05706 | 7573681 | 5 | 3272 | 3446 | 2939 | 197.26 | 178.72 | Yes | 09/09/2021 | GO2122003172PH | MVS |  | Administrative Approval Issued | N/A | Yes | 180.14 | Yes | 180.14 | 10/02/2021
35 | HOOGHLY | Hooghly Division | Khanakul - II | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme | SM/06989 | TSM/006261 | SM/04471 | 6132548 | 1 | 2584 | 900 | 2215 | 57.3 | 57.3 | Yes | 11/11/2020 | GO2021002510PH | SVS |  | Administrative Approval Issued | N/A | Yes | 97.6 | Yes | 97.6 | 25/09/2020
36 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME | SM/11997 | TSM/011090 | SM/03976 | 40019990 | 4 | 3455 | 3456 | 3456 | 213.94 | 213.94 | Yes | 01/09/2022 | GO2223006899PH | MVS | PH222361815S000 | Administrative Approval Issued | N/A | Yes | 40.34 | Yes | 90.3 | 05/07/2022
37 | HOOGHLY | Hooghly Division | Haripal | 2nd (2020-2021) | Retrofitting | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) | SM/06763 | TSM/005631 | SM/05380 | 7355421 | 4 | 1741 | 1342 | 1342 | 99.47 | 99.47 | Yes | 18/09/2020 | GO2021001268PH | MVS |  | Administrative Approval Issued | N/A | Yes | 30.94 | Yes | 30.94 | 28/08/2020
38 | HOOGHLY | Hooghly Division | Dhaniakhali | 11th(2022-2023) | Retrofitting | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dighir Water Supply Scheme under Dhaniakhali Block | SM/18106 | TSM/020539 | SM/06015 | 40066214 | 2 | 825 | 170 | 170 | 21.11 | 21.11 | Yes | 27/03/2023 | GO2223017772PH | MVS | PH222375473S000 | Administrative Approval Issued | N/A | Yes | 3.77 | Yes | 1.01 | 10/03/2023
39 | HOOGHLY | Hooghly Division | Dhaniakhali | 11th(2022-2023) | Retrofitting | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Chopa Water Supply Scheme under Dhaniakhali Block | SM/18108 | TSM/020536 | SM/06012 | 40066220 | 13 | 5294 | 160 | 160 | 20.53 | 20.53 | Yes | 27/03/2023 | GO2223017785PH | MVS | PH222375475S000 | Administrative Approval Issued | N/A | Yes | 3.46 | No | N/A | 10/03/2023
40 | HOOGHLY | Hooghly Division | Dhaniakhali | 11th(2022-2023) | Retrofitting | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Gopinagar Water Supply Scheme Under Dhaniakhali Block | SM/18109 | TSM/020535 | SM/06036 | 40066215 | 4 | 2471 | 1874 | 1874 | 41.33 | 41.33 | Yes | 27/03/2023 | GO2223017776PH | MVS | PH222375476S000 | Administrative Approval Issued | N/A | Yes | 3.46 | Yes | 1.87 | 10/03/2023
41 | HOOGHLY | Hooghly Division | Haripal | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ENAYETPUR WATER SUPPLY SCHEME. | SM/07438 | TSM/006702 | SM/00354 | 8192740 | 5 | 1532 | 4951 | 2082 | 272.67 | 167.75 | Yes | 30/12/2020 | GO2021003877PH | MVS |  | Administrative Approval Issued | N/A | Yes | 75.02 | Yes | 1.16 | 04/12/2020
42 | HOOGHLY | Hooghly Division | Polba - Dadpur | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | TSM/006691 | SM/04639 | 8191612 | 5 | 2008 | 1961 | 1961 | 123.87 | 123.87 | Yes | 30/12/2020 | GO2021003865PH | MVS |  | Administrative Approval Issued | N/A | Yes | 114.85 | Yes | 114.85 | 04/12/2020
43 | HOOGHLY | Hooghly Division | Pandua | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | TSM/006693 | SM/04802 | 6687858 | 6 | 2631 | 1951 | 1951 | 115.31 | 115.31 | Yes | 30/12/2020 | GO2021003862PH | MVS |  | Administrative Approval Issued | N/A | Yes | 110.18 | Yes | 110.18 | 04/12/2020
44 | HOOGHLY | Hooghly Division | Chanditala - I | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | SM/06992 | TSM/006263 | SM/04524 | 8136239 | 1 | 1792 | 1695 | 1695 | 98.98 | 98.98 | Yes | 11/11/2020 | GO2021002513PH | SVS |  | Administrative Approval Issued | N/A | Yes | 194.92 | Yes | 194.92 | 25/09/2020
45 | HOOGHLY | Hooghly Division | Arambag | 2nd (2020-2021) | Retrofitting | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Jaysinhachak Mouza of Arandi Water Supply Scheme | SM/06759 | TSM/005638 | SM/04443 | 8136191 | 1 | 625 | 511 | 511 | 40.46 | 40.46 | Yes | 18/09/2020 | GO2021001270PH | SVS |  | Administrative Approval Issued | N/A | Yes | 24.19 | Yes | 24.19 | 28/08/2020
46 | HOOGHLY | Hooghly Division | Jangipara | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME. | SM/07946 | TSM/007127 | SM/05378 | 7350475 | 9 | 3812 | 3076 | 3076 | 97.35 | 97.35 | Yes | 21/01/2021 | GO2021004958PH | MVS |  | Administrative Approval Issued | N/A | Yes | 44.87 | Yes | 44.87 | 08/01/2021
47 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 2nd (2020-2021) | Retrofitting | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | SM/06761 | TSM/005634 | SM/03961 | 8136095 | 5 | 892 | 1065 | 1065 | 83.39 | 83.39 | Yes | 18/09/2020 | GO2021001271PH | MVS |  | Administrative Approval Issued | N/A | Yes | 60.65 | Yes | 60.65 | 28/08/2020
48 | HOOGHLY | Hooghly Division | Haripal | 2nd (2020-2021) | Retrofitting | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | TSM/005641 | SM/04710 | 8136209 | 3 | 2083 | 1190 | 1190 | 99.51 | 99.51 | Yes | 18/09/2020 | GO2021001276PH | MVS |  | Administrative Approval Issued | N/A | Yes | 38.82 | Yes | 38.82 | 28/08/2020
49 | HOOGHLY | Hooghly Division | Khanakul - I | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. | SM/07543 | TSM/006684 | SM/01119 | 8197868 | 2 | 1715 | 1348 | 1348 | 86.15 | 86.15 | Yes | 31/12/2020 | GO2021003909PH | MVS |  | Administrative Approval Issued | N/A | Yes | 74.78 | Yes | 74.78 | 04/12/2020
50 | HOOGHLY | Hooghly Division | Tarakeswar | 7th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | SM/08743 | TSM/007483 | SM/06296 | 7940653 | 5 | 3021 | 2499 | 2754 | 147.07 | 147.07 | Yes | 09/09/2021 | GO2122003172PH | MVS |  | Administrative Approval Issued | N/A | Yes | 9.23 | Yes | 103.65 | 19/02/2021
51 | HOOGHLY | Hooghly Division | Arambag | 1st (2021-2022) | Retrofitting | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | TSM/008215 | SM/05551 | 7401875 | 5 | 2068 | 1625 | 1625 | 97.91 | 97.91 | Yes | 28/10/2021 | GO2122004569PH | MVS | TPH212243392M001 | Administrative Approval Issued | N/A | Yes | 69.84 | Yes | 69.84 | 19/08/2021
52 | HOOGHLY | Hooghly Division | Polba - Dadpur | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AKNA WATER SUPPLY SCHEME. | SM/09069 | TSM/008206 | SM/04990 | 6865610 | 5 | 1179 | 1553 | 1553 | 95.2 | 95.2 | Yes | 28/10/2021 | GO2122004569PH | MVS | TPH212243392M004 | Administrative Approval Issued | N/A | Yes | 13.84 | Yes | 8.42 | 19/08/2021
53 | HOOGHLY | Hooghly Division | Polba - Dadpur | 7th (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNETION (FHTC) WITHIN THE COMMAND AREA OF DUBIR BHERI WATER SUPPLY SCHEME | SM/10131 | TSM/009864 | SM/04777 | 40004900 | 7 | 2040 | 1061 | 1061 | 83.52 | 83.52 | Yes | 08/02/2022 | GO2122009347PH | MVS | PH212248595S000 | Administrative Approval Issued | N/A | Yes | 49.01 | Yes | 54.34 | 16/12/2021
54 | HOOGHLY | Hooghly Division | Balagarh | 7th (2021-2022) | Retrofitting | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. | SM/10133 | TSM/009778 | SM/01489 | 40004896 | 5 | 2085 | 1702 | 1702 | 99.96 | 99.96 | Yes | 08/02/2022 | GO2122009342PH | MVS | PH212248597S000 | Administrative Approval Issued | N/A | Yes | 97.04 | Yes | 97.04 | 16/12/2021
55 | HOOGHLY | Hooghly Division | Dhaniakhali | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09774 | TSM/008318 | SM/05452 | 40003519 | 8 | 2998 | 2826 | 2826 | 166.04 | 166.04 | Yes | 30/11/2021 | GO2122006246PH | MVS | TPH212243254M003 | Administrative Approval Issued | N/A | Yes | 44.75 | Yes | 23.88 | 19/08/2021
56 | HOOGHLY | Hooghly Division | Chanditala - I | 10th(2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | SM/11004 | TSM/010297 | SM/05743 | 7589585 | 6 | 4148 | 4123 | 4123 | 244.08 | 244.08 | Yes | 01/06/2022 | GO2223003715PH | MVS | PH222354633S000 | Administrative Approval Issued | N/A | Yes | 291.78 | Yes | 228.54 | 16/03/2022
57 | HOOGHLY | Hooghly Division | Tarakeswar | 10th(2021-2022) | Retrofitting | RETROFITTING WORKS OF TALPUR PWSS FOR PROVIDING 1224 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11006 | TSM/010364 | SM/05558 | 7544501 | 1 | 1402 | 1224 | 1224 | 77.49 | 77.49 | Yes | 01/06/2022 | GO2223003712PH | SVS | PH222354636S000 | Administrative Approval Issued | N/A | Yes | 5.21 | Yes | 5.21 | 16/03/2022
58 | HOOGHLY | Hooghly Division | Khanakul - II | 10th(2021-2022) | Retrofitting | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11225 | TSM/010362 | SM/04989 | 6865612 | 3 | 5384 | 4588 | 4588 | 271.91 | 271.91 | Yes | 16/06/2022 | GO2223004151PH | MVS | PH222354632S000 | Administrative Approval Issued | N/A | Yes | 81 | Yes | 81 | 16/03/2022
59 | HOOGHLY | Hooghly Division | Pandua | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BELUN WATER SUPPLY SCHEME (FHTC : 735 Nos) | SM/12012 | TSM/010979 | SM/00352 | 40021236 | 1 | 862 | 735 | 735 | 47.77 | 47.77 | Yes | 01/09/2022 | GO2223006908PH | SVS | PH222361860S000 | Administrative Approval Issued | N/A | Yes | 51.06 | Yes | 51.06 | 05/07/2022
60 | HOOGHLY | Hooghly Division | Goghat - I | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME | SM/12001 | TSM/010987 | SM/06286 | 7940575 | 5 | 1715 | 1365 | 1365 | 88.46 | 88.46 | Yes | 01/09/2022 | GO2223006903PH | MVS | PH222361820S000 | Administrative Approval Issued | N/A | Yes | 7.03 | Yes | 61.25 | 05/07/2022
61 | HOOGHLY | Hooghly Division | Tarakeswar | 5th (2022-2023) | Retrofitting | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13353 | TSM/010508 | SM/00367 | 40027922 | 6 | 3683 | 2936 | 2936 | 186.31 | 186.31 | Yes | 19/10/2022 | GO2223008949PH | MVS | PH222362252S000 | Administrative Approval Issued | N/A | Yes | 206.99 | Yes | 142.82 | 22/08/2022
62 | HOOGHLY | Hooghly Division | Singur | 11th(2022-2023) | Retrofitting | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | SM/18110 | TSM/020534 | SM/05171 | 40066205 | 9 | 6497 | 1776 | 1776 | 142.51 | 142.51 | Yes | 27/03/2023 | GO2223017771PH | MVS | PH222375477S000 | Administrative Approval Issued | N/A | Yes | 118.42 | Yes | 116.44 | 10/03/2023
63 | HOOGHLY | Hooghly Division | Balagarh | 7th (2021-2022) | Retrofitting | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | SM/10135 | TSM/009771 | SM/02684 | 40004908 | 4 | 2001 | 2163 | 2163 | 137.19 | 137.19 | Yes | 08/02/2022 | GO2122009346PH | MVS | PH212248599S000 | Administrative Approval Issued | N/A | Yes | 85.21 | Yes | 85.21 | 16/12/2021
64 | HOOGHLY | Hooghly Division | Goghat - I | 2nd (2020-2021) | Retrofitting | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) | SM/06756 | TSM/005630 | SM/05383 | 7355467 | 3 | 1563 | 1286 | 1286 | 99.92 | 99.92 | Yes | 18/09/2020 | GO2021001281PH | MVS |  | Administrative Approval Issued | N/A | Yes | 97.99 | Yes | 97.99 | 28/08/2020
65 | HOOGHLY | Hooghly Division | Khanakul - II | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Right bank of Sundeswari river) Water Supply Scheme | SM/06990 | TSM/006262 | SM/04471 | 40033155 | 1 | 2584 | 1315 | 2215 | 80.57 | 80.57 | Yes | 11/11/2020 | GO2021002511PH | SVS |  | Administrative Approval Issued | N/A | Yes | 157.56 | Yes | 157.56 | 25/09/2020
66 | HOOGHLY | Hooghly Division | Arambag | 2nd (2020-2021) | Retrofitting | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme | SM/06762 | TSM/005637 | SM/04443 | 8136191 | 2 | 1293 | 1187 | 1187 | 87.72 | 87.72 | Yes | 18/09/2020 | GO2021001272PH | MVS |  | Administrative Approval Issued | N/A | Yes | 58.51 | Yes | 58.51 | 28/08/2020
67 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR CHANDANNAGAR WATER SUPPLY SCHEME. | SM/09071 | TSM/008209 | SM/05405 | 8390229 | 1 | 3306 | 800 | 800 | 50.04 | 50.04 | Yes | 28/10/2021 | GO2122004569PH | SVS | TPH212243392M006 | Administrative Approval Issued | N/A | Yes | 5.66 | Yes | 5.66 | 19/08/2021
68 | HOOGHLY | Hooghly Division | Balagarh | 7th (2021-2022) | Retrofitting | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | SM/10134 | TSM/009772 | SM/01537 | 40004892 | 4 | 1458 | 1386 | 1386 | 88.95 | 88.95 | Yes | 08/02/2022 | GO2122009358PH | MVS | PH212248598S000 | Administrative Approval Issued | N/A | Yes | 60.64 | Yes | 60.64 | 16/12/2021
69 | HOOGHLY | Hooghly Division | Pandua | 7th (2021-2022) | Retrofitting | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme | SM/10136 | TSM/009766 | SM/03685 | 40004909 | 6 | 2307 | 1694 | 1694 | 104.32 | 104.32 | Yes | 08/02/2022 | GO2122009343PH | MVS | PH212248600S000 | Administrative Approval Issued | N/A | Yes | 76.63 | Yes | 76.63 | 16/12/2021
70 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09775 | TSM/008319 | SM/06011 | 7747555 | 5 | 3447 | 4182 | 4182 | 234.97 | 234.97 | Yes | 30/11/2021 | GO2122006245PH | MVS | TPH212243254M004 | Administrative Approval Issued | N/A | Yes | 33.33 | Yes | 139.31 | 19/08/2021
71 | HOOGHLY | Hooghly Division | Polba - Dadpur | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09777 | TSM/008321 | SM/06013 | 7747635 | 8 | 2161 | 2269 | 2123 | 131.1 | 125.76 | Yes | 30/11/2021 | GO2122006245PH | MVS | TPH212243254M006 | Administrative Approval Issued | N/A | Yes | 94.74 | Yes | 94.74 | 19/08/2021
72 | HOOGHLY | Hooghly Division | Dhaniakhali | 10th(2021-2022) | Retrofitting | RETROFITTING WORKS OF BHASTARA PWSS FOR PROVIDING 2289 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11001 | TSM/010361 | SM/03953 | 40014814 | 5 | 2329 | 2289 | 2289 | 128.04 | 128.04 | Yes | 01/06/2022 | GO2223003716PH | MVS | PH222354625S000 | Administrative Approval Issued | N/A | Yes | 67.36 | Yes | 67.36 | 16/03/2022
73 | HOOGHLY | Hooghly Division | Balagarh | 10th(2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | SM/11005 | TSM/009992 | SM/00613 | 40014757 | 13 | 4649 | 4206 | 4206 | 270.62 | 270.62 | Yes | 01/06/2022 | GO2223003714PH | MVS | PH222354635S000 | Administrative Approval Issued | N/A | Yes | 230.67 | Yes | 230.67 | 16/03/2022
74 | HOOGHLY | Hooghly Division | Polba - Dadpur | 11th(2022-2023) | Retrofitting | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dantra Water Supply Scheme Under Polba Dadpur Block | SM/18107 | TSM/020540 | SM/06014 | 40066218 | 6 | 1597 | 180 | 180 | 21.7 | 21.7 | Yes | 27/03/2023 | GO2223017782PH | MVS | PH222375474S000 | Administrative Approval Issued | N/A | Yes | 11.42 | Yes | 11.42 | 10/03/2023
75 | HOOGHLY | Hooghly Division | Dhaniakhali | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. | SM/07958 | TSM/007138 | SM/03846 | 8197334 | 8 | 2470 | 2122 | 2122 | 119.68 | 119.68 | Yes | 21/01/2021 | GO2021004969PH | MVS |  | Administrative Approval Issued | N/A | Yes | 40.41 | Yes | 111.82 | 08/01/2021
76 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME. | SM/09072 | TSM/008211 | SM/03976 | 8384696 | 4 | 3455 | 650 | 3956 | 42.14 | 42.14 | Yes | 28/10/2021 | GO2122004569PH | MVS | TPH212243392M007 | Administrative Approval Issued | N/A | Yes | 18.54 | Yes | 18.54 | 19/08/2021
77 | HOOGHLY | Hooghly Division | Jangipara | 2nd (2020-2021) | Retrofitting | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS | SM/06754 | TSM/005640 | SM/04218 | 8136198 | 3 | 841 | 1236 | 1236 | 73.81 | 73.81 | Yes | 18/09/2020 | GO2021001277PH | MVS |  | Administrative Approval Issued | N/A | Yes | 41.9 | Yes | 41.9 | 28/08/2020
78 | HOOGHLY | Hooghly Division | Dhaniakhali | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | SM/07441 | TSM/006688 | SM/04267 | 8191600 | 2 | 2330 | 2048 | 2048 | 128.62 | 128.62 | Yes | 30/12/2020 | GO2021003855PH | MVS |  | Administrative Approval Issued | N/A | Yes | 155.25 | Yes | 155.25 | 04/12/2020
79 | HOOGHLY | Hooghly Division | Goghat - I | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Mathura,Shyambati,Ballabhbati,Dhulepur mouza) Water Supply Scheme | SM/07149 | TSM/006264 | SM/04496 | 8136249 | 4 | 1291 | 1107 | 1107 | 77.24 | 77.24 | Yes | 01/12/2020 | GO2021002887PH | MVS |  | Administrative Approval Issued | N/A | Yes | 65.25 | Yes | 65.25 | 25/09/2020
80 | HOOGHLY | Hooghly Division | Goghat - I | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Purba Amarpur,Jaykrishnapur mouza) Water Supply Scheme under | SM/07150 | TSM/006265 | SM/04496 | 8136249 | 2 | 999 | 803 | 803 | 56.16 | 56.16 | Yes | 01/12/2020 | GO2021002885PH | MVS |  | Administrative Approval Issued | N/A | Yes | 20.06 | Yes | 20.06 | 25/09/2020
81 | HOOGHLY | Hooghly Division | Tarakeswar | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | TSM/006272 | SM/04010 | 8190866 | 3 | 3223 | 2391 | 2391 | 145.28 | 145.28 | Yes | 30/12/2020 | GO2021003874PH | SVS |  | Administrative Approval Issued | N/A | Yes | 9.28 | Yes | 127.33 | 25/09/2020
82 | HOOGHLY | Hooghly Division | Tarakeswar | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | SM/07953 | TSM/007133 | SM/05470 | 7395830 | 8 | 2492 | 2229 | 2299 | 78.24 | 78.24 | Yes | 21/01/2021 | GO2021004977PH | MVS |  | Administrative Approval Issued | N/A | Yes | 74.38 | Yes | 74.38 | 08/01/2021
83 | HOOGHLY | Hooghly Division | Arambag | 2nd (2020-2021) | Retrofitting | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | SM/06764 | TSM/005636 | SM/04443 | 8136191 | 2 | 1185 | 976 | 976 | 70.7 | 70.7 | Yes | 18/09/2020 | GO2021001273PH | MVS |  | Administrative Approval Issued | N/A | Yes | 16.99 | Yes | 78.16 | 28/08/2020
84 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | TSM/006707 | SM/02754 | 8199346 | 4 | 2391 | 1515 | 1515 | 95.57 | 95.57 | Yes | 31/12/2020 | GO2021003916PH | MVS |  | Administrative Approval Issued | N/A | Yes | 126.87 | Yes | 126.87 | 04/12/2020
85 | HOOGHLY | Hooghly Division | Pursura | 7th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BHANGAMORA WATER SUPPLY SCHEME. | SM/08744 | TSM/007484 | SM/05939 | 7733799 | 2 | 1919 | 1245 | 1135 | 80.9 | 76.88 | Yes | 09/09/2021 | GO2122003172PH | MVS |  | Administrative Approval Issued | N/A | Yes | 40.78 | Yes | 40.78 | 19/02/2021
86 | HOOGHLY | Hooghly Division | Goghat - I | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | TSM/006681 | SM/01922 | 8197892 | 3 | 1265 | 883 | 883 | 57.39 | 57.39 | Yes | 31/12/2020 | GO2021003912PH | MVS |  | Administrative Approval Issued | N/A | Yes | 52.5 | Yes | 52.5 | 04/12/2020
87 | HOOGHLY | Hooghly Division | Balagarh | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. | SM/07955 | TSM/007135 | SM/01538 | 8197031 | 7 | 2954 | 2860 | 2860 | 166.55 | 166.55 | Yes | 21/01/2021 | GO2021004962PH | MVS |  | Administrative Approval Issued | N/A | Yes | 170.04 | Yes | 170.04 | 08/01/2021
88 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 2nd (2020-2021) | Retrofitting | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 1374 nos Functional Household Tap Connection(FHTC) | SM/06757 | TSM/005632 | SM/03961 | 8136095 | 13 | 3947 | 1374 | 3925 | 99.73 | 99.73 | Yes | 18/09/2020 | GO2021001278PH | MVS |  | Administrative Approval Issued | N/A | Yes | 32.79 | Yes | 4.98 | 28/08/2020
89 | HOOGHLY | Hooghly Division | Pandua | 5th (2022-2023) | Retrofitting | RETROFITTING WORKS OF DWARBASINI PWSS FOR PROVIDING 2150 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13355 | TSM/010499 | SM/00625 | 40027938 | 4 | 2450 | 2150 | 2150 | 139.24 | 139.24 | Yes | 19/10/2022 | GO2223008941PH | MVS | PH222362258S000 | Administrative Approval Issued | N/A | Yes | 5.8 | Yes | 5.8 | 22/08/2022
90 | HOOGHLY | Hooghly Division | Polba - Dadpur | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | TSM/008316 | SM/03980 | 40002442 | 18 | 6267 | 5794 | 5146 | 337.05 | 313.36 | Yes | 30/11/2021 | GO2122006246PH | MVS | TPH212243254M001 | Administrative Approval Issued | N/A | Yes | 69.84 | Yes | 226.89 | 19/08/2021
91 | HOOGHLY | Hooghly Division | Arambag | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | SM/07461 | TSM/006271 | SM/03903 | 8190841 | 5 | 2307 | 1814 | 1814 | 111.14 | 111.14 | Yes | 30/12/2020 | GO2021003873PH | MVS |  | Administrative Approval Issued | N/A | Yes | 11.61 | Yes | 104.21 | 25/09/2020
92 | HOOGHLY | Hooghly Division | Polba - Dadpur | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | TSM/007131 | SM/00954 | 8196987 | 4 | 2924 | 2559 | 2559 | 99.37 | 99.37 | Yes | 21/01/2021 | GO2021004961PH | MVS |  | Administrative Approval Issued | N/A | Yes | 119.98 | Yes | 119.98 | 08/01/2021
93 | HOOGHLY | Hooghly Division | Haripal | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | TSM/007134 | SM/04453 | 8197021 | 11 | 4060 | 4296 | 4296 | 247.47 | 247.47 | Yes | 21/01/2021 | GO2021004974PH | MVS |  | Administrative Approval Issued | N/A | Yes | 226.89 | Yes | 226.89 | 08/01/2021
94 | HOOGHLY | Hooghly Division | Khanakul - I | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | SM/07536 | TSM/006708 | SM/01817 | 8192815 | 3 | 1597 | 1270 | 1270 | 81.79 | 81.79 | Yes | 31/12/2020 | GO2021003921PH | MVS |  | Administrative Approval Issued | N/A | Yes | 133.12 | Yes | 133.12 | 04/12/2020
95 | HOOGHLY | Hooghly Division | Balagarh | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. | SM/07538 | TSM/006706 | SM/01536 | 8199354 | 1 | 502 | 502 | 502 | 32.62 | 32.62 | Yes | 31/12/2020 | GO2021003917PH | SVS |  | Administrative Approval Issued | N/A | Yes | 37.79 | Yes | 37.79 | 04/12/2020
96 | HOOGHLY | Hooghly Division | Polba - Dadpur | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MEGSAR WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09776 | TSM/008320 | SM/05423 | 7362766 | 5 | 2257 | 2181 | 2181 | 130.24 | 130.24 | Yes | 30/11/2021 | GO2122006245PH | MVS | TPH212243254M005 | Administrative Approval Issued | N/A | Yes | 87.34 | Yes | 87.34 | 19/08/2021
97 | HOOGHLY | Hooghly Division | Pandua | 10th(2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | SM/11002 | TSM/009990 | SM/00333 | 40014821 | 3 | 4579 | 5784 | 4068 | 371.11 | 308.36 | Yes | 01/06/2022 | GO2223003718PH | MVS | PH222354628S000 | Administrative Approval Issued | N/A | Yes | 188.48 | Yes | 637.32 | 16/03/2022
98 | HOOGHLY | Hooghly Division | Arambag | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME | SM/12015 | TSM/010985 | SM/06269 | 7940820 | 5 | 2786 | 2620 | 2620 | 163.75 | 163.75 | Yes | 01/09/2022 | GO2223006911PH | MVS | PH222361865S000 | Administrative Approval Issued | N/A | Yes | 37.07 | Yes | 156.41 | 05/07/2022
99 | HOOGHLY | Hooghly Division | Arambag | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BATANAL WATER SUPPLY SCHEME | SM/11999 | TSM/011094 | SM/06317 | 7940623 | 10 | 3554 | 3492 | 3492 | 218.68 | 218.68 | Yes | 01/09/2022 | GO2223006907PH | MVS | PH222361818S000 | Administrative Approval Issued | N/A | Yes | 31.44 | Yes | 73.68 | 05/07/2022
100 | HOOGHLY | Hooghly Division | Jangipara | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | SM/12000 | TSM/011111 | SM/05378 | 40026587 | 9 | 3812 | 2300 | 2300 | 148.75 | 148.75 | Yes | 01/09/2022 | GO2223006904PH | MVS | PH222361819S000 | Administrative Approval Issued | N/A | Yes | 134 | Yes | 134 | 05/07/2022
101 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 5th (2022-2023) | Retrofitting | RETROFITTING WORKS OF AMODGHATA PWSS FOR PROVIDING 600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13357 | TSM/010438 | SM/00608 | 40027926 | 5 | 4165 | 600 | 600 | 38.98 | 38.98 | Yes | 19/10/2022 | GO2223008944PH | MVS | PH222362267S000 | Administrative Approval Issued | N/A | Yes | 27.34 | Yes | 31.79 | 22/08/2022
102 | HOOGHLY | Hooghly Division | Polba - Dadpur | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | TSM/007139 | SM/04660 | 8197445 | 18 | 4430 | 3320 | 3320 | 212.07 | 212.07 | Yes | 21/01/2021 | GO2021004979PH | MVS |  | Administrative Approval Issued | N/A | Yes | 25.56 | Yes | 262.68 | 08/01/2021
103 | HOOGHLY | Hooghly Division | Polba - Dadpur | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PUINAN WATER SUPPLY SCHEME. | SM/07947 | TSM/007128 | SM/00326 | 8196823 | 3 | 2439 | 1386 | 2555 | 83.61 | 83.61 | Yes | 21/01/2021 | GO2021004971PH | MVS |  | Administrative Approval Issued | N/A | Yes | 57.2 | Yes | 57.2 | 08/01/2021
104 | HOOGHLY | Hooghly Division | Balagarh | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | SM/07540 | TSM/006701 | SM/01443 | 8199368 | 3 | 1373 | 1068 | 1068 | 66.84 | 66.84 | Yes | 31/12/2020 | GO2021003919PH | MVS |  | Administrative Approval Issued | N/A | Yes | 83.16 | Yes | 83.16 | 04/12/2020
105 | HOOGHLY | Hooghly Division | Balagarh | 10th(2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | TSM/009991 | SM/00353 | 40014663 | 7 | 6718 | 4065 | 5831 | 264.04 | 264.04 | Yes | 02/06/2022 | GO2223003788PH | MVS | PH222354631S000 | Administrative Approval Issued | N/A | Yes | 167.79 | Yes | 167.79 | 16/03/2022
106 | HOOGHLY | Hooghly Division | Chanditala - II | 2nd (2020-2021) | Retrofitting | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) | SM/06755 | TSM/005629 | SM/04444 | 8136162 | 1 | 1539 | 1522 | 1522 | 99.95 | 99.95 | Yes | 18/09/2020 | GO2021001280PH | SVS |  | Administrative Approval Issued | N/A | Yes | 85.08 | Yes | 85.08 | 28/08/2020
107 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 2nd (2020-2021) | Retrofitting | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Rajarambati, Talandu, Taragun Mouza of Digsui-Heora (Zone-II) PWSS | SM/06758 | TSM/005635 | SM/03961 | 8136095 | 3 | 950 | 984 | 984 | 74.68 | 74.68 | Yes | 18/09/2020 | GO2021001269PH | MVS |  | Administrative Approval Issued | N/A | Yes | 29.43 | Yes | 29.43 | 28/08/2020
108 | HOOGHLY | Hooghly Division | Khanakul - I | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | SM/07439 | TSM/006697 | SM/04571 | 8191751 | 4 | 2867 | 2472 | 2472 | 157.36 | 157.36 | Yes | 30/12/2020 | GO2021003868PH | MVS |  | Administrative Approval Issued | N/A | Yes | 184.59 | Yes | 184.59 | 04/12/2020
109 | HOOGHLY | Hooghly Division | Khanakul - II | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur (Within BepariPara, DharaPara, Doctor Para, Gowas Para, Hazra Para, Jamadar Para, Jana Para, Manna Para, Mehadi Para, Moral Para Habitatio | SM/06994 | TSM/006267 | SM/04481 | 8136263 | 1 | 2811 | 1048 | 2096 | 68.52 | 68.52 | Yes | 11/11/2020 | GO2021002516PH | SVS |  | Administrative Approval Issued | N/A | Yes | 88.7 | Yes | 88.7 | 25/09/2020
110 | HOOGHLY | Hooghly Division | Khanakul - II | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | SM/07151 | TSM/006268 | SM/04481 | 8136263 | 1 | 2811 | 1048 | 2096 | 69.81 | 69.81 | Yes | 01/12/2020 | GO2021002886PH | SVS |  | Administrative Approval Issued | N/A | Yes | 81.28 | Yes | 81.28 | 25/09/2020
111 | HOOGHLY | Hooghly Division | Haripal | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | SM/07948 | TSM/007129 | SM/00327 | 8196760 | 7 | 5360 | 4046 | 4046 | 98.47 | 98.47 | Yes | 21/01/2021 | GO2021004957PH | MVS |  | Administrative Approval Issued | N/A | Yes | 57.12 | Yes | 111 | 08/01/2021
112 | HOOGHLY | Hooghly Division | Polba - Dadpur | 5th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | SM/07951 | TSM/007132 | SM/00601 | 8196994 | 10 | 3839 | 4320 | 4320 | 99.86 | 99.86 | Yes | 21/01/2021 | GO2021004975PH | MVS |  | Administrative Approval Issued | N/A | Yes | 40.86 | Yes | 162.53 | 08/01/2021
113 | HOOGHLY | Hooghly Division | Goghat - I | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | TSM/006676 | SM/01914 | 8199398 | 3 | 1438 | 1112 | 1112 | 72.23 | 72.23 | Yes | 31/12/2020 | GO2021003920PH | MVS |  | Administrative Approval Issued | N/A | Yes | 95.11 | Yes | 95.11 | 04/12/2020
114 | HOOGHLY | Hooghly Division | Arambag | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | SM/09067 | TSM/008203 | SM/06035 | 7763276 | 9 | 3201 | 2144 | 2144 | 131.23 | 131.23 | Yes | 28/10/2021 | GO2122004569PH | MVS | TPH212243392M002 | Administrative Approval Issued | N/A | Yes | 86.6 | Yes | 86.6 | 19/08/2021
115 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 1st (2021-2022) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | TSM/008207 | SM/04002 | 8390218 | 9 | 5645 | 2500 | 3870 | 136.85 | 136.85 | Yes | 28/10/2021 | GO2122004569PH | MVS | TPH212243392M005 | Administrative Approval Issued | N/A | Yes | 45.33 | Yes | 179.33 | 19/08/2021
116 | HOOGHLY | Hooghly Division | Balagarh | 3rd (2022-2023) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SRIPUR-BALAGARH WATER SUPPLY SCHEME | SM/12013 | TSM/011088 | SM/00620 | 40019969 | 4 | 4881 | 3502 | 3502 | 199.03 | 199.03 | Yes | 01/09/2022 | GO2223006917PH | MVS | PH222361861S000 | Administrative Approval Issued | N/A | Yes | 30.15 | Yes | 30.15 | 05/07/2022
117 | HOOGHLY | Hooghly Division | Balagarh | 5th (2022-2023) | Retrofitting | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/12882 | TSM/010507 | SM/00356 | 40026588 | 9 | 9782 | 6938 | 6938 | 409.9 | 409.9 | Yes | 23/09/2022 | GO2223008138PH | MVS | PH222362246S000 | Administrative Approval Issued | N/A | Yes | 42.94 | Yes | 80 | 22/08/2022
118 | HOOGHLY | Hooghly Division | Chinsurah - Magra | 5th (2022-2023) | Retrofitting | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | TSM/010441 | SM/00667 | 40027945 | 2 | 3828 | 1600 | 1600 | 103.91 | 103.91 | Yes | 19/10/2022 | GO2223008931PH | MVS | PH222362259S000 | Administrative Approval Issued | N/A | Yes | 54.23 | Yes | 69.32 | 22/08/2022
119 | HOOGHLY | Hooghly Division | Polba - Dadpur | 6th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | TSM/007389 | SM/06020 | 7747627 | 8 | 3527 | 3700 | 3700 | 214.13 | 214.13 | Yes | 09/09/2021 | GO2122003172PH | MVS |  | Administrative Approval Issued | N/A | Yes | 62.47 | Yes | 208.72 | 10/02/2021
120 | HOOGHLY | Hooghly Division | Balagarh | 4th (2020-2021) | Retrofitting | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. | SM/07539 | TSM/006705 | SM/01595 | 8199334 | 1 | 591 | 540 | 540 | 35.08 | 35.08 | Yes | 31/12/2020 | GO2021003915PH | SVS |  | Administrative Approval Issued | N/A | Yes | 66.67 | Yes | 66.67 | 04/12/2020
121 | HOOGHLY | Hooghly Division | Jangipara | 3rd (2020-2021) | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme | SM/06987 | TSM/006249 | SM/04218 | 40015217 | 9 | 1433 | 1435 | 1435 | 92.65 | 92.65 | Yes | 11/11/2020 | GO2021002508PH | MVS |  | Administrative Approval Issued | N/A | Yes | 58.57 | Yes | 58.57 | 25/09/2020
Total | [10 empty] | 615 | 345619 | 263913 | 276419 | 15680.49 | 15461.23 | [8 empty] | 9066.86 |  | 12189.96