## List of schemes approved in SlS
List of schemes approved in SlSSC (Rs. in Lakh)
District - NADIA
SL No | District | Division | Block | SlSSC No. | Scheme Type | Scheme | Scheme SM Code | TSM code | Parent SM code | Scheme IMIS Code | No. of Villages | Total Households | FHTCs approved | Corrected FHTCs | Estimated Cost | Modified Cost | AAFS Status | AAFS Date | AAFS No. | Scheme coverage type | AAFS code | Current Status | Current Position | Tender Status | Tender Cost | WO Status | WO Cost | SlSSC Date
1 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2020-2021) | Retrofitting | Retrofitting of Taldaha water supply scheme under Krishnaganj Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07297 | TSM/006285 | SM/01505 | 8136242 | 5 | 1661 | 1193 | 1193 | 99.95 | 99.95 | Yes | 10/12/2020 | GO2021003279PH | MVS |  | Administrative Approval Issued | N/A | Yes | 30.25 | Yes | 30.25 | 25/09/2020
2 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 5th (2020-2021) | Retrofitting | Retrofitting of Bansbaria water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07936 | TSM/007115 | SM/04671 | 8207272 | 2 | 1348 | 652 | 652 | 62.86 | 62.86 | Yes | 21/01/2021 | GO2021004986PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.98 | Yes | 4.98 | 08/01/2021
3 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Maheshpur water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07937 | TSM/007121 | SM/01351 | 8207399 | 3 | 1970 | 924 | 924 | 74.87 | 74.87 | Yes | 21/01/2021 | GO2021004994PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
4 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Gongra water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07960 | TSM/007113 | SM/01354 | 8207364 | 4 | 2437 | 970 | 970 | 82.68 | 82.68 | Yes | 21/01/2021 | GO2021005006PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
5 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Tengra water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07962 | TSM/007123 | SM/01349 | 8207419 | 2 | 776 | 493 | 493 | 40.29 | 40.29 | Yes | 21/01/2021 | GO2021005003PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
6 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Kadipur water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08301 | TSM/007314 | SM/01472 | 8223818 | 6 | 2498 | 1169 | 1169 | 86.88 | 86.88 | Yes | 26/02/2021 | GO2021007578PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
7 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Helenchi Zone-I water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District, under Nadia ArsenicCivil Division-II, P.H.E. Dte | SM/08252 | TSM/007304 | SM/01875 | 8214489 | 8 | 7581 | 1232 | 1232 | 94.86 | 94.86 | Yes | 22/02/2021 | GO2021007411PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0.05 | Yes | 0.05 | 10/02/2021
8 | NADIA | Nadia Arsenic Civil Division II | Chapra | 1st (2021-2022) | Retrofitting | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | TSM/008242 | SM/01785 | 40000471 | 1 | 2295 | 5598 | 2799 | 298 | 298 | Yes | 25/11/2021 | GO2122005902PH | SVS | TPH212243032M002 | Administrative Approval Issued | N/A | Yes | 14.15 | Yes | 210.61 | 19/08/2021
9 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | TSM/009105 | SM/01788 | 40008425 | 3 | 7447 | 3798 | 3798 | 1334.99 | 1334.99 | Yes | 22/02/2022 | GO2122009915PH | MVS | PH212246699M001 | Administrative Approval Issued | N/A | Yes | 893.32 | Yes | 1037.3 | 22/11/2021
10 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Nischintapur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07939 | TSM/007122 | SM/01490 | 8207403 | 3 | 2486 | 833 | 833 | 70.53 | 70.53 | Yes | 21/01/2021 | GO2021004991PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.98 | Yes | 4.98 | 08/01/2021
11 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | TSM/009120 | SM/01870 | 40000223 | 4 | 4291 | 3052 | 3052 | 630.58 | 630.58 | Yes | 06/12/2021 | GO2122006494PH | MVS | TPH212246319M002 | Administrative Approval Issued | N/A | Yes | 404.87 | Yes | 660.75 | 22/11/2021
12 | NADIA | Nadia Arsenic Civil Division II | Hanskhali | 9th (2021-2022) | New | SANATANPUR PIPED WATER SUPPLY SCHEME | SM/10409 | TSM/008959 |  | 40012502 | 3 | 1219 | 1283 | 1283 | 636.18 | 636.18 | Yes | 08/04/2022 | GO2223000134PH | MVS | PH222352031S000 | Administrative Approval Issued | N/A | Yes | 206.88 | Yes | 674.91 | 17/02/2022
13 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Dharammpur (Part-A) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16100 | TSM/015457 |  | 40056627 | 1 | 447 | 98 | 98 | 40.41 | 40.41 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M001 | Administrative Approval Issued | N/A | Yes | 90.85 | Yes | 31.15 | 28/12/2022
14 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Shatikhali (Part-B) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16103 | TSM/015467 |  | 40056619 | 1 | 277 | 92 | 92 | 39.73 | 39.73 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M004 | Administrative Approval Issued | N/A | Yes | 88.85 | Yes | 35.67 | 28/12/2022
15 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Jaba(Part-B) village, Block- Krishnagar-I, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16108 | TSM/015524 |  | 40056666 | 1 | 247 | 91 | 91 | 39.61 | 39.61 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M009 | Administrative Approval Issued | N/A | Yes | 88.63 | Yes | 33.9 | 28/12/2022
16 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | TSM/009118 | SM/01483 | 40000224 | 3 | 1916 | 1059 | 1059 | 376.67 | 376.67 | Yes | 06/12/2021 | GO2122006493PH | MVS | TPH212246334M001 | Administrative Approval Issued | N/A | Yes | 274.4 | Yes | 276.7 | 22/11/2021
17 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Bahirgachi Zone-I water supply scheme underChapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08305 | TSM/007299 | SM/01483 | 8223806 | 5 | 3092 | 835 | 835 | 49.68 | 49.68 | Yes | 26/02/2021 | GO2021007574PH | MVS |  | Administrative Approval Issued | N/A | Yes | 8.55 | Yes | 8.55 | 10/02/2021
18 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 5th (2020-2021) | Retrofitting | Retrofitting of Damodarkhali water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07935 | TSM/007112 | SM/04572 | 8207349 | 3 | 1989 | 1005 | 1005 | 82.16 | 82.16 | Yes | 21/01/2021 | GO2021004984PH | MVS |  | Administrative Approval Issued | N/A | Yes | 121.54 | Yes | 121.54 | 08/01/2021
19 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 4th (2020-2021) | Retrofitting | Retrofitting of Sakdaha water supply scheme under Krishnaganj Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07833 | TSM/006756 | SM/01555 | 8207414 | 3 | 1271 | 946 | 946 | 79.37 | 79.37 | Yes | 14/01/2021 | GO2021004541PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.98 | Yes | 4.98 | 04/12/2020
20 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09249 | TSM/008759 | SM/01473 | 8385093 | 1 | 733 | 234 | 234 | 183.74 | 183.74 | Yes | 03/11/2021 | GO2122004885PH | SVS | TPH212244665M001 | Administrative Approval Issued | N/A | Yes | 82.6 | Yes | 129.56 | 15/09/2021
21 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | TSM/008757 | SM/01483 | 8385061 | 2 | 1176 | 671 | 671 | 201.91 | 201.91 | Yes | 03/11/2021 | GO2122004885PH | MVS | TPH212244665M002 | Administrative Approval Issued | N/A | Yes | 127.2 | Yes | 164.23 | 15/09/2021
22 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09259 | TSM/008725 | SM/01486 | 8385152 | 4 | 4514 | 2353 | 2353 | 495.94 | 495.94 | Yes | 03/11/2021 | GO2122004887PH | MVS | TPH212244695M002 | Administrative Approval Issued | N/A | Yes | 518.46 | Yes | 371.93 | 15/09/2021
23 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10093 | TSM/009109 | SM/01779 | 40006256 | 5 | 7541 | 3734 | 3734 | 1113.92 | 1113.92 | Yes | 01/02/2022 | GO2122009008PH | MVS | PH212246689M001 | Administrative Approval Issued | N/A | Yes | 845.35 | Yes | 785.81 | 22/11/2021
24 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Mahatpur water supply scheme under Chapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08251 | TSM/007305 | SM/01788 | 8347927 | 3 | 7447 | 1360 | 1360 | 98.97 | 98.97 | Yes | 22/02/2021 | GO2021007400PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
25 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 6th (2022-2023) | New | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | TSM/015027 |  | 40050032 | 1 | 2642 | 3397 | 3397 | 1157.09 | 1157.09 | Yes | 20/01/2023 | GO2223012269PH | SVS | PH222364289S000 | Administrative Approval Issued | N/A | Yes | 468.45 | Yes | 991.65 | 09/09/2022
26 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | TSM/008718 | SM/01444 | 8384692 | 2 | 1004 | 570 | 570 | 214.38 | 214.38 | Yes | 03/11/2021 | GO2122004878PH | MVS | TPH212244725M001 | Administrative Approval Issued | N/A | Yes | 306.97 | Yes | 189.7 | 15/09/2021
27 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2020-2021) | Retrofitting | Retrofitting of PATHARGHATA water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07298 | TSM/006288 | SM/01492 | 8136047 | 1 | 3038 | 921 | 921 | 77.3 | 77.3 | Yes | 10/12/2020 | GO2021003280PH | SVS |  | Administrative Approval Issued | N/A | Yes | 47.69 | Yes | 47.69 | 25/09/2020
28 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Betbaria water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07940 | TSM/007124 | SM/01692 | 8207291 | 1 | 1274 | 1043 | 1043 | 93.26 | 93.26 | Yes | 21/01/2021 | GO2021004989PH | SVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
29 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 6th (2020-2021) | Retrofitting | Retrofitting of Digri water supply scheme underKrishnagar-I Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08303 | TSM/007309 | SM/04636 | 8322496 | 5 | 2717 | 1301 | 970 | 99.45 | 99.45 | Yes | 26/02/2021 | GO2021007576PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
30 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09255 | TSM/008736 | SM/01457 | 8384684 | 1 | 2957 | 1308 | 1308 | 360.4 | 360.4 | Yes | 03/11/2021 | GO2122004877PH | SVS | TPH212244689M001 | Administrative Approval Issued | N/A | Yes | 206.85 | Yes | 259.68 | 15/09/2021
31 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09266 | TSM/008721 | SM/01692 | 8384721 | 1 | 1274 | 372 | 372 | 262.5 | 262.5 | Yes | 03/11/2021 | GO2122004889PH | SVS | TPH212244722M001 | Administrative Approval Issued | N/A | Yes | 195.93 | Yes | 255.67 | 15/09/2021
32 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | TSM/008719 | SM/01556 | 8385162 | 6 | 3071 | 1411 | 1411 | 375.24 | 375.24 | Yes | 03/11/2021 | GO2122004889PH | MVS | TPH212244722M003 | Administrative Approval Issued | N/A | Yes | 423.57 | Yes | 457.58 | 15/09/2021
33 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | TSM/009098 | SM/01875 | 40000226 | 5 | 5033 | 2653 | 2653 | 545.2 | 545.2 | Yes | 06/12/2021 | GO2122006492PH | MVS | TPH212246338M002 | Administrative Approval Issued | N/A | Yes | 269.25 | Yes | 295.69 | 22/11/2021
34 | NADIA | Nadia Arsenic Civil Division II | Santipur | 9th (2021-2022) | New | Manik Nagar Piped W/S Scheme | SM/10407 | TSM/008673 |  | 40012195 | 3 | 1623 | 1182 | 1182 | 557.44 | 557.44 | Yes | 08/04/2022 | GO2223000135PH | MVS | PH222352028S000 | Administrative Approval Issued | N/A | Yes | 238.42 | Yes | 351.86 | 17/02/2022
35 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 5th (2022-2023) | New | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | TSM/014576 |  | 40023293 | 1 | 381 | 462 | 462 | 282.35 | 282.35 | Yes | 13/09/2022 | GO2223007589PH | SVS | PH222362191S000 | Administrative Approval Issued | N/A | Yes | 198.15 | Yes | 200.43 | 22/08/2022
36 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Bahirgachi Zone-II water supply scheme underChapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08306 | TSM/007298 | SM/01483 | 8223899 | 5 | 3092 | 850 | 850 | 59.58 | 59.58 | Yes | 26/02/2021 | GO2021007573PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
37 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 5th (2020-2021) | Retrofitting | Retrofitting of Krishnagar water supply scheme under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07961 | TSM/007114 | SM/00231 | 8207394 | 1 | 1201 | 824 | 824 | 77.01 | 77.01 | Yes | 21/01/2021 | GO2021005007PH | SVS |  | Administrative Approval Issued | N/A | Yes | 3.7 | Yes | 4.97 | 08/01/2021
38 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | TSM/008756 | SM/04671 | 8385068 | 2 | 1348 | 962 | 962 | 192.64 | 192.64 | Yes | 03/11/2021 | GO2122004885PH | MVS | TPH212244665M003 | Administrative Approval Issued | N/A | Yes | 117.92 | Yes | 118.34 | 15/09/2021
39 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 6th (2020-2021) | Retrofitting | Retrofitting of Bagakhali Zone-I water supply scheme underTehatta-I Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08307 | TSM/007296 | SM/01870 | 8223792 | 4 | 4291 | 1176 | 1176 | 96.32 | 96.32 | Yes | 26/02/2021 | GO2021007597PH | MVS |  | Administrative Approval Issued | N/A | Yes | 5 | Yes | 5 | 10/02/2021
40 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Matiary water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08309 | TSM/007293 | SM/01485 | 8223874 | 2 | 2959 | 1267 | 1267 | 99.84 | 99.84 | Yes | 26/02/2021 | GO2021007595PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
41 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | TSM/008760 | SM/01875 | 8385081 | 3 | 2238 | 739 | 739 | 324.86 | 324.86 | Yes | 03/11/2021 | GO2122004890PH | MVS | TPH212244648M001 | Administrative Approval Issued | N/A | Yes | 112.09 | Yes | 279.17 | 15/09/2021
42 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09248 | TSM/008758 | SM/01875 | 8385077 | 3 | 3267 | 2269 | 2269 | 329.58 | 329.58 | Yes | 03/11/2021 | GO2122004890PH | MVS | TPH212244648M002 | Administrative Approval Issued | N/A | Yes | 391.88 | Yes | 350.95 | 15/09/2021
43 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09270 | TSM/008717 | SM/06293 | 40000524 | 5 | 2762 | 2595 | 2595 | 239.82 | 239.82 | Yes | 03/11/2021 | GO2122004878PH | MVS | PH212244725M002 | Administrative Approval Issued | N/A | Yes | 17.52 | Yes | 250.4 | 15/09/2021
44 | NADIA | Nadia Arsenic Civil Division II | Chapra | 7th (2021-2022) | New | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | TSM/009022 |  | 40002357 | 4 | 1668 | 1374 | 1374 | 679.34 | 679.34 | Yes | 02/02/2022 | GO2122009123PH | MVS | PH212248323S000 | Administrative Approval Issued | N/A | Yes | 141.9 | Yes | 474.48 | 16/12/2021
45 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 6th (2021-2022) | New | Dhopahat Piped Water Supply Scheme | SM/09942 | TSM/008625 |  | 40005663 | 4 | 2126 | 1823 | 1823 | 910.07 | 910.07 | Yes | 13/12/2021 | GO2122006701PH | MVS | PH212247248S000 | Administrative Approval Issued | N/A | Yes | 187.31 | Yes | 941.85 | 22/11/2021
46 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09872 | TSM/009113 | SM/01485 | 40000225 | 2 | 2959 | 2266 | 2266 | 656.84 | 656.84 | Yes | 06/12/2021 | GO2122006491PH | MVS | PH212246340S000 | Administrative Approval Issued | N/A | Yes | 21.73 | Yes | 580.99 | 22/11/2021
47 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2022-2023) | New | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | TSM/011888 |  | 40019249 | 2 | 2205 | 1800 | 1800 | 681.25 | 681.25 | Yes | 25/08/2022 | GO2223006707PH | MVS | PH222359403S000 | Administrative Approval Issued | N/A | Yes | 407.96 | Yes | 729.13 | 05/07/2022
48 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2022-2023) | New | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | TSM/011903 |  | 40019256 | 3 | 2201 | 2060 | 2060 | 869.42 | 869.42 | Yes | 25/08/2022 | GO2223006708PH | MVS | PH222359405S000 | Administrative Approval Issued | N/A | Yes | 568.46 | Yes | 917.77 | 05/07/2022
49 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Shatikhali (Part-A) village, Block- Tehatta-II, Nadia District, Under Nadia Arsenic Civil Division-II. | SM/16102 | TSM/015466 |  | 40056408 | 1 | 277 | 97 | 97 | 40.3 | 40.3 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M003 | Administrative Approval Issued | N/A | Yes | 90.52 | Yes | 35.56 | 28/12/2022
50 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | TSM/008727 | SM/01349 | 8384675 | 2 | 776 | 138 | 138 | 271.9 | 271.9 | Yes | 03/11/2021 | GO2122004875PH | MVS | TPH212244696M002 | Administrative Approval Issued | N/A | Yes | 615.73 | Yes | 252.84 | 15/09/2021
51 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | TSM/009114 | SM/01785 | 40006265 | 8 | 9382 | 5978 | 5978 | 2169.04 | 2169.04 | Yes | 01/02/2022 | GO2122009008PH | MVS | PH212246689M002 | Administrative Approval Issued | N/A | Yes | 1402.36 | Yes | 1807.09 | 22/11/2021
52 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2020-2021) | Retrofitting | Retrofitting of Lakshmipur water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07299 | TSM/006287 | SM/01350 | 8136227 | 3 | 2552 | 803 | 803 | 76.25 | 76.25 | Yes | 10/12/2020 | GO2021003281PH | MVS |  | Administrative Approval Issued | N/A | Yes | 44.32 | Yes | 44.32 | 25/09/2020
53 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Khanjepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07943 | TSM/007120 | SM/01473 | 8207386 | 1 | 733 | 622 | 622 | 55.53 | 55.53 | Yes | 21/01/2021 | GO2021004997PH | SVS |  | Administrative Approval Issued | N/A | Yes | 0 | No | N/A | 08/01/2021
54 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Jayghata water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08302 | TSM/007312 | SM/03107 | 8223861 | 3 | 2026 | 1038 | 1038 | 75.64 | 75.64 | Yes | 26/02/2021 | GO2021007577PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
55 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 6th (2020-2021) | Retrofitting | Retrofitting of Barnia water supply scheme underTehatta-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08304 | TSM/007308 | SM/01779 | 8223907 | 5 | 7541 | 1060 | 1060 | 84.21 | 84.21 | Yes | 26/02/2021 | GO2021007575PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0.36 | Yes | 0.36 | 10/02/2021
56 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | TSM/008761 | SM/01505 | 8385085 | 5 | 1661 | 660 | 660 | 298.02 | 298.02 | Yes | 03/11/2021 | GO2122004886PH | MVS | TPH212244456M003 | Administrative Approval Issued | N/A | Yes | 231.7 | Yes | 283.17 | 15/09/2021
57 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Brittihuda water supply scheme under Chapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08249 | TSM/007310 | SM/01785 | 8214480 | 8 | 9382 | 972 | 972 | 76.67 | 76.67 | Yes | 22/02/2021 | GO2021007405PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
58 | NADIA | Nadia Arsenic Civil Division II | Karimpur-II | 6th (2020-2021) | Retrofitting | Retrofitting of Thanapara water supply scheme under Karimpur-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08250 | TSM/007307 | SM/01456 | 8347910 | 2 | 5720 | 1331 | 1331 | 97.93 | 97.93 | Yes | 22/02/2021 | GO2021007403PH | MVS |  | Administrative Approval Issued | N/A | Yes | 133 | Yes | 133 | 10/02/2021
59 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Balibanga water supply scheme under Chapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08255 | TSM/007292 | SM/01346 | 8223918 | 5 | 3260 | 976 | 976 | 72.47 | 72.47 | Yes | 22/02/2021 | GO2021007407PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
60 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09252 | TSM/008733 | SM/03107 | 8385037 | 4 | 2291 | 1337 | 1337 | 379.36 | 379.36 | Yes | 03/11/2021 | GO2122004891PH | MVS | TPH212244682M001 | Administrative Approval Issued | N/A | Yes | 228.84 | Yes | 303.68 | 15/09/2021
61 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | TSM/008730 | SM/01555 | 8385020 | 3 | 1271 | 226 | 226 | 247.75 | 247.75 | Yes | 03/11/2021 | GO2122004891PH | MVS | TPH212244682M003 | Administrative Approval Issued | N/A | Yes | 134.03 | Yes | 219.67 | 15/09/2021
62 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09263 | TSM/008724 | SM/01464 | 8384669 | 1 | 1128 | 89 | 89 | 223.22 | 223.22 | Yes | 03/11/2021 | GO2122004873PH | SVS | TPH212244700M001 | Administrative Approval Issued | N/A | Yes | 276.38 | Yes | 196.93 | 15/09/2021
63 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 8th (2021-2022) | New | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | TSM/008886 |  | 40012068 | 2 | 1662 | 1124 | 1124 | 724.36 | 724.36 | Yes | 08/04/2022 | GO2223000133PH | MVS | PH222352024S000 | Administrative Approval Issued | N/A | Yes | 276.11 | Yes | 671.09 | 27/01/2022
64 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 1st (2021-2022) | Retrofitting | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | TSM/008241 | SM/01779 | 40000470 | 5 | 7541 | 9025 | 2718 | 273.75 | 273.75 | Yes | 25/11/2021 | GO2122005902PH | MVS | TPH212243032M001 | Administrative Approval Issued | N/A | Yes | 266.33 | Yes | 266.33 | 19/08/2021
65 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 1st (2021-2022) | Retrofitting | Retrofitting of Patharghata water supply scheme (Phase-II) under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09696 | TSM/008240 | SM/01492 | 40000473 | 1 | 3038 | 6112 | 2532 | 252.57 | 252.57 | Yes | 25/11/2021 | GO2122005903PH | SVS | TPH212245389M001 | Administrative Approval Issued | N/A | Yes | 20.66 | Yes | 239.6 | 19/08/2021
66 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09264 | TSM/008723 | SM/01480 | 8384666 | 1 | 1201 | 9 | 9 | 209.68 | 209.68 | Yes | 03/11/2021 | GO2122004873PH | SVS | TPH212244700M2 | Administrative Approval Issued | N/A | Yes | 237.06 | Yes | 190.75 | 15/09/2021
67 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09267 | TSM/008720 | SM/01492 | 8384730 | 1 | 3038 | 3580 | 3580 | 332.2 | 332.2 | Yes | 03/11/2021 | GO2122004889PH | SVS | TPH212244722M002 | Administrative Approval Issued | N/A | Yes | 1524.1 | Yes | 287.03 | 15/09/2021
68 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 9th (2021-2022) | New | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | TSM/008951 |  | 40012172 | 3 | 2126 | 1975 | 1975 | 784.94 | 784.94 | Yes | 08/04/2022 | GO2223000123PH | MVS | PH222352027S000 | Administrative Approval Issued | N/A | Yes | 177.74 | Yes | 827.09 | 17/02/2022
69 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 9th (2021-2022) | New | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | TSM/008998 |  | 40012086 | 2 | 913 | 797 | 797 | 484.54 | 484.54 | Yes | 08/04/2022 | GO2223000137PH | MVS | PH222352033S000 | Administrative Approval Issued | N/A | Yes | 152.21 | Yes | 453.59 | 17/02/2022
70 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | TSM/008732 | SM/01551 | 8385007 | 3 | 1286 | 266 | 266 | 250.56 | 250.56 | Yes | 03/11/2021 | GO2122004877PH | MVS | TPH212244689M003 | Administrative Approval Issued | N/A | Yes | 346.94 | Yes | 211.26 | 15/09/2021
71 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Bagbaria water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07938 | TSM/007117 | SM/01551 | 8207263 | 3 | 1286 | 984 | 984 | 83.76 | 83.76 | Yes | 21/01/2021 | GO2021004998PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
72 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09253 | TSM/008731 | SM/01346 | 8385011 | 5 | 3260 | 1322 | 1322 | 363.82 | 363.82 | Yes | 03/11/2021 | GO2122004891PH | MVS | TPH212244682M002 | Administrative Approval Issued | N/A | Yes | 463.64 | Yes | 348.2 | 15/09/2021
73 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 8th (2021-2022) | New | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | TSM/009215 |  | 40012316 | 2 | 1252 | 1235 | 1235 | 644.73 | 644.73 | Yes | 08/04/2022 | GO2223000126PH | MVS | PH222352023S000 | Administrative Approval Issued | N/A | Yes | 153.96 | Yes | 706.17 | 27/01/2022
74 | NADIA | Nadia Arsenic Civil Division II | Karimpur-II | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | TSM/009115 | SM/01456 | 40008418 | 8 | 10577 | 4561 | 4561 | 1316.91 | 1316.91 | Yes | 22/02/2022 | GO2122009915PH | MVS | PH212246699M002 | Administrative Approval Issued | N/A | Yes | 1387.19 | Yes | 1167.96 | 22/11/2021
75 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09866 | TSM/009127 | SM/01870 | 40000222 | 2 | 1584 | 550 | 550 | 282.6 | 282.6 | Yes | 06/12/2021 | GO2122006494PH | MVS | TPH212246319M001 | Administrative Approval Issued | N/A | Yes | 81.3 | Yes | 292.26 | 22/11/2021
76 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 6th (2021-2022) | Augmentation | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | TSM/009107 | SM/01445 | 40000228 | 2 | 3746 | 2255 | 2255 | 523.86 | 523.86 | Yes | 06/12/2021 | GO2122006493PH | MVS | TPH212246334M002 | Administrative Approval Issued | N/A | Yes | 297.15 | Yes | 466.06 | 22/11/2021
77 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 9th (2021-2022) | New | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | TSM/008996 |  | 40012303 | 1 | 1496 | 1387 | 1387 | 691.91 | 691.91 | Yes | 08/04/2022 | GO2223000138PH | SVS | PH222352029S000 | Administrative Approval Issued | N/A | Yes | 168.01 | Yes | 627.95 | 17/02/2022
78 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2022-2023) | New | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | TSM/011905 |  | 40019253 | 6 | 1621 | 1847 | 1847 | 827.34 | 827.34 | Yes | 25/08/2022 | GO2223006706PH | MVS | PH222359401S000 | Administrative Approval Issued | N/A | Yes | 499.09 | Yes | 936.03 | 05/07/2022
79 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Chak Rudranagar village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II | SM/16104 | TSM/015477 |  | 40053846 | 1 | 33 | 76 | 76 | 37.9 | 37.9 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M005 | Administrative Approval Issued | N/A | Yes | 83.53 | Yes | 28.01 | 28/12/2022
80 | NADIA | Nadia Arsenic Civil Division II | Karimpur-II | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Jayghata village, Block- Karimpur-II, Nadia District , under Nadia Arsenic Civil Division-II. | SM/16109 | TSM/015525 |  | 40056670 | 1 | 115 | 99 | 99 | 40.53 | 40.53 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M010 | Administrative Approval Issued | N/A | Yes | 91.18 | Yes | 35.68 | 28/12/2022
81 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09245 | TSM/008762 | SM/04573 | 8385074 | 3 | 1364 | 430 | 430 | 254.93 | 254.93 | Yes | 03/11/2021 | GO2122004886PH | MVS | TPH212244456M002 | Administrative Approval Issued | N/A | Yes | 167.77 | Yes | 183.04 | 15/09/2021
82 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | TSM/008728 | SM/01490 | 8385027 | 3 | 2486 | 1595 | 1595 | 410.07 | 410.07 | Yes | 03/11/2021 | GO2122004887PH | MVS | TPH212244695M001 | Administrative Approval Issued | N/A | Yes | 220.22 | Yes | 365.28 | 15/09/2021
83 | NADIA | Nadia Arsenic Civil Division II | Chapra | 7th (2021-2022) | New | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | TSM/009068 |  | 40002354 | 2 | 1956 | 1582 | 1582 | 896.36 | 896.36 | Yes | 02/02/2022 | GO2122009120PH | MVS | PH212248289S000 | Administrative Approval Issued | N/A | Yes | 230.4 | Yes | 952.33 | 16/12/2021
84 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Bahadurpur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07941 | TSM/007118 | SM/01444 | 8207285 | 2 | 1004 | 502 | 502 | 45.89 | 45.89 | Yes | 21/01/2021 | GO2021004996PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
85 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Bagakhali Zone-II water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07942 | TSM/007116 | SM/01870 | 8207251 | 2 | 1584 | 762 | 762 | 69.23 | 69.23 | Yes | 21/01/2021 | GO2021004987PH | MVS |  | Administrative Approval Issued | N/A | Yes | 5 | Yes | 5 | 08/01/2021
86 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Puthimari water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07959 | TSM/007110 | SM/01494 | 8207241 | 1 | 2239 | 915 | 915 | 74.17 | 74.17 | Yes | 21/01/2021 | GO2021005004PH | SVS |  | Administrative Approval Issued | N/A | Yes | 0 | No | N/A | 08/01/2021
87 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | TSM/008763 | SM/04572 | 8385076 | 3 | 1989 | 1593 | 1593 | 341.47 | 341.47 | Yes | 03/11/2021 | GO2122004886PH | MVS | TPH212244456M001 | Administrative Approval Issued | N/A | Yes | 124.14 | Yes | 398.21 | 15/09/2021
88 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Shyamnagar water supply scheme under Krishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08248 | TSM/007318 | SM/01418 | 8223889 | 6 | 3071 | 1023 | 1023 | 71.92 | 71.92 | Yes | 22/02/2021 | GO2021007406PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
89 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | TSM/008734 | SM/01350 | 8384688 | 3 | 2552 | 1556 | 1556 | 363.55 | 363.55 | Yes | 03/11/2021 | GO2122004877PH | MVS | TPH212244689M002 | Administrative Approval Issued | N/A | Yes | 636.91 | Yes | 305.42 | 15/09/2021
90 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09265 | TSM/008722 | SM/01351 | 8385105 | 3 | 1970 | 982 | 982 | 370.76 | 370.76 | Yes | 03/11/2021 | GO2122004873PH | MVS | TPH212244700M003 | Administrative Approval Issued | N/A | Yes | 309.17 | Yes | 326.22 | 15/09/2021
91 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09271 | TSM/008671 | SM/01494 | 8385158 | 1 | 2239 | 1269 | 1269 | 357.37 | 357.37 | Yes | 03/11/2021 | GO2122004878PH | SVS | PH212244725M003 | Administrative Approval Issued | N/A | Yes | 272.47 | Yes | 154.53 | 15/09/2021
92 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 6th (2021-2022) | Augmentation | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09870 | TSM/009095 | SM/04636 | 40000227 | 6 | 2949 | 2623 | 2623 | 332.03 | 332.03 | Yes | 06/12/2021 | GO2122006492PH | MVS | TPH212246338M001 | Administrative Approval Issued | N/A | Yes | 179.4 | Yes | 272.89 | 22/11/2021
93 | NADIA | Nadia Arsenic Civil Division II | Chapra | 7th (2021-2022) | New | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | TSM/009069 |  | 40002353 | 2 | 1995 | 1261 | 1261 | 665.19 | 665.19 | Yes | 02/02/2022 | GO2122009122PH | MVS | PH212248298S000 | Administrative Approval Issued | N/A | Yes | 150.64 | Yes | 594.88 | 16/12/2021
94 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 9th (2021-2022) | New | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | TSM/008994 |  | 40012160 | 2 | 1231 | 1218 | 1218 | 616.06 | 616.06 | Yes | 08/04/2022 | GO2223000127PH | MVS | PH222352026S000 | Administrative Approval Issued | N/A | Yes | 159.44 | Yes | 662.01 | 17/02/2022
95 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2020-2021) | Retrofitting | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07300 | TSM/006286 | SM/01216 | 8136351 | 1 | 1128 | 972 | 972 | 82.35 | 82.35 | Yes | 10/12/2020 | GO2021003282PH | SVS |  | Administrative Approval Issued | N/A | Yes | 14.41 | Yes | 14.41 | 25/09/2020
96 | NADIA | Nadia Arsenic Civil Division II | Karimpur-II | 5th (2022-2023) | New | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | TSM/014311 |  | 40023326 | 1 | 870 | 509 | 509 | 280.28 | 280.28 | Yes | 13/09/2022 | GO2223007591PH | SVS | PH222362262S000 | Administrative Approval Issued | N/A | Yes | 238.93 | Yes | 285.3 | 22/08/2022
97 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Dharammpur (Part-B) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16101 | TSM/015464 |  | 40056634 | 1 | 447 | 95 | 95 | 40.07 | 40.07 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M002 | Administrative Approval Issued | N/A | Yes | 89.85 | Yes | 32.37 | 28/12/2022
98 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Labangola village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16105 | TSM/015521 |  | 40053847 | 1 | 81 | 79 | 79 | 38.24 | 38.24 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M006 | Administrative Approval Issued | N/A | Yes | 56.35 | Yes | 34.47 | 28/12/2022
99 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Chak Ramnagar village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II, | SM/16106 | TSM/015522 |  | 40053849 | 1 | 29 | 82 | 82 | 38.59 | 38.59 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M007 | Administrative Approval Issued | N/A | Yes | 85.53 | Yes | 33.79 | 28/12/2022
100 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 10th(2022-2023) | New | Mini Piped Water Supply Scheme at Jaba(Part-A) village, Block- Krishnagar-I, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16107 | TSM/015523 |  | 40052014 | 1 | 247 | 96 | 96 | 40.53 | 40.53 | Yes | 22/02/2023 | GO2223014643PH | SVS | PH222372072M008 | Administrative Approval Issued | N/A | Yes | 60.12 | Yes | 35.34 | 28/12/2022
101 | NADIA | Nadia Arsenic Civil Division II | Chapra | 9th (2021-2022) | New | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | TSM/008800 |  | 40012127 | 2 | 1534 | 1651 | 1651 | 731.98 | 731.98 | Yes | 08/04/2022 | GO2223000132PH | MVS | PH222352032S000 | Administrative Approval Issued | N/A | Yes | 146.1 | Yes | 656.76 | 17/02/2022
102 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 5th (2020-2021) | Retrofitting | Retrofitting of Chandpur water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07934 | TSM/007111 | SM/04573 | 8207335 | 3 | 1364 | 597 | 883 | 56.33 | 56.33 | Yes | 21/01/2021 | GO2021004990PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0.01 | Yes | 0.01 | 08/01/2021
103 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Chanderghat water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07963 | TSM/007119 | SM/01457 | 8207303 | 1 | 2957 | 995 | 955 | 84.6 | 84.6 | Yes | 21/01/2021 | GO2021005005PH | SVS |  | Administrative Approval Issued | N/A | Yes | 4.98 | Yes | 4.98 | 08/01/2021
104 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 6th (2020-2021) | Retrofitting | Retrofitting of Mobarakpur water supply scheme underTehatta-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08300 | TSM/007316 | SM/01486 | 8223841 | 4 | 4514 | 1119 | 1038 | 83.19 | 83.19 | Yes | 26/02/2021 | GO2021007620PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0 | No | N/A | 10/02/2021
105 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 6th (2020-2021) | Retrofitting | Retrofitting of Baranaldaha water supply scheme underTehatta-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08308 | TSM/007295 | SM/01445 | 8347930 | 2 | 3746 | 1112 | 1112 | 89.71 | 89.71 | Yes | 26/02/2021 | GO2021007572PH | MVS |  | Administrative Approval Issued | N/A | Yes | 45.02 | Yes | 0.01 | 10/02/2021
106 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Helenchi Zone-II water supply scheme under Krishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08253 | TSM/007302 | SM/01875 | 8322337 | 3 | 2880 | 828 | 828 | 63.45 | 63.45 | Yes | 22/02/2021 | GO2021007409PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0 | Yes | 0 | 10/02/2021
107 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Helenchi Zone-III water supply scheme under Krishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08254 | TSM/007301 | SM/01875 | 8322433 | 3 | 2880 | 1331 | 1331 | 95.53 | 95.53 | Yes | 22/02/2021 | GO2021007410PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
108 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | TSM/008729 | SM/01354 | 8384667 | 4 | 2437 | 1106 | 1106 | 354.83 | 354.83 | Yes | 03/11/2021 | GO2122004875PH | MVS | TPH212244696M001 | Administrative Approval Issued | N/A | Yes | 209.33 | Yes | 343.6 | 15/09/2021
109 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Augmentation | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09262 | TSM/008726 | SM/01472 | 8385167 | 6 | 2498 | 833 | 833 | 355.21 | 355.21 | Yes | 03/11/2021 | GO2122004875PH | MVS | TPH212244696M003 | Administrative Approval Issued | N/A | Yes | 289.03 | Yes | 294.73 | 15/09/2021
110 | NADIA | Nadia Arsenic Civil Division II | Karimpur-II | 1st (2021-2022) | Retrofitting | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | TSM/008244 | SM/01456 | 40000474 | 1 | 2295 | 6498 | 3249 | 298.77 | 298.77 | Yes | 25/11/2021 | GO2122005903PH | SVS | TPH212245389M002 | Administrative Approval Issued | N/A | Yes | 0.07 | Yes | 424.14 | 19/08/2021
111 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 9th (2021-2022) | New | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | TSM/008657 |  | 40012112 | 4 | 5380 | 4138 | 4138 | 1172.37 | 1172.37 | Yes | 20/04/2022 | GO2223000426PH | MVS | PH222352030S000 | Administrative Approval Issued | N/A | Yes | 233.44 | Yes | 1173.58 | 17/02/2022
112 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2022-2023) | New | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | TSM/012015 |  | 40032376 | 3 | 2684 | 2816 | 2816 | 1090.05 | 1090.05 | Yes | 14/09/2022 | GO2223007713PH | MVS | PH222359391S000 | Administrative Approval Issued | N/A | Yes | 659.9 | Yes | 999.41 | 05/07/2022
113 | NADIA | Nadia Arsenic Civil Division II | Chapra | 9th (2021-2022) | New | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | TSM/008804 |  | 40012313 | 1 | 1282 | 1665 | 1665 | 675.73 | 675.73 | Yes | 08/04/2022 | GO2223000136PH | SVS | PH222352025S000 | Administrative Approval Issued | N/A | Yes | 167.8 | Yes | 680.19 | 17/02/2022
114 | NADIA | Nadia Arsenic Civil Division II | Karimpur-I | 5th (2022-2023) | New | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | TSM/014577 |  | 40023322 | 1 | 807 | 905 | 905 | 442.03 | 442.03 | Yes | 13/09/2022 | GO2223007590PH | SVS | PH222362272S000 | Administrative Approval Issued | N/A | Yes | 391.42 | Yes | 438.17 | 22/08/2022
115 | NADIA | Nadia Arsenic Civil Division II | Chapra | 1st (2021-2022) | Retrofitting | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | TSM/008243 | SM/01788 | 40000472 | 1 | 2295 | 5086 | 2543 | 297.37 | 297.37 | Yes | 25/11/2021 | GO2122005902PH | SVS | TPH212243032M003 | Administrative Approval Issued | N/A | Yes | 0.1 | Yes | 375.68 | 19/08/2021
Total | [10 empty] | 327 | 288749 | 170655 | 152011 | 39130.42 | 39130.42 | [8 empty] | 22752.87 |  | 33449.12