## List of schemes approved in SlS
List of schemes approved in SlSSC (Rs. in Lakh)
District - NADIA
SL No | District | Division | Block | SlSSC No. | Scheme Type | Scheme | Scheme SM Code | TSM code | Parent SM code | Scheme IMIS Code | No. of Villages | Total Households | FHTCs approved | Corrected FHTCs | Estimated Cost | Modified Cost | AAFS Status | AAFS Date | AAFS No. | Scheme coverage type | AAFS code | Current Status | Current Position | Tender Status | Tender Cost | WO Status | WO Cost | SlSSC Date
1 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2020-2021) | Retrofitting | Retrofitting of Taldaha water supply scheme under Krishnaganj Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07297 | TSM/006285 | SM/01505 | 8136242 | 5 | 1661 | 1193 | 1193 | 99.95 | 99.95 | Yes | 10/12/2020 | GO2021003279PH | MVS |  | Administrative Approval Issued | N/A | Yes | 30.25 | Yes | 30.25 | 25/09/2020
2 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 5th (2020-2021) | Retrofitting | Retrofitting of Bansbaria water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07936 | TSM/007115 | SM/04671 | 8207272 | 2 | 1348 | 652 | 652 | 62.86 | 62.86 | Yes | 21/01/2021 | GO2021004986PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.98 | Yes | 4.98 | 08/01/2021
3 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Maheshpur water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07937 | TSM/007121 | SM/01351 | 8207399 | 3 | 1970 | 924 | 924 | 74.87 | 74.87 | Yes | 21/01/2021 | GO2021004994PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
4 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Gongra water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07960 | TSM/007113 | SM/01354 | 8207364 | 4 | 2437 | 970 | 970 | 82.68 | 82.68 | Yes | 21/01/2021 | GO2021005006PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
5 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Tengra water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07962 | TSM/007123 | SM/01349 | 8207419 | 2 | 776 | 493 | 493 | 40.29 | 40.29 | Yes | 21/01/2021 | GO2021005003PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
6 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Kadipur water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08301 | TSM/007314 | SM/01472 | 8223818 | 6 | 2498 | 1169 | 1169 | 86.88 | 86.88 | Yes | 26/02/2021 | GO2021007578PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
7 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Helenchi Zone-I water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District, under Nadia ArsenicCivil Division-II, P.H.E. Dte | SM/08252 | TSM/007304 | SM/01875 | 8214489 | 8 | 7581 | 1232 | 1232 | 94.86 | 94.86 | Yes | 22/02/2021 | GO2021007411PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0.05 | Yes | 0.05 | 10/02/2021
8 | NADIA | Nadia Arsenic Civil Division II | Chapra | 1st (2021-2022) | Retrofitting | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | TSM/008242 | SM/01785 | 40000471 | 1 | 2295 | 5598 | 2799 | 298 | 298 | Yes | 25/11/2021 | GO2122005902PH | SVS | TPH212243032M002 | Administrative Approval Issued | N/A | Yes | 14.15 | Yes | 210.61 | 19/08/2021
9 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Nischintapur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07939 | TSM/007122 | SM/01490 | 8207403 | 3 | 2486 | 833 | 833 | 70.53 | 70.53 | Yes | 21/01/2021 | GO2021004991PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.98 | Yes | 4.98 | 08/01/2021
10 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Bahirgachi Zone-I water supply scheme underChapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08305 | TSM/007299 | SM/01483 | 8223806 | 5 | 3092 | 835 | 835 | 49.68 | 49.68 | Yes | 26/02/2021 | GO2021007574PH | MVS |  | Administrative Approval Issued | N/A | Yes | 8.55 | Yes | 8.55 | 10/02/2021
11 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 5th (2020-2021) | Retrofitting | Retrofitting of Damodarkhali water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07935 | TSM/007112 | SM/04572 | 8207349 | 3 | 1989 | 1005 | 1005 | 82.16 | 82.16 | Yes | 21/01/2021 | GO2021004984PH | MVS |  | Administrative Approval Issued | N/A | Yes | 121.54 | Yes | 121.54 | 08/01/2021
12 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 4th (2020-2021) | Retrofitting | Retrofitting of Sakdaha water supply scheme under Krishnaganj Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07833 | TSM/006756 | SM/01555 | 8207414 | 3 | 1271 | 946 | 946 | 79.37 | 79.37 | Yes | 14/01/2021 | GO2021004541PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.98 | Yes | 4.98 | 04/12/2020
13 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09249 | TSM/008759 | SM/01473 | 8385093 | 1 | 733 | 234 | 234 | 183.74 | 183.74 | Yes | 03/11/2021 | GO2122004885PH | SVS | TPH212244665M001 | Administrative Approval Issued | N/A | Yes | 82.6 | Yes | 129.56 | 15/09/2021
14 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | TSM/008757 | SM/01483 | 8385061 | 2 | 1176 | 671 | 671 | 201.91 | 201.91 | Yes | 03/11/2021 | GO2122004885PH | MVS | TPH212244665M002 | Administrative Approval Issued | N/A | Yes | 127.2 | Yes | 164.23 | 15/09/2021
15 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Mahatpur water supply scheme under Chapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08251 | TSM/007305 | SM/01788 | 8347927 | 3 | 7447 | 1360 | 1360 | 98.97 | 98.97 | Yes | 22/02/2021 | GO2021007400PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
16 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2020-2021) | Retrofitting | Retrofitting of PATHARGHATA water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07298 | TSM/006288 | SM/01492 | 8136047 | 1 | 3038 | 921 | 921 | 77.3 | 77.3 | Yes | 10/12/2020 | GO2021003280PH | SVS |  | Administrative Approval Issued | N/A | Yes | 47.69 | Yes | 47.69 | 25/09/2020
17 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Betbaria water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07940 | TSM/007124 | SM/01692 | 8207291 | 1 | 1274 | 1043 | 1043 | 93.26 | 93.26 | Yes | 21/01/2021 | GO2021004989PH | SVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
18 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 6th (2020-2021) | Retrofitting | Retrofitting of Digri water supply scheme underKrishnagar-I Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08303 | TSM/007309 | SM/04636 | 8322496 | 5 | 2717 | 1301 | 970 | 99.45 | 99.45 | Yes | 26/02/2021 | GO2021007576PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
19 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Bahirgachi Zone-II water supply scheme underChapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08306 | TSM/007298 | SM/01483 | 8223899 | 5 | 3092 | 850 | 850 | 59.58 | 59.58 | Yes | 26/02/2021 | GO2021007573PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
20 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 5th (2020-2021) | Retrofitting | Retrofitting of Krishnagar water supply scheme under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07961 | TSM/007114 | SM/00231 | 8207394 | 1 | 1201 | 824 | 824 | 77.01 | 77.01 | Yes | 21/01/2021 | GO2021005007PH | SVS |  | Administrative Approval Issued | N/A | Yes | 3.7 | Yes | 4.97 | 08/01/2021
21 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | TSM/008756 | SM/04671 | 8385068 | 2 | 1348 | 962 | 962 | 192.64 | 192.64 | Yes | 03/11/2021 | GO2122004885PH | MVS | TPH212244665M003 | Administrative Approval Issued | N/A | Yes | 117.92 | Yes | 118.34 | 15/09/2021
22 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 6th (2020-2021) | Retrofitting | Retrofitting of Bagakhali Zone-I water supply scheme underTehatta-I Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08307 | TSM/007296 | SM/01870 | 8223792 | 4 | 4291 | 1176 | 1176 | 96.32 | 96.32 | Yes | 26/02/2021 | GO2021007597PH | MVS |  | Administrative Approval Issued | N/A | Yes | 5 | Yes | 5 | 10/02/2021
23 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Matiary water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08309 | TSM/007293 | SM/01485 | 8223874 | 2 | 2959 | 1267 | 1267 | 99.84 | 99.84 | Yes | 26/02/2021 | GO2021007595PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
24 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | TSM/008760 | SM/01875 | 8385081 | 3 | 2238 | 739 | 739 | 324.86 | 324.86 | Yes | 03/11/2021 | GO2122004890PH | MVS | TPH212244648M001 | Administrative Approval Issued | N/A | Yes | 112.09 | Yes | 279.17 | 15/09/2021
25 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09248 | TSM/008758 | SM/01875 | 8385077 | 3 | 3267 | 2269 | 2269 | 329.58 | 329.58 | Yes | 03/11/2021 | GO2122004890PH | MVS | TPH212244648M002 | Administrative Approval Issued | N/A | Yes | 391.88 | Yes | 350.95 | 15/09/2021
26 | NADIA | Nadia Arsenic Civil Division II | Chapra | 3rd (2020-2021) | Retrofitting | Retrofitting of Lakshmipur water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07299 | TSM/006287 | SM/01350 | 8136227 | 3 | 2552 | 803 | 803 | 76.25 | 76.25 | Yes | 10/12/2020 | GO2021003281PH | MVS |  | Administrative Approval Issued | N/A | Yes | 44.32 | Yes | 44.32 | 25/09/2020
27 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Khanjepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07943 | TSM/007120 | SM/01473 | 8207386 | 1 | 733 | 622 | 622 | 55.53 | 55.53 | Yes | 21/01/2021 | GO2021004997PH | SVS |  | Administrative Approval Issued | N/A | Yes | 0 | No | N/A | 08/01/2021
28 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Jayghata water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08302 | TSM/007312 | SM/03107 | 8223861 | 3 | 2026 | 1038 | 1038 | 75.64 | 75.64 | Yes | 26/02/2021 | GO2021007577PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
29 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 6th (2020-2021) | Retrofitting | Retrofitting of Barnia water supply scheme underTehatta-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08304 | TSM/007308 | SM/01779 | 8223907 | 5 | 7541 | 1060 | 1060 | 84.21 | 84.21 | Yes | 26/02/2021 | GO2021007575PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0.36 | Yes | 0.36 | 10/02/2021
30 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | TSM/008761 | SM/01505 | 8385085 | 5 | 1661 | 660 | 660 | 298.02 | 298.02 | Yes | 03/11/2021 | GO2122004886PH | MVS | TPH212244456M003 | Administrative Approval Issued | N/A | Yes | 231.7 | Yes | 283.17 | 15/09/2021
31 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Brittihuda water supply scheme under Chapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08249 | TSM/007310 | SM/01785 | 8214480 | 8 | 9382 | 972 | 972 | 76.67 | 76.67 | Yes | 22/02/2021 | GO2021007405PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
32 | NADIA | Nadia Arsenic Civil Division II | Karimpur-II | 6th (2020-2021) | Retrofitting | Retrofitting of Thanapara water supply scheme under Karimpur-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08250 | TSM/007307 | SM/01456 | 8347910 | 2 | 5720 | 1331 | 1331 | 97.93 | 97.93 | Yes | 22/02/2021 | GO2021007403PH | MVS |  | Administrative Approval Issued | N/A | Yes | 133 | Yes | 133 | 10/02/2021
33 | NADIA | Nadia Arsenic Civil Division II | Chapra | 6th (2020-2021) | Retrofitting | Retrofitting of Balibanga water supply scheme under Chapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08255 | TSM/007292 | SM/01346 | 8223918 | 5 | 3260 | 976 | 976 | 72.47 | 72.47 | Yes | 22/02/2021 | GO2021007407PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
34 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 1st (2021-2022) | Retrofitting | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | TSM/008241 | SM/01779 | 40000470 | 5 | 7541 | 9025 | 2718 | 273.75 | 273.75 | Yes | 25/11/2021 | GO2122005902PH | MVS | TPH212243032M001 | Administrative Approval Issued | N/A | Yes | 266.33 | Yes | 266.33 | 19/08/2021
35 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 1st (2021-2022) | Retrofitting | Retrofitting of Patharghata water supply scheme (Phase-II) under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09696 | TSM/008240 | SM/01492 | 40000473 | 1 | 3038 | 6112 | 2532 | 252.57 | 252.57 | Yes | 25/11/2021 | GO2122005903PH | SVS | TPH212245389M001 | Administrative Approval Issued | N/A | Yes | 20.66 | Yes | 239.6 | 19/08/2021
36 | NADIA | Nadia Arsenic Civil Division II | Chapra | 5th (2020-2021) | Retrofitting | Retrofitting of Bagbaria water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07938 | TSM/007117 | SM/01551 | 8207263 | 3 | 1286 | 984 | 984 | 83.76 | 83.76 | Yes | 21/01/2021 | GO2021004998PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
37 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09245 | TSM/008762 | SM/04573 | 8385074 | 3 | 1364 | 430 | 430 | 254.93 | 254.93 | Yes | 03/11/2021 | GO2122004886PH | MVS | TPH212244456M002 | Administrative Approval Issued | N/A | Yes | 167.77 | Yes | 183.04 | 15/09/2021
38 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Bahadurpur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07941 | TSM/007118 | SM/01444 | 8207285 | 2 | 1004 | 502 | 502 | 45.89 | 45.89 | Yes | 21/01/2021 | GO2021004996PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 08/01/2021
39 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Bagakhali Zone-II water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07942 | TSM/007116 | SM/01870 | 8207251 | 2 | 1584 | 762 | 762 | 69.23 | 69.23 | Yes | 21/01/2021 | GO2021004987PH | MVS |  | Administrative Approval Issued | N/A | Yes | 5 | Yes | 5 | 08/01/2021
40 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Puthimari water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07959 | TSM/007110 | SM/01494 | 8207241 | 1 | 2239 | 915 | 915 | 74.17 | 74.17 | Yes | 21/01/2021 | GO2021005004PH | SVS |  | Administrative Approval Issued | N/A | Yes | 0 | No | N/A | 08/01/2021
41 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 3rd (2021-2022) | Retrofitting | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | TSM/008763 | SM/04572 | 8385076 | 3 | 1989 | 1593 | 1593 | 341.47 | 341.47 | Yes | 03/11/2021 | GO2122004886PH | MVS | TPH212244456M001 | Administrative Approval Issued | N/A | Yes | 124.14 | Yes | 398.21 | 15/09/2021
42 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Shyamnagar water supply scheme under Krishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08248 | TSM/007318 | SM/01418 | 8223889 | 6 | 3071 | 1023 | 1023 | 71.92 | 71.92 | Yes | 22/02/2021 | GO2021007406PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
43 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 3rd (2020-2021) | Retrofitting | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07300 | TSM/006286 | SM/01216 | 8136351 | 1 | 1128 | 972 | 972 | 82.35 | 82.35 | Yes | 10/12/2020 | GO2021003282PH | SVS |  | Administrative Approval Issued | N/A | Yes | 14.41 | Yes | 14.41 | 25/09/2020
44 | NADIA | Nadia Arsenic Civil Division II | Krishnagar-I | 5th (2020-2021) | Retrofitting | Retrofitting of Chandpur water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07934 | TSM/007111 | SM/04573 | 8207335 | 3 | 1364 | 597 | 883 | 56.33 | 56.33 | Yes | 21/01/2021 | GO2021004990PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0.01 | Yes | 0.01 | 08/01/2021
45 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 5th (2020-2021) | Retrofitting | Retrofitting of Chanderghat water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07963 | TSM/007119 | SM/01457 | 8207303 | 1 | 2957 | 995 | 955 | 84.6 | 84.6 | Yes | 21/01/2021 | GO2021005005PH | SVS |  | Administrative Approval Issued | N/A | Yes | 4.98 | Yes | 4.98 | 08/01/2021
46 | NADIA | Nadia Arsenic Civil Division II | Tehatta-I | 6th (2020-2021) | Retrofitting | Retrofitting of Mobarakpur water supply scheme underTehatta-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08300 | TSM/007316 | SM/01486 | 8223841 | 4 | 4514 | 1119 | 1038 | 83.19 | 83.19 | Yes | 26/02/2021 | GO2021007620PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0 | No | N/A | 10/02/2021
47 | NADIA | Nadia Arsenic Civil Division II | Tehatta-II | 6th (2020-2021) | Retrofitting | Retrofitting of Baranaldaha water supply scheme underTehatta-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08308 | TSM/007295 | SM/01445 | 8347930 | 2 | 3746 | 1112 | 1112 | 89.71 | 89.71 | Yes | 26/02/2021 | GO2021007572PH | MVS |  | Administrative Approval Issued | N/A | Yes | 45.02 | Yes | 0.01 | 10/02/2021
48 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Helenchi Zone-II water supply scheme under Krishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08253 | TSM/007302 | SM/01875 | 8322337 | 3 | 2880 | 828 | 828 | 63.45 | 63.45 | Yes | 22/02/2021 | GO2021007409PH | MVS |  | Administrative Approval Issued | N/A | Yes | 0 | Yes | 0 | 10/02/2021
49 | NADIA | Nadia Arsenic Civil Division II | Krishnaganj | 6th (2020-2021) | Retrofitting | Retrofitting of Helenchi Zone-III water supply scheme under Krishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District | SM/08254 | TSM/007301 | SM/01875 | 8322433 | 3 | 2880 | 1331 | 1331 | 95.53 | 95.53 | Yes | 22/02/2021 | GO2021007410PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.99 | Yes | 4.99 | 10/02/2021
50 | NADIA | Nadia Arsenic Civil Division II | Karimpur-II | 1st (2021-2022) | Retrofitting | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | TSM/008244 | SM/01456 | 40000474 | 1 | 2295 | 6498 | 3249 | 298.77 | 298.77 | Yes | 25/11/2021 | GO2122005903PH | SVS | TPH212245389M002 | Administrative Approval Issued | N/A | Yes | 0.07 | Yes | 424.14 | 19/08/2021
51 | NADIA | Nadia Arsenic Civil Division II | Chapra | 1st (2021-2022) | Retrofitting | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | TSM/008243 | SM/01788 | 40000472 | 1 | 2295 | 5086 | 2543 | 297.37 | 297.37 | Yes | 25/11/2021 | GO2122005902PH | SVS | TPH212243032M003 | Administrative Approval Issued | N/A | Yes | 0.1 | Yes | 375.68 | 19/08/2021
Total | [10 empty] | 155 | 144235 | 76813 | 58169 | 6512.3 | 6512.3 | [8 empty] | 2215.27 |  | 3937.95