## List of schemes approved in SlS
List of schemes approved in SlSSC (Rs. in Lakh)
District - MURSHIDABAD
SL No | District | Division | Block | SlSSC No. | Scheme Type | Scheme | Scheme SM Code | TSM code | Parent SM code | Scheme IMIS Code | No. of Villages | Total Households | FHTCs approved | Corrected FHTCs | Estimated Cost | Modified Cost | AAFS Status | AAFS Date | AAFS No. | Scheme coverage type | AAFS code | Current Status | Current Position | Tender Status | Tender Cost | WO Status | WO Cost | SlSSC Date
1 | MURSHIDABAD | Berhampur Division I | Beldanga - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-J) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08107 | TSM/006505 | SM/01396 | 5272688 | 1 | 3263 | 5364 | 2282 | 383.46 | 383.46 | Yes | 09/02/2021 | GO2021006713PH | MVS |  | Administrative Approval Issued | N/A | Yes | 259.69 | No | N/A | 04/12/2020
2 | MURSHIDABAD | Berhampur Division I | Lalgola | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nasipur (Code-314186) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-C) | SM/07690 | TSM/006448 | SM/00871 | 8362354 | 1 | 2723 | 1920 | 1920 | 129.56 | 129.56 | Yes | 07/01/2021 | GO2021004283PH | SVS |  | Administrative Approval Issued | N/A | Yes | 111.5 | No | N/A | 04/12/2020
3 | MURSHIDABAD | Berhampur Division I | Beldanga - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mirzapur (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In | SM/07704 | TSM/006901 | SM/03343 | 5272688 | 1 | 6340 | 767 | 5380 | 64.01 | 64.01 | Yes | 07/01/2021 | GO2021004288PH | SVS |  | Administrative Approval Issued | N/A | Yes | 118.11 | No | N/A | 04/12/2020
4 | MURSHIDABAD | Berhampur Division I | Lalgola | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidaba | SM/07705 | TSM/006428 | SM/01495 | 8155412 | 1 | 2570 | 2126 | 2126 | 143.18 | 143.18 | Yes | 07/01/2021 | GO2021004279PH | SVS |  | Administrative Approval Issued | N/A | Yes | 32.28 | No | N/A | 04/12/2020
5 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The C | SM/07724 | TSM/006434 | SM/01539 | 8155521 | 4 | 1966 | 1454 | 1454 | 99.92 | 99.92 | Yes | 07/01/2021 | GO2021004265PH | SVS |  | Administrative Approval Issued | N/A | Yes | 18.37 | No | N/A | 04/12/2020
6 | MURSHIDABAD | Berhampur Division I | Beldanga - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08114 | TSM/006897 | SM/03343 | 5272688 | 5 | 7500 | 4053 | 9240 | 312.34 | 312.34 | Yes | 09/02/2021 | GO2021006696PH | MVS |  | Administrative Approval Issued | N/A | Yes | 34.66 | No | N/A | 04/12/2020
7 | MURSHIDABAD | Berhampur Division I | Murshidabad Jiaganj | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08115 | TSM/006902 | SM/01013 | 8275548 | 3 | 4114 | 7186 | 3458 | 552.45 | 552.45 | Yes | 09/02/2021 | GO2021006702PH | MVS |  | Administrative Approval Issued | N/A | Yes | 400.92 | No | N/A | 04/12/2020
8 | MURSHIDABAD | Berhampur Division I | Murshidabad Jiaganj | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector | SM/08117 | TSM/006904 | SM/01013 | 8275574 | 18 | 8044 | 6774 | 6844 | 533.01 | 533.01 | Yes | 09/02/2021 | GO2021006709PH | MVS |  | Administrative Approval Issued | N/A | Yes | 326.26 | No | N/A | 04/12/2020
9 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 3rd (2020-2021) | Retrofitting | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for the Village of Aragi Kulgachi (VillageCode-314471) , Subarnamrigi (VillageCode-314473) under command area of Digha ground wate | SM/06976 | TSM/006028 | SM/01462 | 8130587 | 2 | 826 | 1169 | 1169 | 72.72 | 72.72 | Yes | 09/11/2020 | GO2021002464PH | SVS |  | Administrative Approval Issued | N/A | Yes | 64.2 | No | N/A | 25/09/2020
10 | MURSHIDABAD | Berhampur Division I | Bhagawangola - II | 3rd (2020-2021) | Retrofitting | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Harirampur ground water supply scheme | SM/06979 | TSM/006032 | SM/01947 | 8136588 | 2 | 857 | 717 | 717 | 46.15 | 46.15 | Yes | 09/11/2020 | GO2021002467PH | MVS |  | Administrative Approval Issued | N/A | Yes | 27.23 | No | N/A | 25/09/2020
11 | MURSHIDABAD | Berhampur Division I | Raninagar - II | 3rd (2020-2021) | Retrofitting | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramchandrapur ground water supply scheme | SM/07232 | TSM/006067 | SM/02437 | 8136628 | 1 | 281 | 250 | 250 | 21.55 | 21.55 | Yes | 08/12/2020 | GO2021003163PH | SVS |  | Administrative Approval Issued | N/A | Yes | 5.13 | No | N/A | 25/09/2020
12 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 3rd (2020-2021) | Retrofitting | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Paschim Gobindapur (VillageCode-314448)& Barbaria(Village Code-314462) under command area of Gobra ground water s | SM/07234 | TSM/006073 | SM/01943 | 8136633 | 2 | 1590 | 1305 | 1305 | 87.8 | 87.8 | Yes | 08/12/2020 | GO2021003165PH | SVS |  | Administrative Approval Issued | N/A | Yes | 19.75 | No | N/A | 25/09/2020
13 | MURSHIDABAD | Berhampur Division I | Beldanga - II | 3rd (2020-2021) | Retrofitting | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) | SM/07236 | TSM/006024 | SM/01407 | 1723179 | 2 | 1127 | 837 | 837 | 58.14 | 58.14 | Yes | 08/12/2020 | GO2021003171PH | MVS |  | Administrative Approval Issued | N/A | Yes | 3.55 | No | N/A | 25/09/2020
14 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mahatpur (Code-314442) In The Command Area Of Telia Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block In Murshidabad | SM/07786 | TSM/006455 | SM/01944 | 8155579 | 2 | 524 | 235 | 386 | 16.62 | 16.62 | Yes | 07/01/2021 | GO2021004220PH | SVS |  | Administrative Approval Issued | N/A | Yes | 10.54 | No | N/A | 04/12/2020
15 | MURSHIDABAD | Berhampur Division I | Lalgola | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Karttikpur (Code-314220) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-C) Under Lalgola Block | SM/07787 | TSM/006460 | SM/03277 | 4922411 | 1 | 1853 | 1220 | 1220 | 76.68 | 76.68 | Yes | 07/01/2021 | GO2021004219PH | SVS |  | Administrative Approval Issued | N/A | Yes | 61.23 | No | N/A | 04/12/2020
16 | MURSHIDABAD | Berhampur Division I | Nawda | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-II Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08903 | TSM/006488 | SM/02306 | 8156317 | 1 | 5694 | 5343 | 5343 | 362.25 | 362.25 | Yes | 29/09/2021 | GO2122003903PH | SVS |  | Administrative Approval Issued | N/A | Yes | 338.24 | No | N/A | 04/12/2020
17 | MURSHIDABAD | Berhampur Division I | Nawda | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | TSM/006500 | SM/02219 | 1723404 | 1 | 4204 | 9334 | 4492 | 650.52 | 650.52 | Yes | 29/09/2021 | GO2122003903PH | MVS |  | Administrative Approval Issued | N/A | Yes | 574.81 | No | N/A | 04/12/2020
18 | MURSHIDABAD | Berhampur Division I | Beldanga - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begunbari (Zone-I) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08909 | TSM/006504 | SM/00199 | 5272688 | 14 | 12923 | 6617 | 9496 | 460.21 | 460.21 | Yes | 29/09/2021 | GO2122003903PH | MVS |  | Administrative Approval Issued | N/A | Yes | 350.09 | No | N/A | 04/12/2020
19 | MURSHIDABAD | Berhampur Division I | Berhampore | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | TSM/006887 | SM/01013 | 8275456 | 9 | 6613 | 13110 | 5663 | 964.85 | 964.85 | Yes | 29/09/2021 | GO2122003903PH | MVS |  | Administrative Approval Issued | N/A | Yes | 42.93 | No | N/A | 04/12/2020
20 | MURSHIDABAD | Berhampur Division I | Beldanga - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo | SM/08908 | TSM/006882 | SM/03343 | 5272688 | 5 | 3682 | 5174 | 3493 | 384.82 | 384.82 | Yes | 29/09/2021 | GO2122003903PH | MVS |  | Administrative Approval Issued | N/A | Yes | 1.46 | No | N/A | 04/12/2020
21 | MURSHIDABAD | Berhampur Division I | Bhagawangola - II | 2nd (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | TSM/011876 | SM/01946 | 40034512 | 3 | 1279 | 349 | 349 | 354.9 | 354.9 | Yes | 15/09/2022 | GO2223007744PH | MVS | PH222360897M000 | Administrative Approval Issued | N/A | Yes | 752.33 | No | N/A | 20/05/2022
22 | MURSHIDABAD | Berhampur Division I | Hariharpara | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | TSM/006894 | SM/01013 | 8363463 | 2 | 6892 | 10847 | 6837 | 777.42 | 777.42 | Yes | 09/02/2021 | GO2021006698PH | MVS |  | Administrative Approval Issued | N/A | Yes | 4.86 | No | N/A | 04/12/2020
23 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 2nd (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | TSM/011874 | SM/01503 | 40026918 | 4 | 3777 | 2695 | 2695 | 899.98 | 899.98 | Yes | 22/09/2022 | GO2223008129PH | MVS | PH222360853M000 | Administrative Approval Issued | N/A | Yes | 146.03 | No | N/A | 20/05/2022
24 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 2nd (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. | SM/12738 | TSM/011934 | SM/01461 | 40027193 | 1 | 452 | 299 | 299 | 231.37 | 231.37 | Yes | 20/09/2022 | GO2223007999PH | MVS | PH222360846S000 | Administrative Approval Issued | N/A | Yes | 146.9 | No | N/A | 20/05/2022
25 | MURSHIDABAD | Berhampur Division I | Lalgola | 7th (2022-2023) | Augmentation | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | TSM/014465 | SM/01446 | 40035996 | 2 | 2369 | 671 | 671 | 838.18 | 838.18 | Yes | 20/01/2023 | GO2223012258PH | MVS | PH222365418M000 | Administrative Approval Issued | N/A | Yes | 26.59 | No | N/A | 26/09/2022
26 | MURSHIDABAD | Berhampur Division I | Nawda | 7th (2022-2023) | Augmentation | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | TSM/016325 | SM/02219 | 40036634 | 1 | 4204 | 342 | 342 | 804.99 | 804.99 | Yes | 07/02/2023 | GO2223013383PH | SVS | PH222365371M000 | Administrative Approval Issued | N/A | Yes | 600.88 | No | N/A | 26/09/2022
27 | MURSHIDABAD | Berhampur Division I | Lalgola | 7th (2022-2023) | Augmentation | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | TSM/014461 | SM/01471 | 40035989 | 3 | 2390 | 369 | 369 | 775.12 | 775.12 | Yes | 03/02/2023 | GO2223012927PH | MVS | PH222365424M000 | Administrative Approval Issued | N/A | Yes | 449.79 | No | N/A | 26/09/2022
28 | MURSHIDABAD | Berhampur Division I | Jalangi | 7th (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . | SM/14739 | TSM/011839 | SM/01948 | 40035999 | 4 | 1869 | 214 | 797 | 244.16 | 244.16 | Yes | 31/01/2023 | GO2223012661PH | MVS | PH222365435M000 | Administrative Approval Issued | N/A | Yes | 199.33 | No | N/A | 26/09/2022
29 | MURSHIDABAD | Berhampur Division I | Beldanga - II | 7th (2022-2023) | Augmentation | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | TSM/016301 | SM/01407 | 40034472 | 3 | 2588 | 250 | 250 | 436.62 | 436.62 | Yes | 15/02/2023 | GO2223013866PH | MVS | PH222365403M000 | Administrative Approval Issued | N/A | Yes | 36.21 | No | N/A | 26/09/2022
30 | MURSHIDABAD | Berhampur Division I | Nawda | 10th(2022-2023) | New | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Sibnagar Zone IV, Block- Nawda, District- Murshidabad. | SM/16437 | TSM/017930 |  | 40053687 | 1 | 528 | 100 | 100 | 40.62 | 40.62 | Yes | 28/02/2023 | GO2223014999PH | SVS | PH222371944M000 | Administrative Approval Issued | N/A | Yes | 61.08 | No | N/A | 28/12/2022
31 | MURSHIDABAD | Berhampur Division I | Lalgola | 10th(2022-2023) | New | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - DURGAPUR ZONE-IV, BLOCK - LALGOLA, DISTRICT - MURSHIDABAD. | SM/16049 | TSM/017920 |  | 40053686 | 1 | 332 | 100 | 100 | 40.62 | 40.62 | Yes | 22/02/2023 | GO2223014714PH | SVS | PH222371945M000 | Administrative Approval Issued | N/A | Yes | 61.08 | No | N/A | 28/12/2022
32 | MURSHIDABAD | Berhampur Division I | Beldanga - II | 8th (2022-2023) | New | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | TSM/015748 |  | 40033419 | 1 | 400 | 814 | 814 | 439.33 | 439.33 | Yes | 28/02/2023 | GO2223015061PH | SVS | PH222367556M000 | Administrative Approval Issued | N/A | Yes | 127.2 | No | N/A | 30/09/2022
33 | MURSHIDABAD | Berhampur Division I | Bhagawangola - II | 10th(2022-2023) | New | MALIPUR PIPED WATER SUPPLY SCHEME. | SM/16785 | TSM/017831 |  | 40035636 | 1 | 435 | 446 | 446 | 421.98 | 421.98 | Yes | 13/03/2023 | GO2223015697PH | SVS | PH222371455M000 | Administrative Approval Issued | N/A | Yes | 238.78 | No | N/A | 28/12/2022
34 | MURSHIDABAD | Berhampur Division I | Raninagar - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Char Alampur Village (Code-314767), Maheswarpur Village (Code-314768), Chatra Village (Code-314769) Under Command Area Of Moktarp | SM/07703 | TSM/006489 | SM/01400 | 8156363 | 3 | 1050 | 856 | 856 | 65.9 | 65.9 | Yes | 07/01/2021 | GO2021004270PH | MVS |  | Administrative Approval Issued | N/A | Yes | 35.66 | No | N/A | 04/12/2020
35 | MURSHIDABAD | Berhampur Division I | Lalgola | 7th (2022-2023) | New | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | TSM/016512 |  | 40033361 | 3 | 2771 | 3460 | 3460 | 1265.2 | 1265.2 | Yes | 04/08/2023 | 2248/PHE-28011/137/2023-SCHM CELL-Dept. of PHE | MVS | PH222367554M000 | Administrative Approval Issued | N/A | Yes | 730.65 | No | N/A | 26/09/2022
36 | MURSHIDABAD | Berhampur Division I | Raninagar - II | 3rd (2020-2021) | Retrofitting | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Komnagar ground water supply scheme | SM/07223 | TSM/006033 | SM/01545 | 8136589 | 1 | 983 | 882 | 882 | 59.03 | 59.03 | Yes | 08/12/2020 | GO2021003174PH | SVS |  | Administrative Approval Issued | N/A | Yes | 18.78 | No | N/A | 25/09/2020
37 | MURSHIDABAD | Berhampur Division I | Lalgola | 3rd (2020-2021) | Retrofitting | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sitesnagar ground water supply scheme | SM/07226 | TSM/006049 | SM/01500 | 8136593 | 1 | 1547 | 1410 | 1410 | 87.91 | 87.91 | Yes | 08/12/2020 | GO2021003170PH | SVS |  | Administrative Approval Issued | N/A | Yes | 16.64 | No | N/A | 25/09/2020
38 | MURSHIDABAD | Berhampur Division I | Lalgola | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Gr | SM/07688 | TSM/006412 | SM/00871 | 8362348 | 4 | 2113 | 1471 | 1587 | 98.85 | 98.85 | Yes | 07/01/2021 | GO2021004285PH | SVS |  | Administrative Approval Issued | N/A | Yes | 11.94 | No | N/A | 04/12/2020
39 | MURSHIDABAD | Berhampur Division I | Lalgola | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr | SM/07691 | TSM/006429 | SM/02241 | 1723408 | 3 | 1431 | 1206 | 1207 | 84.54 | 84.54 | Yes | 07/01/2021 | GO2021004276PH | SVS |  | Administrative Approval Issued | N/A | Yes | 91.48 | No | N/A | 04/12/2020
40 | MURSHIDABAD | Berhampur Division I | Berhampore | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | TSM/006889 | SM/01013 | 8363450 | 3 | 5125 | 14430 | 4593 | 1063.3 | 1063.3 | Yes | 09/02/2021 | GO2021006710PH | MVS |  | Administrative Approval Issued | N/A | Yes | 35.32 | No | N/A | 04/12/2020
41 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Opar Orahar (Code-314444) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-A) | SM/07729 | TSM/006439 | SM/01503 | 8155548 | 1 | 1264 | 959 | 959 | 64.96 | 64.96 | Yes | 07/01/2021 | GO2021004256PH | SVS |  | Administrative Approval Issued | N/A | Yes | 55.66 | No | N/A | 04/12/2020
42 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 3rd (2020-2021) | Retrofitting | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme | SM/06980 | TSM/006034 | SM/01461 | 8136297 | 2 | 1649 | 1274 | 1275 | 80.61 | 80.61 | Yes | 09/11/2020 | GO2021002468PH | MVS |  | Administrative Approval Issued | N/A | Yes | 5.82 | No | N/A | 25/09/2020
43 | MURSHIDABAD | Berhampur Division I | Raninagar - I | 3rd (2020-2021) | Retrofitting | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-II ground water supply scheme | SM/07231 | TSM/006065 | SM/01594 | 1723220 | 2 | 1125 | 1069 | 1069 | 71.2 | 71.2 | Yes | 08/12/2020 | GO2021003162PH | MVS |  | Administrative Approval Issued | N/A | Yes | 71.9 | No | N/A | 25/09/2020
44 | MURSHIDABAD | Berhampur Division I | Raninagar - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpu | SM/07698 | TSM/006484 | SM/01450 | 8156282 | 3 | 1493 | 1363 | 1363 | 95.9 | 95.9 | Yes | 07/01/2021 | GO2021004266PH | MVS |  | Administrative Approval Issued | N/A | Yes | 47.01 | No | N/A | 04/12/2020
45 | MURSHIDABAD | Berhampur Division I | Beldanga - II | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnag | SM/07694 | TSM/006474 | SM/01397 | 1723170 | 3 | 1174 | 1290 | 1290 | 83.34 | 83.34 | Yes | 07/01/2021 | GO2021004257PH | MVS |  | Administrative Approval Issued | N/A | Yes | 27.05 | No | N/A | 04/12/2020
46 | MURSHIDABAD | Berhampur Division I | Raninagar - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part | SM/07718 | TSM/006512 | SM/01450 | 8156429 | 2 | 1648 | 1238 | 1238 | 93.76 | 93.76 | Yes | 08/01/2021 | GO2021004310PH | MVS |  | Administrative Approval Issued | N/A | Yes | 19.17 | No | N/A | 04/12/2020
47 | MURSHIDABAD | Berhampur Division I | Beldanga - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maheshpur (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block I | SM/07890 | TSM/006900 | SM/03343 | 5272688 | 5 | 5237 | 2141 | 4583 | 173.44 | 173.44 | Yes | 19/01/2021 | GO2021004751PH | MVS |  | Administrative Approval Issued | N/A | Yes | 21.7 | No | N/A | 04/12/2020
48 | MURSHIDABAD | Berhampur Division I | Murshidabad Jiaganj | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | TSM/006885 | SM/01013 | 8275475 | 12 | 7035 | 9759 | 6259 | 717.96 | 717.96 | Yes | 29/09/2021 | GO2122003903PH | MVS |  | Administrative Approval Issued | N/A | Yes | 102.77 | No | N/A | 04/12/2020
49 | MURSHIDABAD | Berhampur Division I | Berhampore | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | TSM/006888 | SM/01013 | 8275447 | 5 | 5242 | 11888 | 7620 | 870.99 | 870.99 | Yes | 29/09/2021 | GO2122003903PH | MVS |  | Administrative Approval Issued | N/A | Yes | 793.79 | No | N/A | 04/12/2020
50 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 2nd (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | TSM/011872 | SM/01539 | 40027250 | 7 | 4681 | 2310 | 2310 | 902.24 | 902.24 | Yes | 15/09/2022 | GO2223007743PH | MVS | PH222360850M000 | Administrative Approval Issued | N/A | Yes | 130.74 | No | N/A | 20/05/2022
51 | MURSHIDABAD | Berhampur Division I | Bhagawangola - II | 2nd (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. | SM/12586 | TSM/011668 | SM/01947 | 40027367 | 2 | 857 | 552 | 552 | 512.37 | 512.37 | Yes | 15/09/2022 | GO2223007732PH | MVS | PH222360922M000 | Administrative Approval Issued | N/A | Yes | 441.4 | No | N/A | 20/05/2022
52 | MURSHIDABAD | Berhampur Division I | Jalangi | 7th (2022-2023) | Augmentation | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | TSM/015857 | SM/01697 | 40034352 | 1 | 1178 | 300 | 300 | 797.62 | 797.62 | Yes | 12/12/2022 | GO2223010886PH | SVS | PH222365383M000 | Administrative Approval Issued | N/A | Yes | 41.38 | No | N/A | 26/09/2022
53 | MURSHIDABAD | Berhampur Division I | Beldanga - II | 7th (2022-2023) | Augmentation | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | TSM/015998 | SM/01546 | 40034380 | 5 | 2133 | 653 | 653 | 591.27 | 591.27 | Yes | 20/01/2023 | GO2223012270PH | MVS | PH222365412M000 | Administrative Approval Issued | N/A | Yes | 564.83 | No | N/A | 26/09/2022
54 | MURSHIDABAD | Berhampur Division I | Raninagar - II | 7th (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | TSM/011842 | SM/01545 | 40033991 | 1 | 983 | 312 | 312 | 662.31 | 662.31 | Yes | 12/12/2022 | GO2223010882PH | SVS | PH222365393M000 | Administrative Approval Issued | N/A | Yes | 454.99 | No | N/A | 26/09/2022
55 | MURSHIDABAD | Berhampur Division I | Lalgola | 8th (2022-2023) | Augmentation | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III | SM/15231 | TSM/017872 | SM/03277 | 40034991 | 1 | 4229 | 330 | 330 | 527.09 | 527.09 | Yes | 07/02/2023 | GO2223013388PH | SVS | PH222365401M000 | Administrative Approval Issued | N/A | Yes | 18.02 | No | N/A | 30/09/2022
56 | MURSHIDABAD | Berhampur Division I | Beldanga - II | 8th (2022-2023) | Augmentation | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | TSM/017576 | SM/01750 | 40034465 | 2 | 3138 | 385 | 385 | 969.51 | 969.51 | Yes | 16/02/2023 | GO2223013906PH | MVS | PH222365453M000 | Administrative Approval Issued | N/A | Yes | 850.06 | No | N/A | 30/09/2022
57 | MURSHIDABAD | Berhampur Division I | Raninagar - II | 7th (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | TSM/011844 | SM/02200 | 40034535 | 1 | 2271 | 721 | 721 | 546.4 | 546.4 | Yes | 31/01/2023 | GO2223012653PH | SVS | PH222365392M000 | Administrative Approval Issued | N/A | Yes | 45.47 | No | N/A | 26/09/2022
58 | MURSHIDABAD | Berhampur Division I | Raninagar - I | 7th (2022-2023) | Augmentation | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | TSM/016373 | SM/01594 | 40034186 | 4 | 1817 | 664 | 748 | 933.72 | 933.72 | Yes | 03/02/2023 | GO2223012925PH | MVS | PH222365386M000 | Administrative Approval Issued | N/A | Yes | 1326.37 | No | N/A | 26/09/2022
59 | MURSHIDABAD | Berhampur Division I | Berhampore | 10th(2022-2023) | New | Mini piped water supply scheme (maximum 100 households) Village-Char Halalpur Zone-IV, Block-Berhampore, District- Murshidabad. | SM/16433 | TSM/018011 |  | 40053934 | 1 | 829 | 28 | 28 | 31.51 | 31.51 | Yes | 28/02/2023 | GO2223014997PH | SVS | PH222371928M000 | Administrative Approval Issued | N/A | Yes | 45.02 | No | N/A | 28/12/2022
60 | MURSHIDABAD | Berhampur Division I | Berhampore | 10th(2022-2023) | New | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAR NARAYANPUR , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. | SM/16441 | TSM/013372 |  | 40053665 | 1 | 141 | 78 | 78 | 38.14 | 38.14 | Yes | 28/02/2023 | GO2223015006PH | SVS | PH222371951M000 | Administrative Approval Issued | N/A | Yes | 57.07 | No | N/A | 28/12/2022
61 | MURSHIDABAD | Berhampur Division I | Berhampore | 10th(2022-2023) | New | Mini piped water supply scheme (maximum 100 households) Village-Sonadiar Zone-I, Block-Berhampore, District- Murshidabad. | SM/16500 | TSM/017951 |  | 40065608 | 1 | 120 | 100 | 100 | 40.62 | 40.62 | Yes | 03/03/2023 | GO2223015214PH | SVS | PH222371940M000 | Administrative Approval Issued | N/A | Yes | 61 | No | N/A | 28/12/2022
62 | MURSHIDABAD | Berhampur Division I | Lalgola | 10th(2022-2023) | New | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-I Block- Lalgola, District- Murshidabad. | SM/16210 | TSM/018009 |  | 40053725 | 1 | 332 | 100 | 100 | 40.62 | 40.62 | Yes | 24/02/2023 | GO2223014900PH | SVS | PH222371929M000 | Administrative Approval Issued | N/A | Yes | 61.08 | No | N/A | 28/12/2022
63 | MURSHIDABAD | Berhampur Division I | Lalgola | 9th (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | TSM/017963 | SM/01751 | 40035672 | 4 | 6299 | 1169 | 1169 | 994.64 | 994.64 | Yes | 28/02/2023 | GO2223015033PH | MVS | PH222370519M000 | Administrative Approval Issued | N/A | Yes | 68.85 | No | N/A | 16/11/2022
64 | MURSHIDABAD | Berhampur Division I | Bhagawangola - II | 10th(2022-2023) | New | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | TSM/017648 |  | 40053508 | 4 | 1556 | 1482 | 1482 | 711.04 | 711.04 | Yes | 13/03/2023 | GO2223015795PH | MVS | PH222371390M000 | Administrative Approval Issued | N/A | Yes | 49.94 | No | N/A | 28/12/2022
65 | MURSHIDABAD | Berhampur Division I | Lalgola | 10th(2022-2023) | New | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | TSM/017667 |  | 40053642 | 3 | 961 | 1042 | 1042 | 613.13 | 613.13 | Yes | 30/03/2023 | GO2223018091PH | MVS | PH222371467M000 | Administrative Approval Issued | N/A | Yes | 558.26 | No | N/A | 28/12/2022
66 | MURSHIDABAD | Berhampur Division I | Bhagawangola - II | 8th (2022-2023) | New | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | TSM/016515 |  | 40033392 | 3 | 8053 | 3022 | 3022 | 1308.69 | 1308.69 | Yes | 04/08/2023 | 2247/PHE-28011/102/2023-ESTT CELL-Dept. of PHE | MVS | PH222367557M000 | Administrative Approval Issued | N/A | Yes | 1064.18 | No | N/A | 30/09/2022
67 | MURSHIDABAD | Berhampur Division I | Raninagar - I | 7th (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | TSM/012745 | SM/01582 | 40036597 | 2 | 3765 | 1091 | 1091 | 1074.75 | 1074.75 | Yes | 26/07/2023 | 2049/PHE-28011/30/2023-ESTT CELL-Dept. of PHE | MVS | PH222365430M000 | Administrative Approval Issued | N/A | Yes | 110.29 | No | N/A | 26/09/2022
68 | MURSHIDABAD | Berhampur Division I | Lalgola | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) | SM/07687 | TSM/006395 | SM/00871 | 8362345 | 5 | 1965 | 1461 | 1461 | 99.51 | 99.51 | Yes | 07/01/2021 | GO2021004286PH | SVS |  | Administrative Approval Issued | N/A | Yes | 19.95 | No | N/A | 04/12/2020
69 | MURSHIDABAD | Berhampur Division I | Bhagawangola - I | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Telia Village (Code-314466) In The Command Area Of Telia Ground Water Supply Scheme (Part-B) | SM/07732 | TSM/006457 | SM/01944 | 8155597 | 1 | 2620 | 1906 | 1906 | 118.61 | 118.61 | Yes | 07/01/2021 | GO2021004268PH | SVS |  | Administrative Approval Issued | N/A | Yes | 95.85 | No | N/A | 04/12/2020
70 | MURSHIDABAD | Berhampur Division I | Bhagawangola - II | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Benipur (Code-314546) In The Command Area Of Benipur Ground Water Supply Scheme (Part-A) Under Bhagwangola-II Bloc | SM/07789 | TSM/006462 | SM/02521 | 1723443 | 1 | 2306 | 1738 | 1738 | 115.48 | 115.48 | Yes | 07/01/2021 | GO2021004215PH | SVS |  | Administrative Approval Issued | N/A | Yes | 78.84 | No | N/A | 04/12/2020
71 | MURSHIDABAD | Berhampur Division I | Bhagawangola - II | 4th (2020-2021) | Retrofitting | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Blo | SM/07790 | TSM/006463 | SM/02521 | 1723443 | 1 | 1574 | 1347 | 1349 | 89.83 | 89.83 | Yes | 07/01/2021 | GO2021004214PH | SVS |  | Administrative Approval Issued | N/A | Yes | 17.89 | No | N/A | 04/12/2020
72 | MURSHIDABAD | Berhampur Division I | Nawda | 11th(2021-2022) | New | MOKTARPUR PIPED WATER SUPPLY SCHEME | SM/11620 | TSM/010430 |  | 40026734 | 4 | 366 | 436 | 436 | 300.98 | 300.98 | Yes | 26/07/2022 | GO2223005563PH | MVS | PH222354836M000 | Administrative Approval Issued | N/A | Yes | 233.8 | No | N/A | 30/03/2022
73 | MURSHIDABAD | Berhampur Division I | Jalangi | 7th (2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | TSM/011836 | SM/01701 | 40033983 | 1 | 477 | 57 | 57 | 360.07 | 360.07 | Yes | 12/12/2022 | GO2223010881PH | SVS | PH222365396M000 | Administrative Approval Issued | N/A | Yes | 144.92 | No | N/A | 26/09/2022
74 | MURSHIDABAD | Berhampur Division I | Lalgola | 7th (2022-2023) | Augmentation | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | TSM/015869 | SM/01495 | 40035982 | 3 | 3250 | 1303 | 1303 | 649.29 | 649.29 | Yes | 20/01/2023 | GO2223012268PH | MVS | PH222365416M000 | Administrative Approval Issued | N/A | Yes | 448.37 | No | N/A | 26/09/2022
75 | MURSHIDABAD | Berhampur Division I | Lalgola | 7th (2022-2023) | Augmentation | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | TSM/014464 | SM/01484 | 40036005 | 3 | 1997 | 1100 | 1100 | 770.8 | 770.8 | Yes | 20/01/2023 | GO2223012261PH | MVS | PH222365421M000 | Administrative Approval Issued | N/A | Yes | 62.25 | No | N/A | 26/09/2022
76 | MURSHIDABAD | Berhampur Division I | Raninagar - II | 7th (2022-2023) | Augmentation | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14046 | TSM/016385 | SM/01748 | 40035346 | 4 | 4454 | 255 | 255 | 686.91 | 686.91 | Yes | 12/12/2022 | GO2223010890PH | MVS | PH222365380M000 | Administrative Approval Issued | N/A | Yes | 43.12 | No | N/A | 26/09/2022
Total | [10 empty] | 223 | 207448 | 171089 | 144823 | 31189.57 | 31189.57 | [8 empty] | 14831.29