## List of Scheme Sanctioned
List of Scheme Sanctioned (Rs. in Lakh)
SL No | District | Division | Block | SlSSC No. | Scheme Type | Scheme | Scheme SM Code | Scheme TSM code | Parent SM code | Sub Division | Name of AE entrusted | Name of JE entrusted | Nature of Source | Total Households | Approved FHTCs | Modified FHTCs | Estimated Cost | Modified Cost | Current Status | Current Position | AAFS code | Scheme coverage type | AAFS Date | AAFS No. | Tender Status | Tender Cost | WO Status | WO Cost | SlSSC Date
1 | UTTAR DINAJPUR | Raiganj Division | Chopra | 3rd (2020-2021) | Retrofitting | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte (SM/07977) | SM/07977 | TSM/006330 | SM/06039 | Raiganj Sub-Division |  | Junior Engineer, ISD ,Junior Engineer, RSD |  | 11012 | 9907 | 9907 | 502.08 | 502.08 | Administrative Approval Issued |  |  | MVS | 22/01/2021 | GO2021005144PH | Yes | 498.98 | No | N/A | 25/09/2020
2 | UTTAR DINAJPUR | Raiganj Division | Kaliaganj | 3rd (2020-2021) | Retrofitting | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block (SM/07072) | SM/07072 | TSM/006321 | SM/06051 | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD |  | 1466 | 1139 | 1139 | 60.91 | 60.91 | Administrative Approval Issued |  |  | MVS | 27/11/2020 | GO2021002848PH | Yes | 58.27 | No | N/A | 25/09/2020
3 | UTTAR DINAJPUR | Raiganj Division | Chopra | 3rd (2020-2021) | Retrofitting | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme (SM/07142) | SM/07142 | TSM/006323 | SM/06038 | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD |  | 2391 | 1788 | 1788 | 91.79 | 91.79 | Administrative Approval Issued |  |  | MVS | 27/11/2020 | GO2021002856PH | Yes | 86.38 | No | N/A | 25/09/2020
4 | UTTAR DINAJPUR | Raiganj Division | Chopra | 2nd (2021-2022) | Retrofitting | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. (SM/09181) | SM/09181 | TSM/009426 | SM/00274 | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD |  | 2187 | 388 | 388 | 25.2 | 25.2 | Administrative Approval Issued |  |  | SVS | 28/10/2021 | GO2122004579PH | Yes | 12.95 | No | N/A | 08/09/2021
5 | UTTAR DINAJPUR | Raiganj Division | Islampur | 1st (2021-2022) | Retrofitting | Laying of additional pipe line for retrofitting of Matikunda (Part-I/II) WSS for installation of FHTC. (SM/09130) | SM/09130 | TSM/009378 | SM/01136 | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD |  | 888 | 841 | 0 | 11.88 | 11.88 | Administrative Approval Issued |  |  | SVS | 29/10/2021 | GO2122004650PH | Yes | 7.89 | No | N/A | 19/08/2021
6 | UTTAR DINAJPUR | Raiganj Division | Karandighi | 2nd (2021-2022) | Retrofitting | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. (SM/09189) | SM/09189 | TSM/009434 | SM/00816 | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD |  | 3135 | 410 | 410 | 26.54 | 26.54 | Administrative Approval Issued |  |  | SVS | 28/10/2021 | GO2122004579PH | Yes | 25.78 | No | N/A | 08/09/2021
7 | UTTAR DINAJPUR | Raiganj Division | Raiganj | 1st (2021-2022) | Retrofitting | Laying of additional pipe line for retrofitting of Udaypur for installation of FHTC. (SM/09158) | SM/09158 | TSM/009403 | SM/02917 | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD |  | 3281 | 2715 | 0 | 15.69 | 15.69 | Administrative Approval Issued |  |  | SVS | 29/10/2021 | GO2122004652PH | Yes | 15.21 | No | N/A | 19/08/2021
8 | UTTAR DINAJPUR | Raiganj Division | Karandighi | 1st (2021-2022) | Retrofitting | Laying of additional pipe line for retrofitting of Choprabari WSS for installation of FHTC. (SM/09134) | SM/09134 | TSM/009382 | SM/05146 | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD |  | 1713 | 1452 | 0 | 1.42 | 1.42 | Administrative Approval Issued |  |  | SVS | 29/10/2021 | GO2122004650PH | Yes | 1.38 | No | N/A | 19/08/2021
9 | UTTAR DINAJPUR | Raiganj Division | Kaliaganj | 1st (2021-2022) | Retrofitting | Laying of additional pipe line for retrofitting of Baruna WSS for installation of FHTC. (SM/09142) | SM/09142 | TSM/009390 | SM/03697 | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD |  | 2368 | 1871 | 0 | 5.32 | 5.32 | Administrative Approval Issued |  |  | SVS | 29/10/2021 | GO2122004652PH | Yes | 5.16 | No | N/A | 19/08/2021
10 | UTTAR DINAJPUR | Raiganj Division | Kaliaganj | 1st (2021-2022) | Retrofitting | Laying of additional pipe line for retrofitting of Bheur WSS for installation of FHTC. (SM/09147) | SM/09147 | TSM/009395 | SM/03739 | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD |  | 3032 | 2440 | 0 | 9.09 | 9.09 | Administrative Approval Issued |  |  | SVS | 29/10/2021 | GO2122004652PH | Yes | 8.81 | No | N/A | 19/08/2021
11 | UTTAR DINAJPUR | Raiganj Division | Itahar | 1st (2021-2022) | Retrofitting | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). (SM/09111) | SM/09111 | TSM/009359 | SM/05002 | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD |  | 2901 | 2581 | 0 | 8.11 | 8.11 | Administrative Approval Issued |  |  | SVS | 29/10/2021 | GO2122004651PH | Yes | 8.44 | No | N/A | 19/08/2021
12 | UTTAR DINAJPUR | Raiganj Division | Chopra | 1st (2021-2022) | Retrofitting | Laying of additional pipe line for retrofitting of Ghirnigaonfor installation of FHTC. (SM/09122) | SM/09122 | TSM/009370 | SM/01360 | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD |  | 2540 | 2407 | 0 | 92.44 | 92.44 | Administrative Approval Issued |  |  | SVS | 29/10/2021 | GO2122004651PH | Yes | 83.58 | No | N/A | 19/08/2021
13 | UTTAR DINAJPUR | Raiganj Division | Raiganj | 10th(2021-2022) | Retrofitting | Restoration of Pipe line for providing FHTC for Maslandpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10463) | SM/10463 | TSM/010802 | SM/05022 | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | Ground Water | 1985 | 1776 | 0 | 7.55 | 7.55 | Administrative Approval Issued |  | PH222352138S000 | MVS | 13/04/2022 | GO2223000203PH | Yes | 7.33 | No | N/A | 16/03/2022
14 | UTTAR DINAJPUR | Raiganj Division | Chopra | 10th(2021-2022) | Augmentation | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. (SM/10545) | SM/10545 | TSM/010497 | SM/06037 | Islampur Sub-Division | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | Ground Water | 28749 | 26241 | 0 | 283.68 | 283.68 | Administrative Approval Issued |  | PH222352116S000 | MVS | 18/04/2022 | GO2223000358PH | Yes | 289.45 | No | N/A | 16/03/2022
15 | UTTAR DINAJPUR | Raiganj Division | Itahar | 10th(2021-2022) | Retrofitting | Restoration of Pipe line for providing FHTC for Shridharpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10442) | SM/10442 | TSM/010803 | SM/03590 | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | Ground Water | 3049 | 2483 | 0 | 7.8 | 7.8 | Administrative Approval Issued |  | PH222352158S000 | MVS | 12/04/2022 | GO2223000183PH | Yes | 4.68 | No | N/A | 16/03/2022
16 | UTTAR DINAJPUR | Raiganj Division | Raiganj | 10th(2021-2022) | Retrofitting | Restoration of Pipe Line for providing FHTC for Barua Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10448) | SM/10448 | TSM/010790 | SM/04984 | Raiganj Sub-Division | Assistant Engineer RSD |  | Ground Water | 1886 | 1871 | 0 | 11.31 | 11.31 | Administrative Approval Issued |  | PH222352173S000 | MVS | 11/04/2022 | GO2223000163PH | Yes | 10.91 | No | N/A | 16/03/2022
17 | UTTAR DINAJPUR | Raiganj Division | Itahar | 10th(2021-2022) | Retrofitting | Restoration of Pipe line for providing FHTC for Mahammadpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10444) | SM/10444 | TSM/010807 | SM/03752 | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | Ground Water | 1856 | 1651 | 0 | 10.7 | 10.7 | Administrative Approval Issued |  | PH222352165S000 | MVS | 12/04/2022 | GO2223000181PH | Yes | 9.08 | No | N/A | 16/03/2022
18 | UTTAR DINAJPUR | Raiganj Division | Chopra | 9th (2021-2022) | New | Mini Piped Water Supply Scheme for the Blocks of Chopra and Goalpokhar-II in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11520) | SM/11520 | TSM/010099 |  | Islampur Sub-Division | Assistant Engineer ISD |  | Ground Water | 1400 | 1632 | 1632 | 977.22 | 977.22 | Administrative Approval Issued |  | PH222354785S000 | MVS | 19/07/2022 | GO2223005217PH | Yes | 649.24 | No | N/A | 17/02/2022
19 | UTTAR DINAJPUR | Raiganj Division | Islampur | 10th(2021-2022) | Retrofitting | Restoration of Pipe Line for providing FHTC of Gunabari Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10426) | SM/10426 | TSM/010788 | SM/01911 | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD | Ground Water | 2472 | 2861 | 0 | 10.57 | 10.57 | Administrative Approval Issued |  | PH222352179S000 | SVS | 08/04/2022 | GO2223000145PH | Yes | 10.26 | No | N/A | 16/03/2022
20 | UTTAR DINAJPUR | Raiganj Division | Chopra | 5th (2022-2023) | Augmentation | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12647) | SM/12647 | TSM/015286 | SM/01360 | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 84 | 2271 | 100 | 52.37 | 52.37 | Administrative Approval Issued |  | PH222363650S000 | SVS | 19/09/2022 | GO2223007871PH | Yes | 46.25 | No | N/A | 22/08/2022
21 | UTTAR DINAJPUR | Raiganj Division | Raiganj | 3rd (2022-2023) | New | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12109) | SM/12109 | TSM/012037 |  | Raiganj Sub-Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | Ground Water | 2156 | 2257 | 2257 | 616.09 | 616.09 | Administrative Approval Issued |  | PH222361379S000 | MVS | 02/09/2022 | GO2223006968PH | Yes | 22.96 | No | N/A | 05/07/2022
22 | UTTAR DINAJPUR | Raiganj Division | Chopra | 4th (2022-2023) | New | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block (SM/12083) | SM/12083 | TSM/014313 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 821 | 967 | 967 | 378.6 | 378.6 | Administrative Approval Issued |  | PH222360976S000 | MVS | 02/09/2022 | GO2223007008PH | Yes | 323.63 | No | N/A | 15/07/2022
23 | UTTAR DINAJPUR | Raiganj Division | Raiganj | 2nd (2022-2023) | New | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. (SM/11961) | SM/11961 | TSM/011690 |  | Raiganj Sub-Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | Ground Water | 2063 | 2986 | 2986 | 583.28 | 583.28 | Administrative Approval Issued |  | PH222355553S000 | MVS | 25/08/2022 | GO2223006710PH | Yes | 545.95 | No | N/A | 20/05/2022
24 | UTTAR DINAJPUR | Raiganj Division | Goalpokhar - I | 5th (2022-2023) | New | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12786) | SM/12786 | TSM/014422 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 2112 | 2242 | 2242 | 549.05 | 549.05 | Administrative Approval Issued |  | PH222363560S000 | MVS | 20/09/2022 | GO2223007929PH | Yes | 466.59 | No | N/A | 22/08/2022
25 | UTTAR DINAJPUR | Raiganj Division | Raiganj | 2nd (2022-2023) | New | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. (SM/11865) | SM/11865 | TSM/011908 |  | Raiganj Sub-Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | Ground Water | 1870 | 1870 | 1870 | 639.64 | 639.64 | Administrative Approval Issued |  | PH222355594S000 | MVS | 17/08/2022 | GO2223006443PH | Yes | 65.55 | No | N/A | 20/05/2022
26 | UTTAR DINAJPUR | Raiganj Division | Karandighi | 1st(2022-2023) | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11794) | SM/11794 | TSM/011647 | SM/00647 | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 2455 | 1680 | 1680 | 671.75 | 671.75 | Administrative Approval Issued |  | PH222354657S000 | MVS | 05/08/2022 | GO2223006082PH | Yes | 332.76 | No | N/A | 25/04/2022
27 | UTTAR DINAJPUR | Raiganj Division | Chopra | 1st (2021-2022) | Retrofitting | Laying of additional pipe line for retrofitting of Barobilla for installation of FHTC. (SM/09135) | SM/09135 | TSM/009383 | SM/01863 | Islampur Sub-Division | Assistant Engineer ISD | Junior Engineer, ISD |  | 1527 | 1218 | 0 | 2.23 | 2.23 | Administrative Approval Issued |  |  | SVS | 29/10/2021 | GO2122004650PH | Yes | 2.17 | No | N/A | 19/08/2021
28 | UTTAR DINAJPUR | Raiganj Division | Goalpokhar - II | 6th (2022-2023) | New | BALDIABASA Piped Water Supply Scheme (SM/13234) | SM/13234 | TSM/015377 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 884 | 1362 | 1362 | 365.91 | 365.91 | Administrative Approval Issued |  | PH222364445S000 | MVS | 13/10/2022 | GO2223008695PH | Yes | 306.17 | No | N/A | 09/09/2022
29 | UTTAR DINAJPUR | Raiganj Division | Raiganj | 8th (2022-2023) | New | KOKRA Piped Water Supply Scheme (SM/14175) | SM/14175 | TSM/018226 |  | Raiganj Sub-Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | Ground Water | 1136 | 1199 | 1199 | 458.9 | 458.9 | Administrative Approval Issued |  | PH222366214S000 | MVS | 09/01/2023 | GO2223011729PH | Yes | 26.45 | No | N/A | 30/09/2022
30 | UTTAR DINAJPUR | Raiganj Division | Kaliaganj | 10th(2021-2022) | Retrofitting | Restoration of Pipe line for providing FHTC for Tungail Bilpara Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10465) | SM/10465 | TSM/010820 | SM/03707 | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | Ground Water | 2456 | 2463 | 0 | 5.97 | 5.97 | Administrative Approval Issued |  | PH222352195S000 | MVS | 13/04/2022 | GO2223000206PH | Yes | 5.79 | No | N/A | 16/03/2022
31 | UTTAR DINAJPUR | Raiganj Division | Karandighi | 9th (2022-2023) | New | KADERGANJ Pipe Water Supply Scheme (SM/15307) | SM/15307 | TSM/018390 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 1173 | 2492 | 2492 | 708.54 | 708.54 | Administrative Approval Issued |  | PH222372328S000 | MVS | 09/02/2023 | GO2223013662PH | Yes | 620.89 | No | N/A | 16/11/2022
32 | UTTAR DINAJPUR | Raiganj Division | Karandighi | 7th (2022-2023) | Augmentation | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME (SM/15125) | SM/15125 | TSM/011435 | SM/00816 | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 1857 | 2112 | 2112 | 529.35 | 529.35 | Administrative Approval Issued |  | PH222372110S000 | MVS | 04/02/2023 | GO2223013172PH | Yes | 12.03 | No | N/A | 26/09/2022
33 | UTTAR DINAJPUR | Raiganj Division | Goalpokhar - I | 7th (2022-2023) | Augmentation | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14232) | SM/14232 | TSM/016477 | SM/03914 | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 3421 | 50 | 50 | 49.54 | 49.54 | Administrative Approval Issued |  | PH222367933S000 | SVS | 10/01/2023 | GO2223011814PH | Yes | 68.05 | No | N/A | 26/09/2022
34 | UTTAR DINAJPUR | Raiganj Division | Goalpokhar - I | 7th (2022-2023) | New | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. (SM/16471) | SM/16471 | TSM/015388 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 933 | 1004 | 1004 | 359.95 | 359.95 | Administrative Approval Issued |  | PH222370558S000 | MVS | 02/03/2023 | GO2223015188PH | Yes | 72.08 | No | N/A | 26/09/2022
35 | UTTAR DINAJPUR | Raiganj Division | Karandighi | 5th (2022-2023) | New | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (SM/16536) | SM/16536 | TSM/015098 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 2096 | 3752 | 3752 | 1427.38 | 1427.38 | Administrative Approval Issued |  | PH222363039S000 | MVS | 10/03/2023 | GO2223015529PH | Yes | 32.85 | No | N/A | 22/08/2022
36 | UTTAR DINAJPUR | Raiganj Division | Hemtabad | 10th(2022-2023) | New | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/16224) | SM/16224 | TSM/018409 |  | Raiganj Sub-Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | Ground Water | 1665 | 1682 | 1682 | 812.41 | 812.41 | Administrative Approval Issued |  | PH222372544S000 | MVS | 23/02/2023 | GO2223014815PH | Yes | 24.49 | No | N/A | 28/12/2022
37 | UTTAR DINAJPUR | Raiganj Division | Itahar | 11th(2022-2023) | New | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18148) | SM/18148 | TSM/020903 |  | Malda Mechanical Division | Assistant Engineer - I | Junior Engineer-06 | Ground Water | 969 | 1035 | 1035 | 377.79 | 377.79 | Administrative Approval Issued |  | PH222375654S000 | MVS | 29/03/2023 | GO2223017903PH | Yes | 64 | No | N/A | 10/03/2023
38 | UTTAR DINAJPUR | Raiganj Division | Goalpokhar - I | 9th (2022-2023) | New | CHAPWA PIPED WATER SUPPLY SCHEME at GOALPOKHAR-I BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16647) | SM/16647 | TSM/018401 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 2101 | 2196 | 2196 | 631.02 | 631.02 | Administrative Approval Issued |  | PH222372317S000 | MVS | 14/03/2023 | GO2223015938PH | Yes | 437.12 | No | N/A | 16/11/2022
39 | UTTAR DINAJPUR | Raiganj Division | Itahar | 9th (2022-2023) | Augmentation | Augmentation of Kaliganj (Tharais village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. (SM/17741) | SM/17741 | TSM/018631 | SM/03585 | Raiganj Sub-Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | Ground Water | 529 | 482 | 482 | 169.13 | 169.13 | Administrative Approval Issued |  | PH222372908S000 | SVS | 17/03/2023 | GO2223016807PH | Yes | 95.12 | No | N/A | 16/11/2022
40 | UTTAR DINAJPUR | Raiganj Division | Goalpokhar - II | 8th (2022-2023) | New | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14166) | SM/14166 | TSM/017365 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 2235 | 3056 | 3056 | 865.82 | 865.82 | Administrative Approval Issued |  | PH222367494S000 | MVS | 05/01/2023 | GO2223011598PH | Yes | 746.27 | No | N/A | 30/09/2022
41 | UTTAR DINAJPUR | Raiganj Division | Hemtabad | 8th (2022-2023) | New | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. (SM/18298) | SM/18298 | TSM/017842 |  | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | Ground Water | 2118 | 2297 | 2297 | 1068.47 | 1068.47 | Administrative Approval Issued |  | PH222366270S000 | MVS | 26/06/2023 | 1667/PHE-28011/60/2023-SCHM CELL-Dept. of PHE | Yes | 22.59 | No | N/A | 30/09/2022
42 | UTTAR DINAJPUR | Raiganj Division | Karandighi | 9th (2022-2023) | New | BUDHRA PWSS (SM/19012) | SM/19012 | TSM/018370 |  |  |  |  | Ground Water | 1148 | 1680 | 1680 | 586.89 | 586.89 | Administrative Approval Issued |  | PH222372359S000 | MVS | 27/10/2023 | PHE/IV/3274/W-709/23 | Yes | 1433.22 | No | N/A | 16/11/2022
43 | UTTAR DINAJPUR | Raiganj Division | Itahar | 7th (2022-2023) | New | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/18341) | SM/18341 | TSM/016713 |  | Raiganj Sub-Division | Assistant Engineer RSD | Junior Engineer, RSD | Ground Water | 5996 | 5716 | 5716 | 2257.53 | 2257.53 | Administrative Approval Issued |  | PH222371920S000 | MVS | 04/07/2023 | 1749/PHE-28011/55/2023-SCHM CELL-Dept. of PHE | Yes | 83.95 | No | N/A | 26/09/2022
44 | UTTAR DINAJPUR | Raiganj Division | Goalpokhar - I | 5th (2022-2023) | New | BARA SINGHANATH Piped Water Supply Scheme (SM/12529) | SM/12529 | TSM/014476 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 1947 | 2136 | 2136 | 829.54 | 829.54 | Administrative Approval Issued |  | PH222363226S000 | MVS | 13/09/2022 | GO2223007530PH | Yes | 750.58 | No | N/A | 22/08/2022
45 | UTTAR DINAJPUR | Raiganj Division | Goalpokhar - I | 6th (2022-2023) | New | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. (SM/13456) | SM/13456 | TSM/015320 |  | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 2377 | 2656 | 2656 | 644.64 | 644.64 | Administrative Approval Issued |  | PH222364435S000 | MVS | 02/11/2022 | GO2223009195PH | Yes | 536.48 | No | N/A | 09/09/2022
46 | UTTAR DINAJPUR | Raiganj Division | Raiganj | 7th (2022-2023) | Augmentation | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME (SM/15124) | SM/15124 | TSM/011426 | SM/00897 | Raiganj Sub-Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | Ground Water | 2650 | 2906 | 2906 | 671.9 | 671.9 | Administrative Approval Issued |  | PH222372109S000 | MVS | 04/02/2023 | GO2223013178PH | Yes | 594.22 | No | N/A | 26/09/2022
47 | UTTAR DINAJPUR | Raiganj Division | Islampur | 9th (2021-2022) | New | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. (SM/11517) | SM/11517 | TSM/010111 |  | Islampur Sub-Division | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | Ground Water | 1549 | 1442 | 1442 | 975.54 | 975.54 | Administrative Approval Issued |  | PH222354769S000 | MVS | 19/07/2022 | GO2223005220PH | Yes | 746.03 | No | N/A | 17/02/2022
48 | UTTAR DINAJPUR | Raiganj Division | Goalpokhar - I | 5th (2022-2023) | Augmentation | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12655) | SM/12655 | TSM/015267 | SM/04503 | Islampur Sub-Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | Ground Water | 468 | 100 | 100 | 52.37 | 52.37 | Administrative Approval Issued |  | PH222363658S000 | SVS | 19/09/2022 | GO2223007868PH | Yes | 48.34 | No | N/A | 22/08/2022
Total | [13 empty] | 131107 | 123763 | 66721 | 19500.9 | 19500.9 | [7 empty] | 10326.36 |  | 15012.48