## FHTC correction
FHTC correction (Rs. in Lakh)
Sl No. | District | Scheme | Scheme SM Code | TSM Code | Scheme Type | Scheme coverage type | Is Scheme correction completed | FHTC approved | Increased | Decreased | FHTC Modified | Cost Clear | Increased | Decreased | Modified Cost
1 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | TSM/006569 | Retrofitting | SVS | Yes | 492 | 0 | 0 | 492 | 38.44 | 0 | 0 | 38.44
2 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mamudpur (314685) & Gobindapur (314687) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/07918 | TSM/006579 | Retrofitting | MVS | Yes | 992 | 0 | 0 | 992 | 79.52 | 0 | 0 | 79.52
3 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahammadpur ( 315549 ) of Mahammadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District ( PART-I ) | SM/07922 | TSM/006583 | Retrofitting | SVS | Yes | 1302 | 0 | 0 | 1302 | 105.77 | 0 | 0 | 105.77
4 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rampara Faridpur Village (Code-315664) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-B) | SM/07693 | TSM/006472 | Retrofitting | MVS | Yes | 1771 | 0 | 0 | 1771 | 131.51 | 0 | 0 | 131.51
5 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme | SM/06982 | TSM/006052 | Retrofitting | MVS | Yes | 1163 | 0 | 0 | 1163 | 71.77 | 0 | 0 | 71.77
6 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | TSM/006892 | Retrofitting | MVS | Yes | 14063 | 0 | 11529 | 2534 | 1011.33 | 0 | 0 | 1011.33
7 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Digha (VillageCode-314460) under command area under Digha ground water supply scheme (Part-A) | SM/06975 | TSM/006027 | Retrofitting | SVS | Yes | 1415 | 0 | 0 | 1415 | 86.87 | 0 | 0 | 86.87
8 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dighirpahar (314794) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-I) | SM/07282 | TSM/006104 | Retrofitting | SVS | Yes | 1325 | 0 | 0 | 1325 | 99.99 | 0 | 0 | 99.99
9 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Maiya Village (Code-314146) In The Command Area Of Maiya Ground Water Supply Scheme (Part-A) | SM/07734 | TSM/006451 | Retrofitting | SVS | Yes | 3290 | 0 | 60 | 3230 | 215.11 | 0 | 0 | 215.11
10 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme | SM/07228 | TSM/006054 | Retrofitting | MVS | Yes | 1195 | 0 | 60 | 1135 | 84.17 | 0 | 0 | 84.17
11 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV | SM/07283 | TSM/006108 | Retrofitting | SVS | Yes | 673 | 0 | 110 | 563 | 52.54 | 0 | 0 | 52.54
12 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Nandalalpur Arazi (314628) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshid | SM/07284 | TSM/006109 | Retrofitting | SVS | Yes | 1021 | 0 | 0 | 1021 | 74.76 | 0 | 0 | 74.76
13 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) | SM/07230 | TSM/006061 | Retrofitting | SVS | Yes | 1095 | 0 | 0 | 1095 | 74.26 | 0 | 0 | 74.26
14 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jafarganj (313809) of Andhua under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07296 | TSM/006140 | Retrofitting | SVS | Yes | 1261 | 0 | 0 | 1261 | 90.93 | 0 | 0 | 90.93
15 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) | SM/07767 | TSM/006538 | Retrofitting | SVS | Yes | 4077 | 0 | 0 | 4077 | 285.68 | 0 | 0 | 285.68
16 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dighirpar ( 314125 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PAR | SM/07508 | TSM/006543 | Retrofitting | SVS | Yes | 812 | 1 | 0 | 813 | 58.94 | 0 | 0 | 58.94
17 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) | SM/07768 | TSM/006544 | Retrofitting | SVS | Yes | 3864 | 0 | 0 | 3864 | 281.95 | 0 | 0 | 281.95
18 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Madhya Gobindopur (Code-314485), Maheshpur(Code-314486) In The Command Area Of Bhundar Kismat Ground Water Supply | SM/07794 | TSM/006467 | Retrofitting | MVS | Yes | 1195 | 0 | 0 | 1195 | 82.35 | 0 | 0 | 82.35
19 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bausi (Code-314208) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-B) | SM/07714 | TSM/006430 | Retrofitting | MVS | Yes | 1130 | 0 | 0 | 1130 | 79.62 | 0 | 0 | 79.62
20 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-I Ground Water Supply Scheme Under Nawda Block In Murshidabad District | SM/07721 | TSM/006517 | Retrofitting | SVS | Yes | 607 | 0 | 0 | 607 | 53.33 | 0 | 0 | 53.33
21 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) | SM/07771 | TSM/006549 | Retrofitting | SVS | Yes | 1516 | 0 | 0 | 1516 | 113.58 | 0 | 0 | 113.58
22 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs | SM/07773 | TSM/006553 | Retrofitting | MVS | Yes | 1840 | 0 | 42 | 1798 | 139.17 | 0 | 0 | 139.17
23 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part | SM/07889 | TSM/006515 | Retrofitting | MVS | Yes | 629 | 0 | 0 | 629 | 49.64 | 0 | 0 | 49.64
24 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kalmegha (Code-314221) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-D) Under Lalgola Block In | SM/07788 | TSM/006461 | Retrofitting | SVS | Yes | 1640 | 0 | 5 | 1635 | 99.99 | 0 | 0 | 99.99
25 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bhundar Kismat (Code-314468) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-A) Under Bhagw | SM/07793 | TSM/006466 | Retrofitting | SVS | Yes | 2308 | 0 | 1003 | 1305 | 157.17 | 0 | 0 | 157.17
26 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | TSM/006539 | Retrofitting | SVS | Yes | 6736 | 0 | 0 | 6736 | 480.62 | 0 | 0 | 480.62
27 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area | SM/08199 | TSM/006550 | Retrofitting | MVS | Yes | 5138 | 2639 | 0 | 7777 | 386.05 | 0 | 0 | 386.05
28 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | TSM/006556 | Retrofitting | SVS | Yes | 5019 | 0 | 0 | 5019 | 380.89 | 0 | 0 | 380.89
29 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu | SM/08899 | TSM/006432 | Retrofitting | SVS | Yes | 5674 | 3 | 0 | 5677 | 373.6 | 0 | 0 | 373.6
30 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kashipur Village (Code-315687), Jhikra Village (Code-315688) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-C) U | SM/08902 | TSM/006486 | Retrofitting | MVS | Yes | 4396 | 0 | 0 | 4396 | 304.14 | 0 | 0 | 304.14
31 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Haribhanga Daulatpur, Ramipur, Tekaraipur, Borakuli, Balumati (314785, 314786, 314788, 314789 & 314790) of Tekaraipara under Ground Water Based Water Supply Scheme | SM/08276 | TSM/006064 | Retrofitting | MVS | Yes | 4370 | 0 | 0 | 4370 | 342.72 | 0 | 0 | 342.72
32 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa | SM/08282 | TSM/006105 | Retrofitting | MVS | Yes | 6670 | 0 | 0 | 6670 | 497.66 | 0 | 0 | 497.66
33 | MURSHIDABAD | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad | SM/09743 | TSM/007541 | Retrofitting | SVS | Yes | 2145 | 0 | 0 | 2145 | 251.5 | 0 | 0 | 251.5
34 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II | SM/09746 | TSM/007507 | Retrofitting | MVS | Yes | 4417 | 0 | 0 | 4417 | 328.18 | 0 | 0 | 328.18
35 | MURSHIDABAD | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Bhagabanbati (315342) for Bara Satui under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block in Murshidabad District under Murshidabad Divisio | SM/11163 | TSM/008735 | Augmentation | MVS | Yes | 810 | 0 | 491 | 319 | 195.5 | 0 | 19.96 | 175.54
36 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I | SM/11164 | TSM/008638 | Augmentation | SVS | Yes | 3446 | 0 | 1759 | 1687 | 284.98 | 0 | 71.5 | 213.48
37 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Chandabad ( 315517 ) of Ghoramara under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad Di | SM/09837 | TSM/007494 | Retrofitting | SVS | Yes | 382 | 0 | 0 | 382 | 34.02 | 0 | 0 | 34.02
38 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh | SM/09844 | TSM/007502 | Retrofitting | SVS | Yes | 89 | 0 | 0 | 89 | 9.41 | 0 | 0 | 9.41
39 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Paraspur ( 314616 ) of Muradpur-Jalangi (Zone-I, Zone - II & Zone - III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block o | SM/09845 | TSM/007503 | Retrofitting | SVS | Yes | 192 | 0 | 0 | 192 | 16.64 | 0 | 0 | 16.64
40 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | SM/09764 | TSM/007531 | Retrofitting | SVS | Yes | 4333 | 0 | 0 | 4333 | 313.08 | 0 | 0 | 313.08
41 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Keyadanga ( 313966 ) of Keyadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District under Murshida | SM/09849 | TSM/007509 | Retrofitting | SVS | Yes | 569 | 330 | 0 | 899 | 44.53 | 0 | 0 | 44.53
42 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | TSM/010305 | Augmentation | SVS | Yes | 1905 | 0 | 563 | 1342 | 498.55 | 0 | 22.89 | 475.66
43 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10628 | TSM/010307 | Augmentation | SVS | Yes | 3349 | 0 | 2849 | 500 | 999.92 | 0 | 0 | 999.92
44 | MURSHIDABAD | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11714 | TSM/011685 | Augmentation | MVS | Yes | 5532 | 0 | 3028 | 2504 | 907.4 | 0 | 0 | 907.4
45 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | TSM/011667 | Augmentation | MVS | Yes | 1521 | 345 | 0 | 1866 | 698.71 | 0 | 0 | 698.71
46 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | TSM/011696 | Augmentation | SVS | Yes | 373 | 0 | 0 | 373 | 442.96 | 0 | 0 | 442.96
47 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | TSM/011681 | Augmentation | SVS | Yes | 212 | 0 | 0 | 212 | 188.66 | 0 | 0 | 188.66
48 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11563 | TSM/010759 | Augmentation | MVS | Yes | 3136 | 0 | 1479 | 1657 | 993.35 | 0 | 60.12 | 933.23
49 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11564 | TSM/010384 | Augmentation | MVS | Yes | 6648 | 0 | 4389 | 2259 | 949.24 | 0 | 0 | 949.24
50 | MURSHIDABAD | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | TSM/010176 | New | MVS | Yes | 81085 | 0 | 5549 | 75536 | 33305.51 | 0 | 0 | 33305.51
51 | MURSHIDABAD | ANDULIA AND ADJOININNG MOUJAS PWSS | SM/13723 | TSM/014892 | New | MVS | Yes | 3482 | 0 | 0 | 3482 | 821.59 | 0 | 0 | 821.59
52 | MURSHIDABAD | BRAHMANDIHI AND ADJOINING MOUJAS PWSS | SM/13729 | TSM/014712 | New | MVS | Yes | 2931 | 0 | 0 | 2931 | 758.82 | 0 | 0 | 758.82
53 | MURSHIDABAD | JASOHARI PIPE WATER SUPPLY SCHEME. | SM/13728 | TSM/014468 | New | MVS | Yes | 2016 | 0 | 0 | 2016 | 478.24 | 0 | 0 | 478.24
54 | MURSHIDABAD | GARULIA AND IT'S ADJOINING MOUJAS PWSS | SM/13924 | TSM/015349 | New | MVS | Yes | 3016 | 0 | 0 | 3016 | 770.8 | 0 | 0 | 770.8
55 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13927 | TSM/015221 | Augmentation | MVS | Yes | 2530 | 0 | 1695 | 835 | 758.89 | 0 | 68.9 | 689.98
56 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand | SM/08191 | TSM/006093 | Retrofitting | MVS | Yes | 4430 | 179 | 0 | 4609 | 333.13 | 0 | 0 | 333.13
57 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . | SM/14050 | TSM/011837 | Augmentation | SVS | Yes | 86 | 0 | 0 | 86 | 202.23 | 0 | 0 | 202.23
58 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14832 | TSM/017199 | Augmentation | MVS | Yes | 2519 | 0 | 465 | 2054 | 821.37 | 0 | 18.9 | 802.47
59 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. | SM/14070 | TSM/017303 | Augmentation | MVS | Yes | 810 | 0 | 0 | 810 | 507.83 | 0 | 0 | 507.83
60 | MURSHIDABAD | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | TSM/017832 | Augmentation | MVS | Yes | 1469 | 0 | 0 | 1469 | 980.83 | 0 | 0 | 980.83
61 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | TSM/011699 | Augmentation | MVS | Yes | 558 | 0 | 0 | 558 | 624.73 | 0 | 0 | 624.73
62 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | TSM/012748 | Augmentation | MVS | Yes | 954 | 0 | 0 | 954 | 915.51 | 0 | 0 | 915.51
63 | MURSHIDABAD | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | TSM/015361 | New | MVS | Yes | 1447 | 0 | 0 | 1447 | 569.98 | 0 | 0 | 569.98
64 | MURSHIDABAD | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | TSM/017326 | New | SVS | Yes | 1536 | 0 | 0 | 1536 | 828.25 | 0 | 0 | 828.25
65 | MURSHIDABAD | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. | SM/15067 | TSM/017540 | Augmentation | SVS | Yes | 2416 | 0 | 0 | 2416 | 959.55 | 0 | 0 | 959.55
66 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/16241 | TSM/017816 | Augmentation | SVS | Yes | 329 | 0 | 0 | 329 | 291.78 | 0 | 0 | 291.78
67 | MURSHIDABAD | Augmentation of Jaykrishnapur Zone-II piped water supply scheme in Samserganj Block in the District of Murshidabad. | SM/16245 | TSM/018903 | Augmentation | SVS | Yes | 557 | 0 | 0 | 557 | 657.87 | 0 | 0 | 657.87
68 | MURSHIDABAD | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | TSM/019377 | Augmentation | SVS | Yes | 1183 | 0 | 0 | 1183 | 855.97 | 0 | 0 | 855.97
69 | MURSHIDABAD | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. | SM/15836 | TSM/015222 | Augmentation | SVS | Yes | 890 | 0 | 885 | 5 | 762.57 | 0 | 35.98 | 726.59
70 | MURSHIDABAD | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16278 | TSM/016067 | New | MVS | Yes | 2500 | 0 | 0 | 2500 | 702.59 | 0 | 0 | 702.59
71 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone- III, Block- Lalgola, District- Murshidabad. | SM/16434 | TSM/017985 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
72 | MURSHIDABAD | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16442 | TSM/019528 | New | SVS | Yes | 252 | 0 | 0 | 252 | 81.23 | 0 | 0 | 81.23
73 | MURSHIDABAD | GOPJAN(P) PIPED WATER SUPPLY SCHEME, BLOCK- BERHAMPORE , DISTRICT- MURSHIDABAD. | SM/16444 | TSM/019383 | New | SVS | Yes | 120 | 0 | 0 | 120 | 40.62 | 0 | 0 | 40.62
74 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HARUA PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16545 | TSM/016025 | Augmentation | MVS | Yes | 5674 | 0 | 1288 | 4386 | 889.36 | 0 | 52.36 | 837
75 | MURSHIDABAD | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-B) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16554 | TSM/017308 | Augmentation | MVS | Yes | 526 | 42 | 0 | 568 | 302 | 0 | 0 | 302
76 | MURSHIDABAD | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | TSM/015747 | New | MVS | Yes | 1624 | 0 | 0 | 1624 | 758.25 | 0 | 0 | 758.25
77 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16455 | TSM/016103 | Augmentation | SVS | Yes | 257 | 0 | 255 | 2 | 779.3 | 0 | 10.37 | 768.93
78 | MURSHIDABAD | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16112 | TSM/017595 | New | SVS | Yes | 565 | 0 | 0 | 565 | 226.02 | 0 | 0 | 226.02
79 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16407 | TSM/017461 | Augmentation | MVS | Yes | 1917 | 0 | 1704 | 213 | 969.05 | 0 | 69.27 | 899.78
80 | MURSHIDABAD | Augmentation of BHASIPAIKAR ZONE-IIB piped water supply scheme in Samserganj Block in the District of Murshidabad. | SM/16171 | TSM/018901 | Augmentation | SVS | Yes | 967 | 0 | 0 | 967 | 819.74 | 0 | 0 | 819.74
81 | MURSHIDABAD | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | TSM/017327 | New | SVS | Yes | 1493 | 0 | 0 | 1493 | 856.53 | 0 | 0 | 856.53
82 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Lahari, Block- Bhagwangola-II, District- Murshidabad. | SM/16213 | TSM/017946 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
83 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas | SM/08279 | TSM/006074 | Retrofitting | MVS | Yes | 4436 | 0 | 47 | 4389 | 340.16 | 0 | 0 | 340.16
84 | MURSHIDABAD | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. | SM/16417 | TSM/018276 | Augmentation | MVS | Yes | 2889 | 0 | 0 | 2889 | 709.24 | 0 | 0 | 709.24
85 | MURSHIDABAD | Augmentation of Basudevpur Zone-II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/16180 | TSM/015933 | Augmentation | MVS | Yes | 931 | 0 | 280 | 651 | 591.55 | 0 | 11.38 | 580.17
86 | MURSHIDABAD | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16395 | TSM/017523 | New | MVS | Yes | 909 | 0 | 0 | 909 | 246.58 | 0 | 0 | 246.58
87 | MURSHIDABAD | BAHARAGACHI PIPE WATER SUPPLY SCHEME. | SM/15939 | TSM/016503 | New | MVS | Yes | 857 | 0 | 0 | 857 | 719.97 | 0 | 0 | 719.97
88 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED MADNA ZONE II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15917 | TSM/016005 | Augmentation | MVS | Yes | 2071 | 0 | 681 | 1390 | 998.29 | 0 | 27.68 | 970.61
89 | MURSHIDABAD | BASANTAPUR AND ADJOINING MOUJAS PWSS | SM/15940 | TSM/015832 | New | MVS | Yes | 417 | 0 | 0 | 417 | 161.21 | 0 | 0 | 161.21
90 | MURSHIDABAD | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | TSM/016504 | New | SVS | Yes | 1358 | 0 | 0 | 1358 | 824.91 | 0 | 0 | 824.91
91 | MURSHIDABAD | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16424 | TSM/018269 | Augmentation | MVS | Yes | 931 | 0 | 0 | 931 | 528.16 | 0 | 0 | 528.16
92 | MURSHIDABAD | Augmentation of Bhasaipaikar Zone-IB piped water supply scheme in Samserganj Block in the District of Murshidabad. | SM/16169 | TSM/018900 | Augmentation | SVS | Yes | 150 | 0 | 0 | 150 | 832.44 | 0 | 0 | 832.44
93 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | TSM/018237 | Augmentation | MVS | Yes | 3268 | 0 | 0 | 3268 | 975.16 | 0 | 0 | 975.16
94 | MURSHIDABAD | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. | SM/15747 | TSM/018305 | Augmentation | MVS | Yes | 797 | 0 | 0 | 797 | 534.48 | 0 | 0 | 534.48
95 | MURSHIDABAD | DAKSHIN RAYPUR AND ADJOINING MOUJAS PWSS | SM/15942 | TSM/015947 | New | MVS | Yes | 1428 | 177 | 0 | 1605 | 540.51 | 0 | 0 | 540.51
96 | MURSHIDABAD | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IX & X )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16672 | TSM/014929 | Retrofitting | MVS | Yes | 12105 | 0 | 0 | 12105 | 998.65 | 0 | 0 | 998.65
97 | MURSHIDABAD | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | TSM/015605 | Augmentation | SVS | Yes | 833 | 0 | 831 | 2 | 981.89 | 0 | 33.78 | 948.1
98 | MURSHIDABAD | DIAR FATEPUR PWSS | SM/16781 | TSM/017637 | New | SVS | Yes | 3118 | 0 | 0 | 3118 | 915.29 | 0 | 0 | 915.29
99 | MURSHIDABAD | SHUKUR PUKUR PWSS | SM/16782 | TSM/017611 | New | SVS | Yes | 601 | 0 | 0 | 601 | 391.07 | 0 | 0 | 391.07
100 | MURSHIDABAD | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16863 | TSM/018267 | Augmentation | MVS | Yes | 1085 | 0 | 0 | 1085 | 556.98 | 0 | 0 | 556.98
101 | MURSHIDABAD | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS | SM/16816 | TSM/017593 | New | MVS | Yes | 1183 | 0 | 0 | 1183 | 549.36 | 0 | 0 | 549.36
102 | MURSHIDABAD | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/17389 | TSM/018308 | Augmentation | SVS | Yes | 2062 | 0 | 0 | 2062 | 563.21 | 0 | 0 | 563.21
103 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Alikpur Village (Code-315626), Mashimpur Village (Code-315627), Sekandarpur (Code-315628) Under Command Area Of Mashimpur Ground | SM/07720 | TSM/006514 | Retrofitting | MVS | Yes | 1199 | 0 | 0 | 1199 | 92.89 | 0 | 0 | 92.89
104 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18543 | TSM/018626 | Augmentation | SVS | Yes | 594 | 4027 | 0 | 4621 | 1120.71 | 0 | 0 | 1120.71
105 | MURSHIDABAD | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | TSM/017640 | New | MVS | Yes | 4831 | 0 | 0 | 4831 | 1544.31 | 0 | 0 | 1544.31
106 | MURSHIDABAD | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, | SM/18775 | TSM/016898 | Augmentation | MVS | Yes | 4236 | 0 | 250 | 3986 | 1549.76 | 0 | 0 | 1549.76
107 | MURSHIDABAD | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/18777 | TSM/017547 | Augmentation | SVS | Yes | 2933 | 0 | 1018 | 1915 | 1121.12 | 0 | 0 | 1121.12
108 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. | SM/19122 | TSM/017809 | Augmentation | MVS | Yes | 2091 | 0 | 0 | 2091 | 1550.75 | 0 | 0 | 1550.75
109 | MURSHIDABAD | Augmentation of Jot Kamal Zone-III Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/18471 | TSM/016614 | Augmentation | SVS | Yes | 2622 | 0 | 0 | 2622 | 1118.46 | 0 | 0 | 1118.46
110 | MURSHIDABAD | Source Augumentation& Functional Household Tap Connections (FHTC) of Mouza Radhakrishanapur, Malatipur, Khalifabaj, Sahabazpur, Paharpur, Krishnapur (314148, 314149, 314150, 314151, 314153 ) of Lalgola Under Ground Water Based Water Supply Scheme For Arse | SM/19019 | TSM/008711 | Augmentation | MVS | Yes | 9966 | 0 | 0 | 9966 | 872.83 | 0 | 0 | 872.83
111 | MURSHIDABAD | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | TSM/017955 | New | SVS | Yes | 3715 | 0 | 0 | 3715 | 1348.64 | 0 | 0 | 1348.64
112 | MURSHIDABAD | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. | SM/18687 | TSM/017522 | New | MVS | Yes | 2619 | 0 | 0 | 2619 | 1027.21 | 0 | 0 | 1027.21
113 | MURSHIDABAD | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME | SM/16398 | TSM/016077 | Augmentation | SVS | Yes | 560 | 459 | 0 | 1019 | 422.27 | 0 | 0 | 422.27
114 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | TSM/017812 | Augmentation | MVS | Yes | 1263 | 0 | 0 | 1263 | 2130.14 | 0 | 0 | 2130.14
115 | MURSHIDABAD | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | TSM/016004 | Augmentation | MVS | Yes | 1095 | 0 | 0 | 1095 | 1478.49 | 0 | 0 | 1478.49
116 | MURSHIDABAD | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | TSM/017609 | Augmentation | MVS | Yes | 32512 | 0 | 0 | 32512 | 38369 | 0 | 0 | 38369
117 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pirojpur & Madhurkol (314723 & 314724) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/07913 | TSM/006573 | Retrofitting | SVS | Yes | 1234 | 0 | 0 | 1234 | 96.61 | 0 | 0 | 96.61
118 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Komnagar ground water supply scheme | SM/07223 | TSM/006033 | Retrofitting | SVS | Yes | 882 | 0 | 0 | 882 | 59.03 | 0 | 0 | 59.03
119 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sitesnagar ground water supply scheme | SM/07226 | TSM/006049 | Retrofitting | SVS | Yes | 1410 | 0 | 0 | 1410 | 87.91 | 0 | 0 | 87.91
120 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07925 | TSM/006710 | Retrofitting | MVS | Yes | 0 | 241 | 0 | 241 | 69.2 | 0 | 0 | 69.2
121 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Balbalpara (313852) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) | SM/07511 | TSM/006555 | Retrofitting | SVS | Yes | 821 | 0 | 0 | 821 | 62.34 | 0 | 0 | 62.34
122 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07672 | TSM/006137 | Retrofitting | SVS | Yes | 2133 | 0 | 0 | 2133 | 161.68 | 0 | 0 | 161.68
123 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block | SM/07677 | TSM/006076 | Retrofitting | MVS | Yes | 3431 | 0 | 0 | 3431 | 248.75 | 0 | 0 | 248.75
124 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/07678 | TSM/006077 | Retrofitting | SVS | Yes | 1332 | 0 | 0 | 1332 | 109.83 | 0 | 0 | 109.83
125 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Gr | SM/07688 | TSM/006412 | Retrofitting | SVS | Yes | 1471 | 116 | 0 | 1587 | 98.85 | 0 | 0 | 98.85
126 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr | SM/07691 | TSM/006429 | Retrofitting | SVS | Yes | 1206 | 1 | 0 | 1207 | 84.54 | 0 | 0 | 84.54
127 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District | SM/07273 | TSM/006040 | Retrofitting | SVS | Yes | 507 | 0 | 0 | 507 | 44.21 | 0 | 0 | 44.21
128 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District | SM/07200 | TSM/006072 | Retrofitting | SVS | Yes | 731 | 0 | 0 | 731 | 57.01 | 0 | 0 | 57.01
129 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of | SM/07279 | TSM/006100 | Retrofitting | MVS | Yes | 773 | 67 | 0 | 840 | 68.99 | 0 | 0 | 68.99
130 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Opar Orahar (Code-314444) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-A) | SM/07729 | TSM/006439 | Retrofitting | SVS | Yes | 959 | 0 | 0 | 959 | 64.96 | 0 | 0 | 64.96
131 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme | SM/06980 | TSM/006034 | Retrofitting | MVS | Yes | 1274 | 1 | 0 | 1275 | 80.61 | 0 | 0 | 80.61
132 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-II ground water supply scheme | SM/07231 | TSM/006065 | Retrofitting | MVS | Yes | 1069 | 0 | 0 | 1069 | 71.2 | 0 | 0 | 71.2
133 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpu | SM/07698 | TSM/006484 | Retrofitting | MVS | Yes | 1363 | 0 | 0 | 1363 | 95.9 | 0 | 0 | 95.9
134 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B | SM/07287 | TSM/006113 | Retrofitting | MVS | Yes | 984 | 0 | 0 | 984 | 72.14 | 0 | 0 | 72.14
135 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) | SM/07908 | TSM/006567 | Retrofitting | SVS | Yes | 822 | 0 | 0 | 822 | 63.81 | 0 | 0 | 63.81
136 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | TSM/006039 | Retrofitting | MVS | Yes | 1315 | 0 | 2 | 1313 | 121.53 | 0 | 0 | 121.53
137 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bewa (P) (313794) of Bewa-II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07665 | TSM/006084 | Retrofitting | SVS | Yes | 2805 | 0 | 0 | 2805 | 197.42 | 0 | 0 | 197.42
138 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | TSM/006545 | Retrofitting | SVS | Yes | 2369 | 0 | 0 | 2369 | 173.5 | 0 | 0 | 173.5
139 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ahiron (313929) of Ahiron under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - I Block of Murshidabad District (PART-I) | SM/07675 | TSM/006060 | Retrofitting | SVS | Yes | 2377 | 0 | 0 | 2377 | 173.36 | 0 | 0 | 173.36
140 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnag | SM/07694 | TSM/006474 | Retrofitting | MVS | Yes | 1290 | 0 | 0 | 1290 | 83.34 | 0 | 0 | 83.34
141 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part | SM/07718 | TSM/006512 | Retrofitting | MVS | Yes | 1238 | 0 | 0 | 1238 | 93.76 | 0 | 0 | 93.76
142 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P | SM/07772 | TSM/006551 | Retrofitting | MVS | Yes | 3920 | 3 | 0 | 3923 | 295.16 | 0 | 0 | 295.16
143 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi | SM/07774 | TSM/006554 | Retrofitting | SVS | Yes | 2712 | 0 | 0 | 2712 | 205.5 | 0 | 0 | 205.5
144 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maheshpur (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block I | SM/07890 | TSM/006900 | Retrofitting | MVS | Yes | 2141 | 2442 | 0 | 4583 | 173.44 | 0 | 0 | 173.44
145 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A | SM/08184 | TSM/006045 | Retrofitting | MVS | Yes | 5031 | 0 | 0 | 5031 | 376.23 | 0 | 0 | 376.23
146 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur | SM/08194 | TSM/006141 | Retrofitting | MVS | Yes | 6073 | 0 | 0 | 6073 | 442.13 | 0 | 0 | 442.13
147 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Aurangabad (313981) of Aurangabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District (PART-I) | SM/08275 | TSM/006062 | Retrofitting | SVS | Yes | 7747 | 0 | 0 | 7747 | 558.86 | 0 | 0 | 558.86
148 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas | SM/08278 | TSM/006068 | Retrofitting | MVS | Yes | 6499 | 1 | 0 | 6500 | 517.99 | 0 | 0 | 517.99
149 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | TSM/006885 | Retrofitting | MVS | Yes | 9759 | 0 | 3500 | 6259 | 717.96 | 0 | 0 | 717.96
150 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | TSM/006888 | Retrofitting | MVS | Yes | 11888 | 0 | 4268 | 7620 | 870.99 | 0 | 0 | 870.99
151 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09739 | TSM/007536 | Retrofitting | SVS | Yes | 1216 | 0 | 0 | 1216 | 96.99 | 0 | 0 | 96.99
152 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Pakamati Mahula ( 315353 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under | SM/09740 | TSM/007537 | Retrofitting | SVS | Yes | 95 | 0 | 0 | 95 | 9.7 | 0 | 0 | 9.7
153 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bamuha (313962) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad D | SM/09759 | TSM/007525 | Retrofitting | SVS | Yes | 845 | 0 | 0 | 845 | 64.56 | 0 | 0 | 64.56
154 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Maradighi ( 315674 ) of Rejinagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh | SM/09839 | TSM/007497 | Retrofitting | SVS | Yes | 205 | 0 | 0 | 205 | 17.46 | 0 | 0 | 17.46
155 | MURSHIDABAD | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph | SM/10606 | TSM/010396 | Retrofitting | MVS | Yes | 7626 | 0 | 0 | 7626 | 575.23 | 0 | 0 | 575.23
156 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10610 | TSM/010733 | Augmentation | MVS | Yes | 2487 | 0 | 1597 | 890 | 567.92 | 0 | 64.92 | 503
157 | MURSHIDABAD | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | TSM/008708 | Augmentation | MVS | Yes | 4872 | 620 | 0 | 5492 | 962.13 | 0 | 0 | 962.13
158 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | TSM/010300 | Augmentation | MVS | Yes | 2601 | 0 | 2250 | 351 | 607.53 | 0 | 91.46 | 516.07
159 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | TSM/010732 | Augmentation | MVS | Yes | 2366 | 0 | 2000 | 366 | 567.12 | 0 | 81.3 | 485.82
160 | MURSHIDABAD | Source Augmentation of Functional Household Tap Connections (FHTC) of Mouza Habaspur (314487) of Habaspur under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Bhagwangola-I Block of Murshidabad District Under Murshidabad Division Phe | SM/11162 | TSM/008699 | Augmentation | SVS | Yes | 4287 | 0 | 0 | 4287 | 480.32 | 0 | 0 | 480.32
161 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10679 | TSM/010313 | Augmentation | MVS | Yes | 4394 | 0 | 1551 | 2843 | 989.12 | 0 | 63.05 | 926.07
162 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | TSM/011872 | Augmentation | MVS | Yes | 2310 | 0 | 0 | 2310 | 902.24 | 0 | 0 | 902.24
163 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-II BLOCK-RAGHUNATHGANJ- II | SM/10797 | TSM/008623 | Augmentation | MVS | Yes | 6695 | 0 | 1627 | 5068 | 762.78 | 0 | 68.45 | 694.32
164 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | TSM/011876 | Augmentation | MVS | Yes | 349 | 0 | 0 | 349 | 354.9 | 0 | 0 | 354.9
165 | MURSHIDABAD | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Sinkaipur (314775) of Azamatpur Ground water based water supply scheme for arsenic affected areas of Raninagar - I Block in Murshidabad District under Murshidabad Division, P.H.E.D | SM/11219 | TSM/008702 | Augmentation | MVS | Yes | 89 | 0 | 87 | 2 | 72.82 | 0 | 3.54 | 69.28
166 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | TSM/010771 | Augmentation | MVS | Yes | 6204 | 0 | 5495 | 709 | 936.21 | 0 | 0 | 936.21
167 | MURSHIDABAD | NABADURGA AND ADJOINING MOUJAS PWSS | SM/13934 | TSM/015567 | New | MVS | Yes | 2909 | 0 | 0 | 2909 | 917.51 | 0 | 0 | 917.51
168 | MURSHIDABAD | MUNIGRAM AND ADJOINING MOUJAS PWSS | SM/13935 | TSM/015026 | New | MVS | Yes | 1029 | 0 | 0 | 1029 | 389.65 | 0 | 0 | 389.65
169 | MURSHIDABAD | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | TSM/014741 | New | MVS | Yes | 2086 | 0 | 0 | 2086 | 695.52 | 0 | 0 | 695.52
170 | MURSHIDABAD | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | TSM/015857 | Augmentation | SVS | Yes | 300 | 0 | 0 | 300 | 797.62 | 0 | 0 | 797.62
171 | MURSHIDABAD | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | TSM/014545 | New | MVS | Yes | 4166 | 0 | 0 | 4166 | 938.24 | 0 | 0 | 938.24
172 | MURSHIDABAD | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | TSM/015998 | Augmentation | MVS | Yes | 653 | 0 | 0 | 653 | 591.27 | 0 | 0 | 591.27
173 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SYPPLY SCHEME FOR KANKURIA JAFRABAD ZONE-II BLOCK SAMSERGANJ DIST - MURSHIDABAD. | SM/13114 | TSM/010563 | Augmentation | MVS | Yes | 7140 | 0 | 4713 | 2427 | 1270.06 | 0 | 0 | 1270.06
174 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | TSM/015132 | Augmentation | MVS | Yes | 1473 | 0 | 439 | 1034 | 564.45 | 0 | 17.85 | 546.61
175 | MURSHIDABAD | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | TSM/015293 | Augmentation | MVS | Yes | 919 | 0 | 0 | 919 | 739.79 | 0 | 0 | 739.79
176 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | TSM/011842 | Augmentation | SVS | Yes | 312 | 0 | 0 | 312 | 662.31 | 0 | 0 | 662.31
177 | MURSHIDABAD | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/14722 | TSM/014187 | Augmentation | MVS | Yes | 1558 | 0 | 0 | 1558 | 820.33 | 0 | 0 | 820.33
178 | MURSHIDABAD | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III | SM/15231 | TSM/017872 | Augmentation | SVS | Yes | 330 | 0 | 0 | 330 | 527.09 | 0 | 0 | 527.09
179 | MURSHIDABAD | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | TSM/017576 | Augmentation | MVS | Yes | 385 | 0 | 0 | 385 | 969.51 | 0 | 0 | 969.51
180 | MURSHIDABAD | BATHUR AND ADJOINING MOUJAS PWSS | SM/15265 | TSM/015179 | New | MVS | Yes | 547 | 0 | 0 | 547 | 206.5 | 0 | 0 | 206.5
181 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | TSM/011844 | Augmentation | SVS | Yes | 721 | 0 | 0 | 721 | 546.4 | 0 | 0 | 546.4
182 | MURSHIDABAD | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | TSM/015232 | New | MVS | Yes | 3817 | 0 | 0 | 3817 | 973.05 | 0 | 0 | 973.05
183 | MURSHIDABAD | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | TSM/014460 | New | MVS | Yes | 1930 | 0 | 0 | 1930 | 558.72 | 0 | 0 | 558.72
184 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | TSM/016373 | Augmentation | MVS | Yes | 664 | 84 | 0 | 748 | 933.72 | 0 | 0 | 933.72
185 | MURSHIDABAD | KUMAR SANDA AND ADJOINING MOUJAS PWSS | SM/14238 | TSM/014647 | New | MVS | Yes | 4073 | 0 | 0 | 4073 | 1000.77 | 0 | 0 | 1000.77
186 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | TSM/010309 | Augmentation | MVS | Yes | 823 | 0 | 0 | 823 | 715.32 | 0 | 0 | 715.32
187 | MURSHIDABAD | PETARI AND ADJOINING MOUJAS PWSS | SM/14237 | TSM/014932 | New | MVS | Yes | 2616 | 0 | 0 | 2616 | 1012.65 | 0 | 0 | 1012.65
188 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. | SM/16427 | TSM/017737 | Augmentation | MVS | Yes | 1143 | 20 | 0 | 1163 | 687.2 | 0 | 0 | 687.2
189 | MURSHIDABAD | Mini piped water supply scheme (maximum 100 households) Village-Char Halalpur Zone-IV, Block-Berhampore, District- Murshidabad. | SM/16433 | TSM/018011 | New | SVS | Yes | 28 | 0 | 0 | 28 | 31.51 | 0 | 0 | 31.51
190 | MURSHIDABAD | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAR NARAYANPUR , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. | SM/16441 | TSM/013372 | New | SVS | Yes | 78 | 0 | 0 | 78 | 38.14 | 0 | 0 | 38.14
191 | MURSHIDABAD | SEHALAI PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-I , DISTRICT- MURSHIDABAD. | SM/16443 | TSM/019536 | New | SVS | Yes | 244 | 0 | 0 | 244 | 81.23 | 0 | 0 | 81.23
192 | MURSHIDABAD | SERPUR (CT) PIPE WATER SUPPLY SCHEME. | SM/16481 | TSM/016496 | New | SVS | Yes | 2187 | 114 | 0 | 2301 | 938.46 | 0 | 0 | 938.46
193 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. | SM/16176 | TSM/017803 | Augmentation | SVS | Yes | 68 | 0 | 0 | 68 | 133.85 | 0 | 0 | 133.85
194 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. | SM/15638 | TSM/013098 | Augmentation | SVS | Yes | 2004 | 0 | 1018 | 986 | 827.89 | 0 | 41.38 | 786.5
195 | MURSHIDABAD | Mini piped water supply scheme (maximum 100 households) Village-Sonadiar Zone-I, Block-Berhampore, District- Murshidabad. | SM/16500 | TSM/017951 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
196 | MURSHIDABAD | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16173 | TSM/018059 | Augmentation | SVS | Yes | 360 | 0 | 0 | 360 | 471.99 | 0 | 0 | 471.99
197 | MURSHIDABAD | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | TSM/017825 | Augmentation | SVS | Yes | 400 | 0 | 0 | 400 | 765.79 | 0 | 0 | 765.79
198 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-I Block- Lalgola, District- Murshidabad. | SM/16210 | TSM/018009 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
199 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | TSM/017963 | Augmentation | MVS | Yes | 1169 | 0 | 0 | 1169 | 994.64 | 0 | 0 | 994.64
200 | MURSHIDABAD | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16419 | TSM/018601 | Augmentation | MVS | Yes | 870 | 0 | 0 | 870 | 692.82 | 0 | 0 | 692.82
201 | MURSHIDABAD | DHANDANGA AMD IT'S ADJOINING MOUJAS | SM/16392 | TSM/018457 | New | MVS | Yes | 855 | 0 | 0 | 855 | 258.1 | 0 | 0 | 258.1
202 | MURSHIDABAD | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16394 | TSM/017712 | New | MVS | Yes | 925 | 0 | 0 | 925 | 242.17 | 0 | 0 | 242.17
203 | MURSHIDABAD | Augmentation of Bharatpur Zone -IIB Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. | SM/15728 | TSM/017921 | Augmentation | MVS | Yes | 797 | 0 | 0 | 797 | 534.48 | 0 | 0 | 534.48
204 | MURSHIDABAD | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16113 | TSM/018256 | New | SVS | Yes | 523 | 0 | 0 | 523 | 245.5 | 0 | 0 | 245.5
205 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16624 | TSM/015220 | Augmentation | SVS | Yes | 1313 | 0 | 541 | 772 | 606.43 | 0 | 21.99 | 584.43
206 | MURSHIDABAD | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | TSM/017648 | New | MVS | Yes | 1482 | 0 | 0 | 1482 | 711.04 | 0 | 0 | 711.04
207 | MURSHIDABAD | KIRTTIPUR AND ADJOINING MOUJAS PWSS | SM/15691 | TSM/017592 | New | MVS | Yes | 1599 | 0 | 0 | 1599 | 460.95 | 0 | 0 | 460.95
208 | MURSHIDABAD | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- III & Zone- XI) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. | SM/16673 | TSM/014922 | Retrofitting | MVS | Yes | 12601 | 0 | 0 | 12601 | 998.82 | 0 | 0 | 998.82
209 | MURSHIDABAD | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- I & Zone- V) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. | SM/16674 | TSM/014918 | Retrofitting | MVS | Yes | 12602 | 0 | 0 | 12602 | 996.89 | 0 | 0 | 996.89
210 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16769 | TSM/015855 | Augmentation | SVS | Yes | 297 | 318 | 0 | 615 | 220.12 | 0 | 0 | 220.12
211 | MURSHIDABAD | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16899 | TSM/018302 | Augmentation | MVS | Yes | 445 | 0 | 0 | 445 | 575.4 | 0 | 0 | 575.4
212 | MURSHIDABAD | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | TSM/015782 | Augmentation | MVS | Yes | 1444 | 0 | 0 | 1444 | 479.79 | 0 | 0 | 479.79
213 | MURSHIDABAD | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16870 | TSM/018010 | Augmentation | SVS | Yes | 2315 | 0 | 0 | 2315 | 945.91 | 0 | 0 | 945.91
214 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15752 | TSM/016021 | Augmentation | MVS | Yes | 5674 | 0 | 0 | 5674 | 863.23 | 0 | 0 | 863.23
215 | MURSHIDABAD | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | TSM/017667 | New | MVS | Yes | 1042 | 0 | 0 | 1042 | 613.13 | 0 | 0 | 613.13
216 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | TSM/018480 | Augmentation | MVS | Yes | 1075 | 0 | 0 | 1075 | 1898.34 | 0 | 0 | 1898.34
217 | MURSHIDABAD | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. | SM/18774 | TSM/016895 | Augmentation | MVS | Yes | 4730 | 0 | 2319 | 2411 | 1593.91 | 0 | 0 | 1593.91
218 | MURSHIDABAD | AUGMENTATION OF SARBANGAPUR ZONE-IA PIPED WATER SUPPLY SCHEME BLOCK -NAWDA , DISTRICT - MURSHIDABAD . | SM/19123 | TSM/017297 | Augmentation | SVS | Yes | 522 | 0 | 0 | 522 | 1029.17 | 0 | 0 | 1029.17
219 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18384 | TSM/018632 | Augmentation | SVS | Yes | 1712 | 0 | 0 | 1712 | 2055.8 | 0 | 0 | 2055.8
220 | MURSHIDABAD | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. | SM/18590 | TSM/017820 | Augmentation | MVS | Yes | 1178 | 0 | 0 | 1178 | 1563.27 | 0 | 0 | 1563.27
221 | MURSHIDABAD | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | TSM/016515 | New | MVS | Yes | 3022 | 0 | 0 | 3022 | 1308.69 | 0 | 0 | 1308.69
222 | MURSHIDABAD | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | TSM/015184 | New | MVS | Yes | 4256 | 0 | 0 | 4256 | 1240.43 | 0 | 0 | 1240.43
223 | MURSHIDABAD | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | TSM/015752 | New | MVS | Yes | 3600 | 0 | 0 | 3600 | 1083.25 | 0 | 0 | 1083.25
224 | MURSHIDABAD | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18773 | TSM/017306 | Augmentation | MVS | Yes | 1191 | 0 | 1187 | 4 | 994.52 | 0 | 0 | 994.52
225 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-IV, BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18662 | TSM/018639 | Augmentation | MVS | Yes | 6034 | 0 | 0 | 6034 | 2059.61 | 0 | 0 | 2059.61
226 | MURSHIDABAD | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/18694 | TSM/016734 | Augmentation | MVS | Yes | 3339 | 0 | 0 | 3339 | 1333.05 | 0 | 0 | 1333.05
227 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18756 | TSM/015907 | Augmentation | MVS | Yes | 2261 | 0 | 2049 | 212 | 974.86 | 0 | 0 | 974.86
228 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | TSM/012745 | Augmentation | MVS | Yes | 1091 | 0 | 0 | 1091 | 1074.75 | 0 | 0 | 1074.75
229 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagdanga ( 314725 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV | SM/07916 | TSM/006577 | Retrofitting | SVS | Yes | 767 | 0 | 0 | 767 | 61.03 | 0 | 0 | 61.03
230 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric | SM/07917 | TSM/006578 | Retrofitting | MVS | Yes | 1222 | 0 | 0 | 1222 | 97.32 | 0 | 0 | 97.32
231 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mridadpur (314570) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-II | SM/07920 | TSM/006581 | Retrofitting | SVS | Yes | 1193 | 493 | 0 | 1686 | 95.93 | 0 | 0 | 95.93
232 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Sahebnagar (VillageCode-314609) under command area of Kazipara ground water supply scheme (Part-A) | SM/07222 | TSM/006029 | Retrofitting | MVS | Yes | 1000 | 0 | 0 | 1000 | 66.28 | 0 | 0 | 66.28
233 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART- | SM/07923 | TSM/006584 | Retrofitting | SVS | Yes | 1839 | 1 | 0 | 1840 | 152.87 | 0 | 0 | 152.87
234 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) | SM/07687 | TSM/006395 | Retrofitting | SVS | Yes | 1461 | 0 | 0 | 1461 | 99.51 | 0 | 0 | 99.51
235 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Telia Village (Code-314466) In The Command Area Of Telia Ground Water Supply Scheme (Part-B) | SM/07732 | TSM/006457 | Retrofitting | SVS | Yes | 1906 | 0 | 0 | 1906 | 118.61 | 0 | 0 | 118.61
236 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Barabil Raghunathpur (314626) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murs | SM/07686 | TSM/006110 | Retrofitting | SVS | Yes | 2798 | 0 | 0 | 2798 | 200.91 | 0 | 0 | 200.91
237 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07909 | TSM/006568 | Retrofitting | SVS | Yes | 1467 | 2 | 0 | 1469 | 114.54 | 0 | 0 | 114.54
238 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | TSM/006540 | Retrofitting | MVS | Yes | 1153 | 0 | 0 | 1153 | 83.51 | 0 | 0 | 83.51
239 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | TSM/006092 | Retrofitting | MVS | Yes | 3207 | 0 | 489 | 2718 | 241.98 | 0 | 0 | 241.98
240 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | TSM/006552 | Retrofitting | MVS | Yes | 1287 | 0 | 0 | 1287 | 97.32 | 0 | 0 | 97.32
241 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Benipur (Code-314546) In The Command Area Of Benipur Ground Water Supply Scheme (Part-A) Under Bhagwangola-II Bloc | SM/07789 | TSM/006462 | Retrofitting | SVS | Yes | 1738 | 0 | 0 | 1738 | 115.48 | 0 | 0 | 115.48
242 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) | SM/08189 | TSM/006090 | Retrofitting | MVS | Yes | 26031 | 2465 | 0 | 28496 | 2032.59 | 0 | 0 | 2032.59
243 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhagirathpur (314699) of Bhagirathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/08272 | TSM/006048 | Retrofitting | SVS | Yes | 5406 | 0 | 0 | 5406 | 385.47 | 0 | 0 | 385.47
244 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/08280 | TSM/006078 | Retrofitting | SVS | Yes | 4099 | 0 | 0 | 4099 | 305.04 | 0 | 0 | 305.04
245 | MURSHIDABAD | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ratanpur ( 313841 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Mursh | SM/09745 | TSM/007543 | Retrofitting | SVS | Yes | 2242 | 0 | 0 | 2242 | 210.01 | 0 | 0 | 210.01
246 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Alampur ( 313932 ) of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District u | SM/09738 | TSM/007516 | Retrofitting | SVS | Yes | 720 | 0 | 0 | 720 | 54.13 | 0 | 0 | 54.13
247 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | TSM/007538 | Retrofitting | MVS | Yes | 14709 | 0 | 0 | 14709 | 1037.9 | 0 | 0 | 1037.9
248 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhandata (314524) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad District under | SM/09755 | TSM/007521 | Retrofitting | SVS | Yes | 1078 | 0 | 0 | 1078 | 81.3 | 0 | 0 | 81.3
249 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Palasi Sonadanga (314527) and Ramnapara (314496) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Bloc | SM/09756 | TSM/007522 | Retrofitting | MVS | Yes | 1154 | 0 | 0 | 1154 | 87.01 | 0 | 0 | 87.01
250 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad | SM/09836 | TSM/007493 | Retrofitting | SVS | Yes | 396 | 0 | 0 | 396 | 32.06 | 0 | 0 | 32.06
251 | MURSHIDABAD | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | TSM/008710 | Augmentation | MVS | Yes | 4273 | 0 | 2439 | 1834 | 971.89 | 0 | 99.15 | 872.74
252 | MURSHIDABAD | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | TSM/008707 | Augmentation | SVS | Yes | 1786 | 0 | 1782 | 4 | 640.21 | 0 | 72.44 | 567.78
253 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | TSM/010289 | Augmentation | MVS | Yes | 2306 | 0 | 1834 | 472 | 620.12 | 0 | 74.55 | 545.57
254 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10626 | TSM/010686 | Augmentation | SVS | Yes | 3163 | 0 | 3163 | 0 | 525.47 | 0 | 0 | 525.47
255 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Blo | SM/07790 | TSM/006463 | Retrofitting | SVS | Yes | 1347 | 2 | 0 | 1349 | 89.83 | 0 | 0 | 89.83
256 | MURSHIDABAD | MOKTARPUR PIPED WATER SUPPLY SCHEME | SM/11620 | TSM/010430 | New | MVS | Yes | 436 | 0 | 0 | 436 | 300.98 | 0 | 0 | 300.98
257 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. | SM/11967 | TSM/010562 | Augmentation | MVS | Yes | 9305 | 0 | 9240 | 65 | 1295.09 | 0 | 0 | 1295.09
258 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11569 | TSM/010776 | Augmentation | MVS | Yes | 6204 | 0 | 5653 | 551 | 512.1 | 0 | 0 | 512.1
259 | MURSHIDABAD | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | TSM/014891 | New | MVS | Yes | 2048 | 0 | 0 | 2048 | 623.31 | 0 | 0 | 623.31
260 | MURSHIDABAD | SERPUR AND ADJOINING MOUJAS PWSS | SM/13930 | TSM/015151 | New | MVS | Yes | 2965 | 0 | 0 | 2965 | 764.95 | 0 | 0 | 764.95
261 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balia Hasennagar, Arazi Nista (31447 & 314526) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of | SM/07280 | TSM/006101 | Retrofitting | MVS | Yes | 1276 | 0 | 0 | 1276 | 97.62 | 0 | 0 | 97.62
262 | MURSHIDABAD | PUNRAPARA AND ADJOINING MOUJAS PWSS | SM/13932 | TSM/015231 | New | MVS | Yes | 2494 | 0 | 0 | 2494 | 597.39 | 0 | 0 | 597.39
263 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | TSM/011836 | Augmentation | SVS | Yes | 57 | 0 | 0 | 57 | 360.07 | 0 | 0 | 360.07
264 | MURSHIDABAD | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | TSM/015869 | Augmentation | MVS | Yes | 1303 | 0 | 0 | 1303 | 649.29 | 0 | 0 | 649.29
265 | MURSHIDABAD | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | TSM/014464 | Augmentation | MVS | Yes | 1100 | 0 | 0 | 1100 | 770.8 | 0 | 0 | 770.8
266 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14828 | TSM/016704 | Augmentation | MVS | Yes | 463 | 228 | 0 | 691 | 628.88 | 0 | 18.54 | 610.34
267 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-II IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14829 | TSM/016703 | Augmentation | SVS | Yes | 177 | 0 | 175 | 2 | 550.94 | 0 | 7.11 | 543.83
268 | MURSHIDABAD | KHESAR AND IT'S ADJOINING MOUJAS PWSS | SM/13937 | TSM/015345 | New | MVS | Yes | 3593 | 0 | 0 | 3593 | 892.38 | 0 | 0 | 892.38
269 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14046 | TSM/016385 | Augmentation | MVS | Yes | 255 | 0 | 0 | 255 | 686.91 | 0 | 0 | 686.91
270 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE | SM/14629 | TSM/015693 | Augmentation | MVS | Yes | 832 | 0 | 78 | 754 | 680.05 | 0 | 3.17 | 676.88
271 | MURSHIDABAD | MIRHATI AND ADJOINING MOUJAS PWSS | SM/14869 | TSM/015227 | New | MVS | Yes | 590 | 0 | 0 | 590 | 232.44 | 0 | 0 | 232.44
272 | MURSHIDABAD | SITARAMPUR PIPED WATER SUPPLY SCHEME. | SM/15048 | TSM/017537 | New | MVS | Yes | 1401 | 0 | 0 | 1401 | 864.73 | 0 | 0 | 864.73
273 | MURSHIDABAD | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | TSM/017469 | New | MVS | Yes | 817 | 0 | 0 | 817 | 758.85 | 0 | 0 | 758.85
274 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15061 | TSM/018031 | Augmentation | MVS | Yes | 1034 | 0 | 0 | 1034 | 807.52 | 0 | 0 | 807.52
275 | MURSHIDABAD | JHILLI AND ADJOINING MOUJAS PWSS | SM/14505 | TSM/015141 | New | MVS | Yes | 3213 | 0 | 0 | 3213 | 831.53 | 0 | 0 | 831.53
276 | MURSHIDABAD | MARURA AND ADJOINING MOUJAS PWSS | SM/14235 | TSM/014938 | New | MVS | Yes | 3572 | 0 | 0 | 3572 | 1168.32 | 0 | 0 | 1168.32
277 | MURSHIDABAD | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/16248 | TSM/016107 | New | SVS | Yes | 1033 | 0 | 0 | 1033 | 394.39 | 0 | 0 | 394.39
278 | MURSHIDABAD | Augmentation of Bharatpur Zone- I A Water Supply Scheme Block -Bharatpur-I, Dist- Murshidabad. | SM/16240 | TSM/018273 | Augmentation | SVS | Yes | 529 | 0 | 0 | 529 | 541.38 | 0 | 0 | 541.38
279 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jorgachha, Ganra Baria, Malatipur (314690, 314697 & 314698) of Jorgachha under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of | SM/07676 | TSM/006071 | Retrofitting | MVS | Yes | 1935 | 1 | 0 | 1936 | 150.4 | 0 | 0 | 150.4
280 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-III, Block- Nawda, District- Murshidabad. | SM/16436 | TSM/017970 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
281 | MURSHIDABAD | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16549 | TSM/016066 | New | MVS | Yes | 2133 | 0 | 0 | 2133 | 641.21 | 0 | 0 | 641.21
282 | MURSHIDABAD | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16456 | TSM/015923 | Augmentation | SVS | Yes | 585 | 0 | 342 | 243 | 478.54 | 0 | 13.9 | 464.64
283 | MURSHIDABAD | Mini piped water supply scheme (maximum 100 households) Village-Sona Diar Zone-II, Block-Berhampore, District- Murshidabad. | SM/16047 | TSM/017993 | New | SVS | Yes | 54 | 0 | 0 | 54 | 35.93 | 0 | 0 | 35.93
284 | MURSHIDABAD | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - MOHESPUR , BLOCK BELDANGA -I ,DISTRICT - MURSHIDABAD. | SM/16050 | TSM/013364 | New | SVS | Yes | 65 | 0 | 0 | 65 | 37.34 | 0 | 0 | 37.34
285 | MURSHIDABAD | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . | SM/16217 | TSM/017931 | New | SVS | Yes | 1961 | 0 | 0 | 1961 | 898.14 | 0 | 0 | 898.14
286 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Alighata, Block- Lalgola, District- Murshidabad. | SM/16496 | TSM/017998 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
287 | MURSHIDABAD | Mini piped water supply scheme (maximum 100 households) Village-Sibnagar Zone-V, Block-Nawda, District- Murshidabad. | SM/16501 | TSM/017937 | New | SVS | Yes | 40 | 0 | 0 | 40 | 33.09 | 0 | 0 | 33.09
288 | MURSHIDABAD | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | TSM/016089 | Augmentation | MVS | Yes | 752 | 0 | 111 | 641 | 503.35 | 0 | 4.51 | 498.84
289 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED MADNA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16405 | TSM/017525 | Augmentation | MVS | Yes | 1889 | 0 | 101 | 1788 | 907.34 | 0 | 4.11 | 903.24
290 | MURSHIDABAD | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16504 | TSM/019535 | New | SVS | Yes | 225 | 0 | 0 | 225 | 81.23 | 0 | 0 | 81.23
291 | MURSHIDABAD | CHANDAMARI PIPED WATER SUPPLY SCHEME. | SM/16218 | TSM/016579 | New | SVS | Yes | 786 | 0 | 0 | 786 | 520.98 | 0 | 0 | 520.98
292 | MURSHIDABAD | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I)PART-B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16556 | TSM/017143 | Augmentation | MVS | Yes | 646 | 415 | 0 | 1061 | 221.25 | 0 | 0 | 221.25
293 | MURSHIDABAD | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16389 | TSM/016069 | New | MVS | Yes | 860 | 0 | 0 | 860 | 261.03 | 0 | 0 | 261.03
294 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16560 | TSM/018030 | Augmentation | SVS | Yes | 623 | 0 | 55 | 568 | 492.65 | 0 | 2.24 | 490.42
295 | MURSHIDABAD | Augmentation of Dakshin Kanda Zone - II Water Supply Scheme Block - Bharatpur-II , Dist- Murshidabad. | SM/15741 | TSM/018001 | Augmentation | MVS | Yes | 769 | 0 | 0 | 769 | 636.25 | 0 | 0 | 636.25
296 | MURSHIDABAD | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16111 | TSM/017479 | New | MVS | Yes | 274 | 0 | 0 | 274 | 124.95 | 0 | 0 | 124.95
297 | MURSHIDABAD | BERBARI AND ADJOINING MOUJAS PWSS | SM/15694 | TSM/017527 | New | MVS | Yes | 359 | 0 | 0 | 359 | 146.43 | 0 | 0 | 146.43
298 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | TSM/006890 | Retrofitting | MVS | Yes | 17596 | 2696 | 0 | 20292 | 1325.56 | 0 | 0 | 1325.56
299 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-I PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16768 | TSM/015839 | Augmentation | SVS | Yes | 879 | 0 | 0 | 879 | 792.83 | 0 | 0 | 792.83
300 | MURSHIDABAD | MANDALSAR AND ADJOINING MOUJAS PWSS | SM/15938 | TSM/016374 | New | MVS | Yes | 1322 | 0 | 0 | 1322 | 479.13 | 0 | 0 | 479.13
301 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | TSM/010764 | Augmentation | SVS | Yes | 5613 | 0 | 5507 | 106 | 852.05 | 0 | 0 | 852.05
302 | MURSHIDABAD | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. | SM/16866 | TSM/017822 | Augmentation | SVS | Yes | 417 | 0 | 0 | 417 | 587.32 | 0 | 0 | 587.32
303 | MURSHIDABAD | SIDDHESWARI & ADJOINING MOUJAS PWSS | SM/18312 | TSM/017104 | New | MVS | Yes | 3140 | 0 | 0 | 3140 | 1223.05 | 0 | 0 | 1223.05
304 | MURSHIDABAD | HABASPUR AND ADJOINING MOUJAS PWSS | SM/18238 | TSM/015749 | New | SVS | Yes | 4643 | 0 | 0 | 4643 | 1547.96 | 0 | 0 | 1547.96
305 | MURSHIDABAD | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | TSM/015216 | New | MVS | Yes | 4588 | 0 | 0 | 4588 | 1115.39 | 0 | 0 | 1115.39
306 | MURSHIDABAD | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. | SM/19124 | TSM/018284 | Augmentation | SVS | Yes | 1468 | 0 | 0 | 1468 | 3659.55 | 0 | 0 | 3659.55
307 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME OF MANIGRAM-BALARAMBATI BLOCK-SAGARDIGHI | SM/19017 | TSM/008645 | Augmentation | MVS | Yes | 1352 | 0 | 368 | 984 | 117.62 | 0 | 14.96 | 102.66
308 | MURSHIDABAD | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | TSM/017302 | New | MVS | Yes | 4264 | 0 | 0 | 4264 | 1218.84 | 0 | 0 | 1218.84
309 | MURSHIDABAD | Retrofitting of Ground Water Based Water Supply Scheme for Kamalakantapur and its Adjoining Mouzas to provided last mile connectivety and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/18488 | TSM/021516 | Retrofitting | MVS | Yes | 1518 | 0 | 0 | 1518 | 135.04 | 0 | 0 | 135.04
310 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sibnagar Laskarpur (314702) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District (P | SM/07906 | TSM/006565 | Retrofitting | SVS | Yes | 3781 | 0 | 0 | 3781 | 291.34 | 0 | 0 | 291.34
311 | MURSHIDABAD | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD | SM/18896 | TSM/016018 | Augmentation | MVS | Yes | 4547 | 1435 | 0 | 5982 | 16379.52 | 0 | 0 | 16379.52
312 | MURSHIDABAD | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | TSM/010640 | New | SVS | Yes | 1507 | 0 | 243 | 1264 | 905.71 | 0 | 0 | 905.71
313 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18736 | TSM/015906 | Augmentation | MVS | Yes | 621 | 0 | 617 | 4 | 1945.44 | 0 | 0 | 1945.44
314 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Ramchandrapur (Code-314219) In The Command Area Of Bansgara Ground Water Supply Scheme(Part-B) | SM/07733 | TSM/006459 | Retrofitting | SVS | Yes | 855 | 0 | 605 | 250 | 55.09 | 0 | 0 | 55.09
315 | MURSHIDABAD | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | TSM/015788 | Augmentation | MVS | Yes | 3440 | 0 | 1411 | 2029 | 1419.76 | 0 | 0 | 1419.76
316 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar | SM/12579 | TSM/011670 | Augmentation | SVS | Yes | 1965 | 0 | 0 | 1965 | 995.02 | 0 | 0 | 995.02
317 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | TSM/012747 | Augmentation | MVS | Yes | 688 | 0 | 0 | 688 | 677.36 | 0 | 0 | 677.36
318 | MURSHIDABAD | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | TSM/015997 | Augmentation | MVS | Yes | 919 | 0 | 0 | 919 | 1060.31 | 0 | 0 | 1060.31
319 | MURSHIDABAD | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | TSM/018282 | Augmentation | MVS | Yes | 3052 | 0 | 0 | 3052 | 3550.58 | 0 | 0 | 3550.58
320 | MURSHIDABAD | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. | SM/18701 | TSM/018298 | Augmentation | MVS | Yes | 6632 | 0 | 0 | 6632 | 1931.29 | 0 | 0 | 1931.29
321 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidaba | SM/07784 | TSM/006453 | Retrofitting | SVS | Yes | 1242 | 1 | 0 | 1243 | 82.98 | 0 | 0 | 82.98
322 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) | SM/07700 | TSM/006501 | Retrofitting | SVS | Yes | 2460 | 0 | 0 | 2460 | 164.71 | 0 | 0 | 164.71
323 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sabdalpur ( 314704 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II | SM/07915 | TSM/006575 | Retrofitting | SVS | Yes | 1252 | 0 | 0 | 1252 | 98.09 | 0 | 0 | 98.09
324 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Udaynagar Diar ground water supply scheme | SM/07224 | TSM/006035 | Retrofitting | SVS | Yes | 715 | 0 | 0 | 715 | 52.11 | 0 | 0 | 52.11
325 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A) | SM/06973 | TSM/006025 | Retrofitting | SVS | Yes | 786 | 0 | 0 | 786 | 50.08 | 0 | 0 | 50.08
326 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme | SM/06984 | TSM/006063 | Retrofitting | MVS | Yes | 1653 | 15 | 0 | 1668 | 99.87 | 0 | 0 | 99.87
327 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) | SM/07274 | TSM/006050 | Retrofitting | SVS | Yes | 1028 | 0 | 0 | 1028 | 85.16 | 0 | 0 | 85.16
328 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Naudaparavillage (Code-314456) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (Part-B) | SM/07727 | TSM/006437 | Retrofitting | SVS | Yes | 675 | 0 | 0 | 675 | 49.3 | 0 | 0 | 49.3
329 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Lakshminathpur (314696) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) | SM/07290 | TSM/006120 | Retrofitting | SVS | Yes | 1322 | 0 | 0 | 1322 | 99.96 | 0 | 0 | 99.96
330 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Domkal, Kalabaria (314695 & 314662) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part | SM/07293 | TSM/006130 | Retrofitting | MVS | Yes | 1313 | 0 | 0 | 1313 | 99.3 | 0 | 0 | 99.3
331 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur | SM/07664 | TSM/006043 | Retrofitting | MVS | Yes | 2253 | 28 | 0 | 2281 | 183.02 | 0 | 0 | 183.02
332 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of | SM/07674 | TSM/006055 | Retrofitting | MVS | Yes | 3899 | 0 | 0 | 3899 | 295.52 | 0 | 0 | 295.52
333 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Pa | SM/07695 | TSM/006476 | Retrofitting | MVS | Yes | 1884 | 0 | 0 | 1884 | 119.21 | 0 | 0 | 119.21
334 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jhaudanga (Code-314195) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-B) | SM/07716 | TSM/006510 | Retrofitting | SVS | Yes | 150 | 0 | 0 | 150 | 12.33 | 0 | 0 | 12.33
335 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gobindotala Village (Code-314454), Paschim Rampur (Code-314455) In The Command Area Of Paschim Rampur Ground Water Supply Scheme | SM/07783 | TSM/006433 | Retrofitting | SVS | Yes | 1231 | 0 | 0 | 1231 | 88.5 | 0 | 0 | 88.5
336 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/07680 | TSM/006081 | Retrofitting | SVS | Yes | 2836 | 0 | 0 | 2836 | 207.09 | 0 | 0 | 207.09
337 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba | SM/08183 | TSM/006044 | Retrofitting | MVS | Yes | 5229 | 0 | 0 | 5229 | 389.91 | 0 | 0 | 389.91
338 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected | SM/08185 | TSM/006046 | Retrofitting | MVS | Yes | 4666 | 0 | 0 | 4666 | 329.04 | 0 | 0 | 329.04
339 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Taraf Rasulpur (314679) of P.T. Rasulpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/08186 | TSM/006086 | Retrofitting | SVS | Yes | 4803 | 0 | 0 | 4803 | 357.84 | 0 | 0 | 357.84
340 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Garaimari ( 314734 ) of Garaimari under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/08201 | TSM/006562 | Retrofitting | SVS | Yes | 7129 | 0 | 0 | 7129 | 548.73 | 0 | 0 | 548.73
341 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dayanagar (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08906 | TSM/006881 | Retrofitting | MVS | Yes | 7368 | 0 | 4074 | 3294 | 505.26 | 0 | 0 | 505.26
342 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Mursh | SM/08271 | TSM/006047 | Retrofitting | MVS | Yes | 5463 | 1 | 0 | 5464 | 423.18 | 0 | 0 | 423.18
343 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | TSM/006886 | Retrofitting | MVS | Yes | 13524 | 0 | 8330 | 5194 | 995.85 | 0 | 0 | 995.85
344 | MURSHIDABAD | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM | SM/08919 | TSM/007491 | Retrofitting | SVS | Yes | 2268 | 484 | 0 | 2752 | 183.43 | 0 | 0 | 183.43
345 | MURSHIDABAD | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | TSM/008739 | Retrofitting | MVS | Yes | 8295 | 0 | 0 | 8295 | 835.07 | 0 | 0 | 835.07
346 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khidirpur (313990) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidaba | SM/09758 | TSM/007524 | Retrofitting | SVS | Yes | 1009 | 0 | 0 | 1009 | 76.56 | 0 | 0 | 76.56
347 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | TSM/007499 | Retrofitting | SVS | Yes | 460 | 0 | 0 | 460 | 36.56 | 0 | 0 | 36.56
348 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadupur ( 315357 ) of Jadupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad | SM/09761 | TSM/007528 | Retrofitting | SVS | Yes | 530 | 0 | 0 | 530 | 43.78 | 0 | 0 | 43.78
349 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Madhupur ( 315333 ) of Arazi Madhupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09768 | TSM/007535 | Retrofitting | SVS | Yes | 793 | 0 | 0 | 793 | 60.39 | 0 | 0 | 60.39
350 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10611 | TSM/010298 | Augmentation | MVS | Yes | 3902 | 0 | 3553 | 349 | 738.67 | 0 | 0 | 738.67
351 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Balijana (Code-314514), Nandanpur (Code-314515), Jibanpur (Code-314516) In The Command Area Of Jhikra Ground Wate | SM/07796 | TSM/006469 | Retrofitting | MVS | Yes | 1278 | 0 | 0 | 1278 | 92.37 | 0 | 0 | 92.37
352 | MURSHIDABAD | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | TSM/008716 | Augmentation | MVS | Yes | 4244 | 0 | 17 | 4227 | 965.82 | 0 | 0 | 965.82
353 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | TSM/010314 | Augmentation | MVS | Yes | 2930 | 0 | 85 | 2845 | 774.74 | 0 | 3.46 | 771.28
354 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A) | SM/07221 | TSM/006023 | Retrofitting | SVS | Yes | 929 | 0 | 0 | 929 | 62.74 | 0 | 0 | 62.74
355 | MURSHIDABAD | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Panchgachhia, Arazi Ramakantapur, Gotha, Sadikpur, (313919, 313910, 313912, 313920) of Madna under Ground water based water supply scheme for arsenic affected areas of Suti-I Block | SM/11217 | TSM/008714 | Augmentation | MVS | Yes | 2167 | 0 | 372 | 1795 | 288.41 | 0 | 15.12 | 273.29
356 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11562 | TSM/010757 | Augmentation | MVS | Yes | 2848 | 0 | 1423 | 1425 | 836.5 | 0 | 57.84 | 778.65
357 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | TSM/010065 | Augmentation | SVS | Yes | 3846 | 0 | 2836 | 1010 | 514.74 | 0 | 0 | 514.74
358 | MURSHIDABAD | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | TSM/014724 | New | MVS | Yes | 3586 | 0 | 0 | 3586 | 963.23 | 0 | 0 | 963.23
359 | MURSHIDABAD | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Chak Bhikhari,(314686) of Juginda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division PheDte. | SM/11231 | TSM/008704 | Augmentation | SVS | Yes | 175 | 0 | 3 | 172 | 150.76 | 0 | 0 | 150.76
360 | MURSHIDABAD | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Tikar Bariakalkihara (314642) of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Divisi | SM/11232 | TSM/008713 | Augmentation | MVS | Yes | 708 | 0 | 0 | 708 | 128.48 | 0 | 0 | 128.48
361 | MURSHIDABAD | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | TSM/014668 | New | MVS | Yes | 2306 | 0 | 0 | 2306 | 605.27 | 0 | 0 | 605.27
362 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11791 | TSM/010779 | Augmentation | MVS | Yes | 2222 | 0 | 837 | 1385 | 698.06 | 0 | 34.02 | 664.04
363 | MURSHIDABAD | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | TSM/015324 | Augmentation | MVS | Yes | 979 | 0 | 406 | 573 | 946.46 | 0 | 16.5 | 929.96
364 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14048 | TSM/016368 | Augmentation | MVS | Yes | 630 | 759 | 0 | 1389 | 713.71 | 0 | 0 | 713.71
365 | MURSHIDABAD | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | TSM/012764 | Augmentation | MVS | Yes | 2658 | 0 | 0 | 2658 | 721.32 | 0 | 0 | 721.32
366 | MURSHIDABAD | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I | SM/14924 | TSM/017870 | Augmentation | MVS | Yes | 3275 | 0 | 0 | 3275 | 881.94 | 0 | 0 | 881.94
367 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . | SM/14066 | TSM/012749 | Augmentation | MVS | Yes | 299 | 0 | 0 | 299 | 613 | 0 | 0 | 613
368 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- II Block - Khargram , Dist- Murshidabad. | SM/14631 | TSM/015768 | Augmentation | MVS | Yes | 466 | 0 | 365 | 101 | 488.47 | 0 | 14.84 | 473.64
369 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. | SM/14632 | TSM/015778 | Augmentation | MVS | Yes | 1060 | 0 | 349 | 711 | 631.26 | 0 | 14.19 | 617.07
370 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14633 | TSM/015872 | Augmentation | SVS | Yes | 1274 | 0 | 637 | 637 | 573.57 | 0 | 25.89 | 547.68
371 | MURSHIDABAD | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | TSM/016308 | Augmentation | SVS | Yes | 328 | 0 | 0 | 328 | 303.6 | 0 | 0 | 303.6
372 | MURSHIDABAD | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | TSM/015751 | New | MVS | Yes | 2018 | 0 | 0 | 2018 | 674.05 | 0 | 0 | 674.05
373 | MURSHIDABAD | Augmentation of Tekaraipara Pipe Water Supply Scheme Block - Raninagar -I District - Murshidabad. | SM/15064 | TSM/017526 | Augmentation | MVS | Yes | 1052 | 0 | 743 | 309 | 997.95 | 0 | 30.2 | 967.74
374 | MURSHIDABAD | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | TSM/016508 | New | MVS | Yes | 1596 | 0 | 0 | 1596 | 724.68 | 0 | 0 | 724.68
375 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply | SM/06974 | TSM/006026 | Retrofitting | SVS | Yes | 1402 | 1 | 0 | 1403 | 91.48 | 0 | 0 | 91.48
376 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahisha Thali ( 313851 ) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-III | SM/07514 | TSM/006559 | Retrofitting | SVS | Yes | 591 | 0 | 0 | 591 | 45.43 | 0 | 0 | 45.43
377 | MURSHIDABAD | MAHISHASTHALI AND ADJOINING MOUJAS PWSS | SM/16015 | TSM/017606 | New | SVS | Yes | 2236 | 0 | 0 | 2236 | 803.16 | 0 | 0 | 803.16
378 | MURSHIDABAD | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | TSM/017330 | New | MVS | Yes | 1771 | 0 | 0 | 1771 | 900.63 | 0 | 0 | 900.63
379 | MURSHIDABAD | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | TSM/019539 | New | SVS | Yes | 383 | 0 | 0 | 383 | 121.85 | 0 | 0 | 121.85
380 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for JAGAIAPUR Block - Nawda District - Murshidabad. | SM/16543 | TSM/013077 | Augmentation | MVS | Yes | 1809 | 0 | 191 | 1618 | 543.46 | 0 | 7.76 | 535.69
381 | MURSHIDABAD | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Chhalimpur, Block- Murshidabad Jiaganj, District- Murshidabad. | SM/16048 | TSM/017934 | New | SVS | Yes | 30 | 0 | 0 | 30 | 31.8 | 0 | 0 | 31.8
382 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | TSM/006471 | Retrofitting | MVS | Yes | 8682 | 0 | 2899 | 5783 | 579.45 | 0 | 0 | 579.45
383 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-I, Block- Nawda, District- Murshidabad. | SM/16499 | TSM/017957 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
384 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16406 | TSM/018239 | Augmentation | SVS | Yes | 3199 | 0 | 0 | 3199 | 951.83 | 0 | 0 | 951.83
385 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE | SM/16408 | TSM/017460 | Augmentation | MVS | Yes | 1666 | 0 | 73 | 1593 | 784.86 | 0 | 2.97 | 781.89
386 | MURSHIDABAD | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | TSM/016047 | Augmentation | MVS | Yes | 662 | 0 | 469 | 193 | 963.3 | 0 | 19.06 | 944.24
387 | MURSHIDABAD | SUJAPUR PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16214 | TSM/019384 | New | SVS | Yes | 210 | 0 | 0 | 210 | 81.23 | 0 | 0 | 81.23
388 | MURSHIDABAD | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16411 | TSM/017904 | Augmentation | MVS | Yes | 2104 | 0 | 0 | 2104 | 587.59 | 0 | 0 | 587.59
389 | MURSHIDABAD | Augmentation of Salar Zone- I B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16423 | TSM/018270 | Augmentation | MVS | Yes | 445 | 0 | 0 | 445 | 540.61 | 0 | 0 | 540.61
390 | MURSHIDABAD | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | TSM/018385 | New | SVS | Yes | 577 | 0 | 0 | 577 | 415.43 | 0 | 0 | 415.43
391 | MURSHIDABAD | MASLA AND ADJOINING MOUJAS PWSS | SM/16529 | TSM/016110 | New | SVS | Yes | 945 | 0 | 0 | 945 | 367.21 | 0 | 0 | 367.21
392 | MURSHIDABAD | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16388 | TSM/016068 | New | MVS | Yes | 1069 | 0 | 0 | 1069 | 436.24 | 0 | 0 | 436.24
393 | MURSHIDABAD | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/16391 | TSM/017533 | New | SVS | Yes | 1920 | 0 | 0 | 1920 | 927.36 | 0 | 0 | 927.36
394 | MURSHIDABAD | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16396 | TSM/017516 | New | MVS | Yes | 3690 | 0 | 0 | 3690 | 710.31 | 0 | 0 | 710.31
395 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | TSM/016383 | Augmentation | MVS | Yes | 678 | 0 | 0 | 678 | 998.86 | 0 | 0 | 998.86
396 | MURSHIDABAD | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | TSM/017958 | Augmentation | MVS | Yes | 1612 | 0 | 0 | 1612 | 709.71 | 0 | 0 | 709.71
397 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. | SM/16623 | TSM/013099 | Augmentation | SVS | Yes | 774 | 0 | 384 | 390 | 801.92 | 0 | 15.61 | 786.31
398 | MURSHIDABAD | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | TSM/017598 | New | MVS | Yes | 458 | 0 | 0 | 458 | 390.77 | 0 | 0 | 390.77
399 | MURSHIDABAD | KELAI AND IT'S ADJOINING MOUJAS | SM/15680 | TSM/018456 | New | MVS | Yes | 3136 | 0 | 0 | 3136 | 801.52 | 0 | 0 | 801.52
400 | MURSHIDABAD | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | TSM/019538 | New | SVS | Yes | 532 | 0 | 0 | 532 | 203.08 | 0 | 0 | 203.08
401 | MURSHIDABAD | ALAMPUR AND ADJOINING MOPUJAS PWSS | SM/16813 | TSM/018255 | New | MVS | Yes | 960 | 0 | 0 | 960 | 444.78 | 0 | 0 | 444.78
402 | MURSHIDABAD | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/15748 | TSM/018611 | Augmentation | MVS | Yes | 1050 | 0 | 0 | 1050 | 789.55 | 0 | 0 | 789.55
403 | MURSHIDABAD | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | TSM/018295 | Augmentation | MVS | Yes | 5176 | 0 | 0 | 5176 | 999.15 | 0 | 0 | 999.15
404 | MURSHIDABAD | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XV & XVII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16985 | TSM/019261 | Retrofitting | MVS | Yes | 10688 | 0 | 0 | 10688 | 965.79 | 0 | 0 | 965.79
405 | MURSHIDABAD | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VI & VII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16988 | TSM/019262 | Retrofitting | MVS | Yes | 9981 | 0 | 0 | 9981 | 934.56 | 0 | 0 | 934.56
406 | MURSHIDABAD | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VIII & XII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16989 | TSM/019259 | Retrofitting | MVS | Yes | 11796 | 0 | 0 | 11796 | 999.61 | 0 | 0 | 999.61
407 | MURSHIDABAD | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/16867 | TSM/018439 | New | MVS | Yes | 448 | 0 | 0 | 448 | 209.46 | 0 | 0 | 209.46
408 | MURSHIDABAD | PASCHIM PUNROPARA (CT) ZONE-I PIPED WATER SUPPLY SCHEME. | SM/19121 | TSM/017898 | New | SVS | Yes | 4363 | 0 | 0 | 4363 | 1667.04 | 0 | 0 | 1667.04
409 | MURSHIDABAD | AOCHA AND ADJJOINING MOUJAS PWSS | SM/18470 | TSM/015995 | New | MVS | Yes | 3819 | 0 | 0 | 3819 | 1040.98 | 0 | 0 | 1040.98
410 | MURSHIDABAD | Augmentation of Putia Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/19016 | TSM/016733 | Augmentation | SVS | Yes | 1362 | 0 | 1360 | 2 | 826.01 | 0 | 0 | 826.01
411 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. | SM/19018 | TSM/017713 | Augmentation | SVS | Yes | 137 | 0 | 0 | 137 | 187.45 | 0 | 0 | 187.45
412 | MURSHIDABAD | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/19111 | TSM/015604 | Augmentation | MVS | Yes | 1042 | 0 | 1033 | 9 | 1111.29 | 0 | 0 | 1111.29
413 | MURSHIDABAD | SRIKANTABATI (CT) PART -A PIPED WATER SUPPLY SCHEME. | SM/18691 | TSM/017518 | New | SVS | Yes | 2733 | 0 | 0 | 2733 | 1102.97 | 0 | 0 | 1102.97
414 | MURSHIDABAD | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. | SM/18692 | TSM/017331 | New | SVS | Yes | 3283 | 0 | 0 | 3283 | 1499.1 | 0 | 0 | 1499.1
415 | MURSHIDABAD | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | TSM/010626 | New | SVS | Yes | 1251 | 915 | 0 | 2166 | 980.49 | 0 | 0 | 980.49
416 | MURSHIDABAD | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. | SM/18737 | TSM/013409 | Augmentation | MVS | Yes | 4627 | 0 | 991 | 3636 | 1052.46 | 0 | 0 | 1052.46
417 | MURSHIDABAD | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS | SM/18464 | TSM/015835 | New | MVS | Yes | 5878 | 0 | 0 | 5878 | 1754.46 | 0 | 0 | 1754.46
418 | MURSHIDABAD | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | TSM/016581 | New | SVS | Yes | 3879 | 0 | 0 | 3879 | 1754.34 | 0 | 0 | 1754.34
419 | MURSHIDABAD | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | TSM/016559 | Augmentation | MVS | Yes | 11311 | 382 | 0 | 11693 | 4390.37 | 0 | 0 | 4390.37
420 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. | SM/18703 | TSM/018479 | Augmentation | MVS | Yes | 1626 | 0 | 0 | 1626 | 2237.11 | 0 | 0 | 2237.11
421 | MURSHIDABAD | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | TSM/017959 | Augmentation | MVS | Yes | 895 | 0 | 0 | 895 | 1031.59 | 0 | 0 | 1031.59
422 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part- | SM/08106 | TSM/006458 | Retrofitting | MVS | Yes | 5737 | 0 | 38 | 5699 | 360.94 | 0 | 0 | 360.94
423 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kusbaria (314722) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) | SM/07912 | TSM/006571 | Retrofitting | SVS | Yes | 1342 | 0 | 0 | 1342 | 105.04 | 0 | 0 | 105.04
424 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur (314567) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART- | SM/07921 | TSM/006582 | Retrofitting | SVS | Yes | 1131 | 0 | 0 | 1131 | 91.1 | 0 | 0 | 91.1
425 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bilaspur (314681) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) | SM/07516 | TSM/006561 | Retrofitting | SVS | Yes | 1028 | 0 | 0 | 1028 | 79.12 | 0 | 0 | 79.12
426 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) | SM/07670 | TSM/006125 | Retrofitting | SVS | Yes | 1854 | 0 | 0 | 1854 | 155.88 | 0 | 0 | 155.88
427 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhulauri (314671) of Dhulauri under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/07673 | TSM/006053 | Retrofitting | SVS | Yes | 1671 | 0 | 0 | 1671 | 142.93 | 0 | 0 | 142.93
428 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarambati, Manigram (314285, 314284) of Monigram Balarambati under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block of Mursh | SM/07679 | TSM/006079 | Retrofitting | MVS | Yes | 1582 | 0 | 91 | 1491 | 122.92 | 0 | 0 | 122.92
429 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District | SM/07692 | TSM/006470 | Retrofitting | MVS | Yes | 4345 | 0 | 0 | 4345 | 283.13 | 0 | 0 | 283.13
430 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | TSM/006070 | Retrofitting | MVS | Yes | 1571 | 0 | 344 | 1227 | 99.86 | 0 | 0 | 99.86
431 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadabpur Nimtala (313796) of Jadabpur Nimtala under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Par | SM/07275 | TSM/006082 | Retrofitting | SVS | Yes | 267 | 0 | 0 | 267 | 21.9 | 0 | 0 | 21.9
432 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/07701 | TSM/006503 | Retrofitting | SVS | Yes | 2301 | 0 | 0 | 2301 | 169.75 | 0 | 0 | 169.75
433 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Chandipur Ramkantapur (Code-314483), Rasulpur (Code-314492) In The Command Area Of Kasba Bahadurpur Ground Water | SM/07726 | TSM/006436 | Retrofitting | SVS | Yes | 1065 | 0 | 0 | 1065 | 76.06 | 0 | 0 | 76.06
434 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Malipara Village (Code-314452), Saaragachi Village (Code-314453),Chainpara Village (Code-314457),Rameswarbati Village (Code-31445 | SM/07728 | TSM/006438 | Retrofitting | SVS | Yes | 872 | 0 | 0 | 872 | 63.18 | 0 | 0 | 63.18
435 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | TSM/006891 | Retrofitting | MVS | Yes | 14595 | 0 | 8091 | 6504 | 1021.1 | 0 | 0 | 1021.1
436 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | TSM/006903 | Retrofitting | MVS | Yes | 10862 | 0 | 6279 | 4583 | 823.92 | 0 | 0 | 823.92
437 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarampur, Palasbati (314475 & 314476) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Murshi | SM/07281 | TSM/006102 | Retrofitting | MVS | Yes | 1296 | 0 | 0 | 1296 | 99.11 | 0 | 0 | 99.11
438 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sundarpur (Code-314445) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-B) | SM/07730 | TSM/006440 | Retrofitting | SVS | Yes | 1000 | 0 | 0 | 1000 | 68.76 | 0 | 0 | 68.76
439 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Muradpur Arazi, Paranpur, Sadikhan Diar (314627, 314637 & 314638) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Aff | SM/07285 | TSM/006111 | Retrofitting | MVS | Yes | 1201 | 0 | 0 | 1201 | 87.45 | 0 | 0 | 87.45
440 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Bansgara ground water supply scheme | SM/07233 | TSM/006069 | Retrofitting | MVS | Yes | 1337 | 685 | 0 | 2022 | 97.22 | 0 | 0 | 97.22
441 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- | SM/07907 | TSM/006566 | Retrofitting | SVS | Yes | 3406 | 0 | 0 | 3406 | 263.57 | 0 | 0 | 263.57
442 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | TSM/006542 | Retrofitting | SVS | Yes | 873 | 0 | 0 | 873 | 63.33 | 0 | 0 | 63.33
443 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) | SM/07668 | TSM/006095 | Retrofitting | SVS | Yes | 3297 | 0 | 0 | 3297 | 241.26 | 0 | 0 | 241.26
444 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jhikra (Code-314512), Ranitala (Code-314513) In The Command Area Of Jhikra Ground Water Supply Scheme (Part-A) Un | SM/07795 | TSM/006468 | Retrofitting | MVS | Yes | 1161 | 0 | 0 | 1161 | 83.47 | 0 | 0 | 83.47
445 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Manganpara Village (Code-315662) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-A) | SM/07717 | TSM/006511 | Retrofitting | SVS | Yes | 678 | 0 | 0 | 678 | 53.68 | 0 | 0 | 53.68
446 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A) | SM/07719 | TSM/006513 | Retrofitting | SVS | Yes | 1113 | 0 | 0 | 1113 | 85.64 | 0 | 0 | 85.64
447 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Moktarpur Village (Code-314766), Under Command Area Of Moktarpur Ground Water Supply Scheme(Part-A) Under Raninagar-I Block In M | SM/07888 | TSM/006516 | Retrofitting | SVS | Yes | 2294 | 0 | 0 | 2294 | 162.87 | 0 | 0 | 162.87
448 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | SM/08198 | TSM/006546 | Retrofitting | MVS | Yes | 4733 | 0 | 0 | 4733 | 348.01 | 0 | 0 | 348.01
449 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mohula (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In | SM/08907 | TSM/006502 | Retrofitting | MVS | Yes | 9733 | 0 | 3542 | 6191 | 674.11 | 0 | 0 | 674.11
450 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | TSM/006080 | Retrofitting | MVS | Yes | 6168 | 0 | 0 | 6168 | 434.98 | 0 | 0 | 434.98
451 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08915 | TSM/006506 | Retrofitting | MVS | Yes | 13322 | 0 | 11700 | 1622 | 983.07 | 0 | 0 | 983.07
452 | MURSHIDABAD | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joykrishnapur (313880) of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under M | SM/09742 | TSM/007540 | Retrofitting | SVS | Yes | 2241 | 0 | 0 | 2241 | 191.97 | 0 | 0 | 191.97
453 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kanupur ( 314992 ) and Ramchandrabati (313992) of Raghunathganj - I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I B | SM/09750 | TSM/007514 | Retrofitting | MVS | Yes | 3379 | 600 | 0 | 3979 | 265.85 | 0 | 0 | 265.85
454 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kolan Radhakantapur (314523) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis | SM/09754 | TSM/007520 | Retrofitting | SVS | Yes | 1260 | 0 | 0 | 1260 | 94.97 | 0 | 0 | 94.97
455 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad | SM/09757 | TSM/007523 | Retrofitting | SVS | Yes | 1142 | 0 | 0 | 1142 | 86.3 | 0 | 0 | 86.3
456 | MURSHIDABAD | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | TSM/008709 | Augmentation | SVS | Yes | 1137 | 0 | 765 | 372 | 441.86 | 0 | 31.1 | 410.76
457 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | TSM/010302 | Augmentation | MVS | Yes | 5526 | 0 | 4536 | 990 | 953.7 | 0 | 0 | 953.7
458 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat | SM/12578 | TSM/011669 | Augmentation | MVS | Yes | 976 | 0 | 0 | 976 | 579.64 | 0 | 0 | 579.64
459 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-II | SM/07669 | TSM/006118 | Retrofitting | SVS | Yes | 1980 | 0 | 0 | 1980 | 151.27 | 0 | 0 | 151.27
460 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II | SM/12580 | TSM/011935 | Augmentation | MVS | Yes | 631 | 0 | 0 | 631 | 244.68 | 0 | 0 | 244.68
461 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/11197 | TSM/010310 | Augmentation | MVS | Yes | 823 | 981 | 0 | 1804 | 595.94 | 0 | 0 | 595.94
462 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF MIRZAPUR (EXCEPT GANKAR MOUZA) BLOCK-RAGHUNATHGANJ-I | SM/11220 | TSM/008647 | Augmentation | MVS | Yes | 4288 | 0 | 987 | 3301 | 417.3 | 0 | 40.12 | 377.18
463 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11567 | TSM/010769 | Augmentation | MVS | Yes | 5613 | 0 | 5508 | 105 | 723.92 | 0 | 0 | 723.92
464 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. | SM/12740 | TSM/011878 | Augmentation | MVS | Yes | 138 | 0 | 0 | 138 | 102.8 | 0 | 0 | 102.8
465 | MURSHIDABAD | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Jamna (315232) of Mahalandi Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Kandi Block of Murshidabad District Under Murshidabad Division PheDte. | SM/11233 | TSM/008715 | Augmentation | MVS | Yes | 498 | 0 | 0 | 498 | 222.96 | 0 | 0 | 222.96
466 | MURSHIDABAD | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Ramnarayanpur (314614) of Narasinghpur Ground water based water supply scheme for Arsenic Affected Areas of Jalangi Block in Murshidabad District under Murshidabad Division, P.H.E. | SM/11234 | TSM/008698 | Augmentation | MVS | Yes | 230 | 0 | 0 | 230 | 159.1 | 0 | 0 | 159.1
467 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Garibpur, Chandpur, Pardiar (314710, 314711, 314712) of Garibpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Bl | SM/08277 | TSM/006066 | Retrofitting | MVS | Yes | 5674 | 0 | 0 | 5674 | 418.69 | 0 | 0 | 418.69
468 | MURSHIDABAD | TENTULIA AND ADJOINING MOUJAS PWSS | SM/13998 | TSM/015024 | New | MVS | Yes | 654 | 0 | 0 | 654 | 337.8 | 0 | 0 | 337.8
469 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | TSM/017305 | Augmentation | MVS | Yes | 889 | 0 | 0 | 889 | 988.06 | 0 | 0 | 988.06
470 | MURSHIDABAD | JAJAN AND ADJOINING MOUJAS PWSS | SM/13925 | TSM/015214 | New | MVS | Yes | 1544 | 0 | 0 | 1544 | 467.74 | 0 | 0 | 467.74
471 | MURSHIDABAD | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14951 | TSM/017573 | Augmentation | MVS | Yes | 121 | 0 | 0 | 121 | 557.12 | 0 | 0 | 557.12
472 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14833 | TSM/017191 | Augmentation | SVS | Yes | 414 | 0 | 65 | 349 | 474.11 | 0 | 2.64 | 471.47
473 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13995 | TSM/015133 | Augmentation | MVS | Yes | 4965 | 0 | 1739 | 3226 | 621.73 | 0 | 70.69 | 551.04
474 | MURSHIDABAD | Augmentation of Bali Zone-III pipe water supply scheme . | SM/15228 | TSM/016317 | Augmentation | SVS | Yes | 363 | 0 | 0 | 363 | 842.2 | 0 | 0 | 842.2
475 | MURSHIDABAD | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. | SM/14950 | TSM/015856 | Augmentation | SVS | Yes | 673 | 0 | 0 | 673 | 509.81 | 0 | 0 | 509.81
476 | MURSHIDABAD | GHORAMARA PIPED WATER SUPPLY SCHEME. | SM/15049 | TSM/017524 | New | MVS | Yes | 567 | 0 | 0 | 567 | 704.88 | 0 | 0 | 704.88
477 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | TSM/014869 | Augmentation | MVS | Yes | 2296 | 0 | 473 | 1823 | 666.8 | 0 | 19.23 | 647.58
478 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | TSM/006508 | Retrofitting | MVS | Yes | 11793 | 0 | 7305 | 4488 | 865.34 | 0 | 0 | 865.34
479 | MURSHIDABAD | Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District . | SM/16242 | TSM/018616 | Augmentation | MVS | Yes | 528 | 0 | 0 | 528 | 500.75 | 0 | 0 | 500.75
480 | MURSHIDABAD | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16266 | TSM/017650 | New | MVS | Yes | 2334 | 0 | 0 | 2334 | 904.77 | 0 | 0 | 904.77
481 | MURSHIDABAD | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16277 | TSM/015991 | New | MVS | Yes | 3012 | 0 | 0 | 3012 | 842.7 | 0 | 0 | 842.7
482 | MURSHIDABAD | Augmentation of Bhasaipaikar Zone- II A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16239 | TSM/018228 | Augmentation | SVS | Yes | 967 | 0 | 0 | 967 | 820.76 | 0 | 0 | 820.76
483 | MURSHIDABAD | Mini piped water supply scheme (maximum 100 households) Village-Arazi Saikuli, Block-Murshidabad -Jiaganj, District- Murshidabad. | SM/16431 | TSM/018035 | New | SVS | Yes | 84 | 0 | 0 | 84 | 38.81 | 0 | 0 | 38.81
484 | MURSHIDABAD | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Pashchim Gobindapur, Block- Murshidabad Jiaganj, District- Murshidabad. | SM/16438 | TSM/017906 | New | SVS | Yes | 48 | 0 | 0 | 48 | 34.17 | 0 | 0 | 34.17
485 | MURSHIDABAD | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE ¿ BILGOBRA , BLOCK- BHAGAWANGOLA-I, DISTRICT MURSHIDABAD. | SM/16439 | TSM/013375 | New | SVS | Yes | 55 | 0 | 0 | 55 | 36.06 | 0 | 0 | 36.06
486 | MURSHIDABAD | GOKUL CHAK PIPED WATER SUPPLY SCHEME . | SM/16043 | TSM/017674 | New | SVS | Yes | 834 | 0 | 0 | 834 | 413.88 | 0 | 0 | 413.88
487 | MURSHIDABAD | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | TSM/016372 | New | MVS | Yes | 1831 | 0 | 0 | 1831 | 590.51 | 0 | 0 | 590.51
488 | MURSHIDABAD | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16172 | TSM/018056 | Augmentation | SVS | Yes | 360 | 0 | 0 | 360 | 471.99 | 0 | 0 | 471.99
489 | MURSHIDABAD | Augmentation of Jaykrishnapur Zone- I Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16174 | TSM/018309 | Augmentation | SVS | Yes | 557 | 0 | 0 | 557 | 641.72 | 0 | 0 | 641.72
490 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15919 | TSM/016009 | Augmentation | MVS | Yes | 4135 | 0 | 1827 | 2308 | 780.33 | 0 | 74.27 | 706.06
491 | MURSHIDABAD | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16280 | TSM/018442 | New | MVS | Yes | 620 | 0 | 0 | 620 | 252.27 | 0 | 0 | 252.27
492 | MURSHIDABAD | CHAK RAMPRASAD PIPED WATER SUPPLY SCHEME, BLOCK -JALANGI ,DIST - MURSHIDABAD. | SM/16209 | TSM/018148 | New | SVS | Yes | 107 | 0 | 0 | 107 | 40.62 | 0 | 0 | 40.62
493 | MURSHIDABAD | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16397 | TSM/017307 | Augmentation | MVS | Yes | 1579 | 0 | 223 | 1356 | 828.77 | 0 | 9.06 | 819.71
494 | MURSHIDABAD | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. | SM/16566 | TSM/018285 | Augmentation | MVS | Yes | 105 | 0 | 0 | 105 | 254.4 | 0 | 0 | 254.4
495 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | TSM/013096 | Augmentation | MVS | Yes | 366 | 0 | 190 | 176 | 603 | 0 | 7.72 | 595.28
496 | MURSHIDABAD | GOBINDAPUR PWSS | SM/16784 | TSM/017597 | New | SVS | Yes | 755 | 0 | 0 | 755 | 422.85 | 0 | 0 | 422.85
497 | MURSHIDABAD | KISMATTATLA AND ADJOINING MOUJAS PWSS | SM/16786 | TSM/017660 | New | MVS | Yes | 890 | 0 | 0 | 890 | 517.85 | 0 | 0 | 517.85
498 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-III, Block- Berhampore, District- Murshidabad. | SM/16812 | TSM/018012 | New | SVS | Yes | 47 | 0 | 0 | 47 | 34.04 | 0 | 0 | 34.04
499 | MURSHIDABAD | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. | SM/15943 | TSM/016576 | New | SVS | Yes | 1316 | 0 | 0 | 1316 | 849.64 | 0 | 0 | 849.64
500 | MURSHIDABAD | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | TSM/015798 | Augmentation | MVS | Yes | 880 | 0 | 62 | 818 | 959.64 | 0 | 2.52 | 957.12
501 | MURSHIDABAD | BHAGWANGOLA AND ADJOING MOUJAS PWSS | SM/16780 | TSM/017654 | New | SVS | Yes | 2896 | 0 | 0 | 2896 | 991.57 | 0 | 0 | 991.57
502 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramnapara ground water supply scheme | SM/07229 | TSM/006056 | Retrofitting | SVS | Yes | 202 | 0 | 0 | 202 | 18.59 | 0 | 0 | 18.59
503 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -III PIPED WATER SUPPLY SCHEME. | SM/19125 | TSM/017794 | Augmentation | MVS | Yes | 1844 | 0 | 0 | 1844 | 1124.55 | 0 | 0 | 1124.55
504 | MURSHIDABAD | CHACHANDA PIPED WATER SUPPLY SCHEME. | SM/18382 | TSM/016589 | New | SVS | Yes | 3653 | 0 | 0 | 3653 | 1131.75 | 0 | 0 | 1131.75
505 | MURSHIDABAD | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME. | SM/18982 | TSM/021537 | Augmentation | SVS | No | 834 | 0 | 0 | 834 | 220.24 | 0 | 0 | 220.24
506 | MURSHIDABAD | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | TSM/017622 | New | SVS | Yes | 6219 | 0 | 0 | 6219 | 1865.49 | 0 | 0 | 1865.49
507 | MURSHIDABAD | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | TSM/015208 | New | MVS | Yes | 6117 | 0 | 0 | 6117 | 1476.45 | 0 | 0 | 1476.45
508 | MURSHIDABAD | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | TSM/016365 | Augmentation | MVS | Yes | 531 | 0 | 0 | 531 | 1196.31 | 0 | 0 | 1196.31
509 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. | SM/18702 | TSM/018899 | Augmentation | SVS | Yes | 3406 | 0 | 0 | 3406 | 1288.62 | 0 | 0 | 1288.62
510 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur Chak ( 314703 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District | SM/07914 | TSM/006576 | Retrofitting | SVS | Yes | 794 | 1 | 0 | 795 | 63.09 | 0 | 0 | 63.09
511 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M | SM/07924 | TSM/006711 | Retrofitting | MVS | Yes | 0 | 1222 | 0 | 1222 | 66.03 | 0 | 0 | 66.03
512 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Durgapur (313864) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) | SM/07512 | TSM/006557 | Retrofitting | SVS | Yes | 878 | 0 | 0 | 878 | 66.82 | 0 | 0 | 66.82
513 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07513 | TSM/006558 | Retrofitting | MVS | Yes | 807 | 0 | 0 | 807 | 61.91 | 0 | 0 | 61.91
514 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sekhalipara (314580) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07517 | TSM/006563 | Retrofitting | SVS | Yes | 1005 | 0 | 0 | 1005 | 77.39 | 0 | 0 | 77.39
515 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagharpur Ramna (314665) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-V) | SM/07671 | TSM/006128 | Retrofitting | SVS | Yes | 1840 | 0 | 0 | 1840 | 138.2 | 0 | 0 | 138.2
516 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) | SM/07689 | TSM/006427 | Retrofitting | SVS | Yes | 449 | 0 | 0 | 449 | 32.25 | 0 | 0 | 32.25
517 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme | SM/06981 | TSM/006036 | Retrofitting | MVS | Yes | 1472 | 1 | 0 | 1473 | 94.89 | 0 | 0 | 94.89
518 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Kosbagoas (VillageCode-314795) under command area of Kosbagoas ground water supply scheme (Part-A) | SM/06983 | TSM/006059 | Retrofitting | SVS | Yes | 1453 | 0 | 0 | 1453 | 93.43 | 0 | 0 | 93.43
519 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Godhanpara ( 314581) & Babaltali ( 314583 ) of Godhanpara under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshida | SM/08100 | TSM/006574 | Retrofitting | MVS | Yes | 5365 | 0 | 0 | 5365 | 420.14 | 0 | 0 | 420.14
520 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Naopukuria (Zone-K) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/07702 | TSM/006883 | Retrofitting | SVS | Yes | 3267 | 2 | 0 | 3269 | 240.81 | 0 | 0 | 240.81
521 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B) | SM/07725 | TSM/006435 | Retrofitting | SVS | Yes | 1722 | 0 | 0 | 1722 | 119.17 | 0 | 0 | 119.17
522 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | TSM/006889 | Retrofitting | MVS | Yes | 14430 | 0 | 9837 | 4593 | 1063.3 | 0 | 0 | 1063.3
523 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07276 | TSM/006083 | Retrofitting | SVS | Yes | 1305 | 0 | 0 | 1305 | 95.4 | 0 | 0 | 95.4
524 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | TSM/006099 | Retrofitting | MVS | Yes | 999 | 0 | 0 | 999 | 88.35 | 0 | 0 | 88.35
525 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C) | SM/07731 | TSM/006442 | Retrofitting | SVS | Yes | 1397 | 1 | 0 | 1398 | 94.33 | 0 | 0 | 94.33
526 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area o | SM/07235 | TSM/006075 | Retrofitting | SVS | Yes | 1200 | 112 | 0 | 1312 | 81.52 | 0 | 0 | 81.52
527 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kulberia Village (Code-315685) Under Command Area Of Andulberia Ground Water Supply Scheme (Part-A) | SM/07696 | TSM/006479 | Retrofitting | SVS | Yes | 804 | 0 | 0 | 804 | 57.19 | 0 | 0 | 57.19
528 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Panchnanpur, Baniakhali (314655 & 314660) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Dist | SM/07288 | TSM/006115 | Retrofitting | MVS | Yes | 1297 | 0 | 0 | 1297 | 99.99 | 0 | 0 | 99.99
529 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Manik Nagar (314694) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II) | SM/07291 | TSM/006123 | Retrofitting | SVS | Yes | 665 | 0 | 0 | 665 | 51.34 | 0 | 0 | 51.34
530 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sambhu Nagar, Ramna Etbarnagar Basantapur (314628) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad | SM/07295 | TSM/006135 | Retrofitting | MVS | Yes | 1229 | 0 | 0 | 1229 | 93.16 | 0 | 0 | 93.16
531 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chhakka Nagar, Kochgiria (314478 & 314481) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Mur | SM/07684 | TSM/006106 | Retrofitting | MVS | Yes | 1479 | 0 | 0 | 1479 | 112.77 | 0 | 0 | 112.77
532 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | TSM/006087 | Retrofitting | MVS | Yes | 3962 | 415 | 0 | 4377 | 299.57 | 0 | 0 | 299.57
533 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hamidhati Pilkhandi & Purbbagram (315713 & 315718 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murs | SM/07509 | TSM/006547 | Retrofitting | MVS | Yes | 1276 | 0 | 0 | 1276 | 97.74 | 0 | 0 | 97.74
534 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bhikan (Code-314211), Ganespur (Code-314215) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(P | SM/07715 | TSM/006431 | Retrofitting | MVS | Yes | 1030 | 0 | 133 | 897 | 69.44 | 0 | 0 | 69.44
535 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bewa (P) (313794) of Bewa-II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-II) | SM/07681 | TSM/006085 | Retrofitting | MVS | Yes | 4130 | 0 | 1325 | 2805 | 290.84 | 0 | 0 | 290.84
536 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Char Molladanga (Code-314558) In The Command Area Of Benipur Ground Water Supply Scheme (Part-C) Under Bhagwangola | SM/07791 | TSM/006464 | Retrofitting | SVS | Yes | 940 | 0 | 0 | 940 | 63.22 | 0 | 0 | 63.22
537 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari (314589) of Katlamari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District (PART-I) | SM/08188 | TSM/006089 | Retrofitting | SVS | Yes | 7840 | 0 | 3940 | 3900 | 578.36 | 0 | 0 | 578.36
538 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | TSM/006094 | Retrofitting | MVS | Yes | 4523 | 356 | 0 | 4879 | 349.63 | 0 | 0 | 349.63
539 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division | SM/08904 | TSM/006499 | Retrofitting | MVS | Yes | 5339 | 0 | 684 | 4655 | 385.71 | 0 | 0 | 385.71
540 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brahmanigram ( 314319 ) and Bergram ( 314328 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of | SM/09747 | TSM/007511 | Retrofitting | MVS | Yes | 1216 | 1 | 0 | 1217 | 94.96 | 0 | 0 | 94.96
541 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan | SM/09737 | TSM/007515 | Retrofitting | MVS | Yes | 12336 | 0 | 4978 | 7358 | 875.99 | 0 | 0 | 875.99
542 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 313951 ) and Kadamtala ( 313953 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Bl | SM/09752 | TSM/007518 | Retrofitting | MVS | Yes | 618 | 30 | 0 | 648 | 46.25 | 0 | 0 | 46.25
543 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debottar Lakshminarayanpur ( 314678 ) of Jitpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District und | SM/09843 | TSM/007501 | Retrofitting | SVS | Yes | 562 | 0 | 0 | 562 | 44.72 | 0 | 0 | 44.72
544 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | TSM/010308 | Augmentation | SVS | Yes | 5024 | 0 | 4524 | 500 | 929.25 | 0 | 0 | 929.25
545 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Srikrishnapur ( 314737 ) of Aminabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshid | SM/09846 | TSM/007504 | Retrofitting | SVS | Yes | 845 | 0 | 0 | 845 | 67.42 | 0 | 0 | 67.42
546 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pairmari ( 314672 ) of Dhulauri under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Di | SM/09847 | TSM/007505 | Retrofitting | SVS | Yes | 776 | 0 | 0 | 776 | 67.61 | 0 | 0 | 67.61
547 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10997 | TSM/010739 | Augmentation | MVS | Yes | 1882 | 0 | 1412 | 470 | 332.05 | 0 | 0 | 332.05
548 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sripatipur, Dakshin Panchnanpur, Char Syampur (314661, 314657 & 314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Do | SM/07289 | TSM/006117 | Retrofitting | MVS | Yes | 1016 | 93 | 0 | 1109 | 78.74 | 0 | 0 | 78.74
549 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | TSM/011661 | Augmentation | MVS | Yes | 1907 | 0 | 0 | 1907 | 671.73 | 0 | 0 | 671.73
550 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. | SM/12586 | TSM/011668 | Augmentation | MVS | Yes | 552 | 0 | 0 | 552 | 512.37 | 0 | 0 | 512.37
551 | MURSHIDABAD | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | TSM/011571 | Augmentation | MVS | Yes | 1363 | 0 | 1215 | 148 | 361.5 | 0 | 49.39 | 312.11
552 | MURSHIDABAD | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Nimtita (313863) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District under Murshidabad Division PheDte. | SM/11215 | TSM/008706 | Augmentation | MVS | Yes | 489 | 0 | 0 | 489 | 164.09 | 0 | 0 | 164.09
553 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | TSM/010853 | Augmentation | SVS | Yes | 4515 | 0 | 3346 | 1169 | 995.43 | 0 | 139.59 | 855.84
554 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | TSM/010866 | Augmentation | MVS | Yes | 2563 | 0 | 1552 | 1011 | 786.26 | 0 | 63.09 | 723.18
555 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | TSM/011877 | Augmentation | MVS | Yes | 1630 | 0 | 0 | 1630 | 553.93 | 0 | 0 | 553.93
556 | MURSHIDABAD | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | TSM/011535 | Augmentation | MVS | Yes | 1238 | 0 | 0 | 1238 | 937.92 | 0 | 0 | 937.92
557 | MURSHIDABAD | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | TSM/014684 | New | MVS | Yes | 2160 | 0 | 0 | 2160 | 635.19 | 0 | 0 | 635.19
558 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF DHUSARIPARA BLOCK-SAMSHERGANJ | SM/11229 | TSM/008655 | Augmentation | SVS | Yes | 4486 | 0 | 1392 | 3094 | 568.17 | 0 | 56.58 | 511.58
559 | MURSHIDABAD | LOHADAHA AND ADJOINING MOUJAS PWSS | SM/13727 | TSM/014633 | New | MVS | Yes | 2489 | 0 | 0 | 2489 | 690.38 | 0 | 0 | 690.38
560 | MURSHIDABAD | PUNIA AND ADJOINING MOUJAS PWSS | SM/13933 | TSM/015229 | New | MVS | Yes | 2799 | 0 | 0 | 2799 | 714.78 | 0 | 0 | 714.78
561 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . | SM/14429 | TSM/012746 | Augmentation | SVS | Yes | 467 | 0 | 0 | 467 | 427.57 | 0 | 0 | 427.57
562 | MURSHIDABAD | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | TSM/016002 | Augmentation | MVS | Yes | 1298 | 0 | 0 | 1298 | 982.3 | 0 | 0 | 982.3
563 | MURSHIDABAD | HAMIDPUR AND ADJOINING MOUJAS PWSS | SM/14867 | TSM/017502 | New | MVS | Yes | 944 | 4246 | 0 | 5190 | 271.8 | 0 | 0 | 271.8
564 | MURSHIDABAD | BIPRA SEKHAR AND ADJOING MOUJAS PWSS | SM/14868 | TSM/017298 | New | MVS | Yes | 2162 | 0 | 0 | 2162 | 864.73 | 0 | 0 | 864.73
565 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14044 | TSM/016396 | Augmentation | MVS | Yes | 375 | 0 | 0 | 375 | 759.79 | 0 | 0 | 759.79
566 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | TSM/016394 | Augmentation | MVS | Yes | 410 | 0 | 0 | 410 | 753.28 | 0 | 0 | 753.28
567 | MURSHIDABAD | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME | SM/14067 | TSM/017856 | Augmentation | MVS | Yes | 1591 | 10 | 0 | 1601 | 998.3 | 0 | 0 | 998.3
568 | MURSHIDABAD | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14068 | TSM/017786 | Augmentation | MVS | Yes | 719 | 0 | 0 | 719 | 995.8 | 0 | 0 | 995.8
569 | MURSHIDABAD | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14922 | TSM/017580 | Augmentation | SVS | Yes | 618 | 0 | 0 | 618 | 855.81 | 0 | 0 | 855.81
570 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | TSM/012743 | Augmentation | MVS | Yes | 719 | 144 | 0 | 863 | 857.82 | 0 | 0 | 857.82
571 | MURSHIDABAD | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS | SM/14503 | TSM/015350 | New | MVS | Yes | 620 | 0 | 0 | 620 | 277.07 | 0 | 0 | 277.07
572 | MURSHIDABAD | KOGRAM AND ADJOINING MOUJAS PWSS | SM/14507 | TSM/015608 | New | MVS | Yes | 2256 | 0 | 0 | 2256 | 790.62 | 0 | 0 | 790.62
573 | MURSHIDABAD | Augmentation of Bharatpur Zone-IB Water Supply Scheme Block - Bharatpur - I , Dist- Murshidabad. | SM/16247 | TSM/018008 | Augmentation | SVS | Yes | 529 | 985 | 0 | 1514 | 541.38 | 0 | 0 | 541.38
574 | MURSHIDABAD | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | TSM/016094 | Augmentation | SVS | Yes | 2614 | 0 | 0 | 2614 | 599.09 | 0 | 0 | 599.09
575 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) | SM/07926 | TSM/006585 | Retrofitting | SVS | Yes | 427 | 0 | 0 | 427 | 38.41 | 0 | 0 | 38.41
576 | MURSHIDABAD | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. | SM/16429 | TSM/019617 | New | SVS | Yes | 209 | 0 | 0 | 209 | 113.82 | 0 | 0 | 113.82
577 | MURSHIDABAD | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAR SUJAPUR , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. | SM/16430 | TSM/019612 | New | SVS | Yes | 135 | 0 | 0 | 135 | 75.32 | 0 | 0 | 75.32
578 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-I, Block- Berhampore, District- Murshidabad. | SM/16432 | TSM/018020 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
579 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Chandabag, Block- Murshidabad-Jiagunj, District- Murshidabad. | SM/16435 | TSM/017981 | New | SVS | Yes | 46 | 0 | 0 | 46 | 33.9 | 0 | 0 | 33.9
580 | MURSHIDABAD | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16544 | TSM/015920 | Augmentation | MVS | Yes | 1856 | 0 | 301 | 1555 | 841.25 | 0 | 12.24 | 829.02
581 | MURSHIDABAD | Augmentation of Rejuvenation of Arjunpur (Zone-III ) PIPED WATER SUPPLY SCHEME | SM/16555 | TSM/017172 | Augmentation | MVS | Yes | 1648 | 0 | 308 | 1340 | 789.76 | 0 | 12.52 | 777.24
582 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-I, Block- Berhampore, District- Murshidabad. | SM/16044 | TSM/018029 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
583 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-II, Block- Berhampore, District- Murshidabad. | SM/16046 | TSM/018019 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
584 | MURSHIDABAD | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/16178 | TSM/016611 | Augmentation | MVS | Yes | 2696 | 0 | 682 | 2014 | 800.76 | 0 | 27.72 | 773.04
585 | MURSHIDABAD | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/16283 | TSM/017543 | Augmentation | MVS | Yes | 175 | 0 | 126 | 49 | 785.06 | 0 | 5.12 | 779.94
586 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-II, Block- Lalgola, District- Murshidabad. | SM/16211 | TSM/017967 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
587 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di | SM/07919 | TSM/006580 | Retrofitting | MVS | Yes | 2930 | 3535 | 0 | 6465 | 235.36 | 0 | 0 | 235.36
588 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE | SM/10013 | TSM/008745 | Augmentation | SVS | Yes | 729 | 0 | 530 | 199 | 274.1 | 0 | 21.54 | 252.56
589 | MURSHIDABAD | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Kuchidanga, Block- Lalgola, District- Murshidabad. | SM/16503 | TSM/017900 | New | SVS | Yes | 29 | 0 | 0 | 29 | 31.65 | 0 | 0 | 31.65
590 | MURSHIDABAD | Augmentation of Mahadebnagar Zone- II B Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16416 | TSM/018055 | Augmentation | MVS | Yes | 1729 | 0 | 0 | 1729 | 541.33 | 0 | 0 | 541.33
591 | MURSHIDABAD | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | TSM/016587 | New | SVS | Yes | 899 | 0 | 0 | 899 | 497.21 | 0 | 0 | 497.21
592 | MURSHIDABAD | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | TSM/016156 | New | MVS | Yes | 1374 | 0 | 0 | 1374 | 666.66 | 0 | 0 | 666.66
593 | MURSHIDABAD | KULGACHI AND ITS ADJOINING MOUJAS PWSS | SM/16302 | TSM/017656 | New | MVS | Yes | 1286 | 0 | 0 | 1286 | 589.74 | 0 | 0 | 589.74
594 | MURSHIDABAD | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | TSM/018428 | New | MVS | Yes | 2038 | 0 | 0 | 2038 | 615.3 | 0 | 0 | 615.3
595 | MURSHIDABAD | Augmentation of Dakshin Kanda Zone- I B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16425 | TSM/018266 | Augmentation | MVS | Yes | 1085 | 0 | 0 | 1085 | 556.98 | 0 | 0 | 556.98
596 | MURSHIDABAD | KESABPUR AND ADJOINING MOUJAS PWSS | SM/16788 | TSM/017602 | New | MVS | Yes | 1256 | 0 | 0 | 1256 | 661.59 | 0 | 0 | 661.59
597 | MURSHIDABAD | RANAGRAM AND ADJOINIG MOUJAS PWSS | SM/16052 | TSM/018246 | New | SVS | Yes | 510 | 0 | 0 | 510 | 198.62 | 0 | 0 | 198.62
598 | MURSHIDABAD | BABARPUR AND ADJOINING MOUJAS PWSS | SM/16814 | TSM/017591 | New | SVS | Yes | 766 | 0 | 0 | 766 | 255.65 | 0 | 0 | 255.65
599 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. | SM/16764 | TSM/015775 | Augmentation | MVS | Yes | 88 | 3 | 0 | 91 | 373.08 | 0 | 0 | 373.08
600 | MURSHIDABAD | FATELLAPUR(CT) PIPE WATER SUPPLY SCHEME. | SM/18413 | TSM/016505 | New | SVS | Yes | 1729 | 0 | 0 | 1729 | 1029.02 | 0 | 0 | 1029.02
601 | MURSHIDABAD | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | TSM/016056 | New | SVS | Yes | 3902 | 0 | 0 | 3902 | 1356.19 | 0 | 0 | 1356.19
602 | MURSHIDABAD | BHATPARA AND ADJOINING MOUJAS | SM/18430 | TSM/014526 | New | MVS | Yes | 3444 | 0 | 0 | 3444 | 1170.19 | 0 | 0 | 1170.19
603 | MURSHIDABAD | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | TSM/016578 | New | SVS | Yes | 5123 | 0 | 0 | 5123 | 1936.25 | 0 | 0 | 1936.25
604 | MURSHIDABAD | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | TSM/017519 | New | MVS | Yes | 2197 | 0 | 0 | 2197 | 1047.42 | 0 | 0 | 1047.42
605 | MURSHIDABAD | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | TSM/017625 | New | MVS | Yes | 4532 | 0 | 0 | 4532 | 1596.9 | 0 | 0 | 1596.9
606 | MURSHIDABAD | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | TSM/018286 | Augmentation | MVS | Yes | 176 | 0 | 0 | 176 | 2018.37 | 0 | 0 | 2018.37
607 | MURSHIDABAD | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | TSM/017949 | New | SVS | Yes | 6026 | 0 | 0 | 6026 | 2107.4 | 0 | 0 | 2107.4
608 | MURSHIDABAD | SAHAJADPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/18689 | TSM/017328 | New | SVS | Yes | 6026 | 0 | 0 | 6026 | 2084.84 | 0 | 0 | 2084.84
609 | MURSHIDABAD | BHARWAN AND ADJOINING MOUJAS PWSS | SM/18452 | TSM/014939 | New | MVS | Yes | 3505 | 0 | 0 | 3505 | 1267.95 | 0 | 0 | 1267.95
610 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-I PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18740 | TSM/016113 | Augmentation | MVS | Yes | 536 | 903 | 0 | 1439 | 553.64 | 0 | 0 | 553.64
611 | MURSHIDABAD | CHARKA PIPE WATER SUPPLY SCHEME. | SM/18465 | TSM/016577 | New | SVS | Yes | 2278 | 0 | 0 | 2278 | 1020.87 | 0 | 0 | 1020.87
612 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | TSM/017788 | Augmentation | MVS | Yes | 766 | 0 | 0 | 766 | 1703.43 | 0 | 0 | 1703.43
613 | MURSHIDABAD | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | TSM/017596 | New | MVS | Yes | 4386 | 0 | 0 | 4386 | 1472.99 | 0 | 0 | 1472.99
614 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-J) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08107 | TSM/006505 | Retrofitting | MVS | Yes | 5364 | 0 | 3082 | 2282 | 383.46 | 0 | 0 | 383.46
615 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kupila ( 314741 ) of Kupila under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07911 | TSM/006570 | Retrofitting | SVS | Yes | 2144 | 2 | 0 | 2146 | 167.77 | 0 | 0 | 167.77
616 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malibbari ( 314569 ) of Malibari under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-I ) | SM/07927 | TSM/006586 | Retrofitting | SVS | Yes | 473 | 0 | 0 | 473 | 48 | 0 | 0 | 48
617 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Diar & Paraspur Diar ( 314651 & 314650 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of | SM/07515 | TSM/006560 | Retrofitting | MVS | Yes | 1170 | 0 | 0 | 1170 | 89.95 | 0 | 0 | 89.95
618 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nasipur (Code-314186) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-C) | SM/07690 | TSM/006448 | Retrofitting | SVS | Yes | 1920 | 0 | 0 | 1920 | 129.56 | 0 | 0 | 129.56
619 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mirzapur (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In | SM/07704 | TSM/006901 | Retrofitting | SVS | Yes | 767 | 4613 | 0 | 5380 | 64.01 | 0 | 0 | 64.01
620 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidaba | SM/07705 | TSM/006428 | Retrofitting | SVS | Yes | 2126 | 0 | 0 | 2126 | 143.18 | 0 | 0 | 143.18
621 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The C | SM/07724 | TSM/006434 | Retrofitting | SVS | Yes | 1454 | 0 | 0 | 1454 | 99.92 | 0 | 0 | 99.92
622 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08114 | TSM/006897 | Retrofitting | MVS | Yes | 4053 | 5187 | 0 | 9240 | 312.34 | 0 | 0 | 312.34
623 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08115 | TSM/006902 | Retrofitting | MVS | Yes | 7186 | 0 | 3728 | 3458 | 552.45 | 0 | 0 | 552.45
624 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector | SM/08117 | TSM/006904 | Retrofitting | MVS | Yes | 6774 | 70 | 0 | 6844 | 533.01 | 0 | 0 | 533.01
625 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for the Village of Aragi Kulgachi (VillageCode-314471) , Subarnamrigi (VillageCode-314473) under command area of Digha ground wate | SM/06976 | TSM/006028 | Retrofitting | SVS | Yes | 1169 | 0 | 0 | 1169 | 72.72 | 0 | 0 | 72.72
626 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Harirampur ground water supply scheme | SM/06979 | TSM/006032 | Retrofitting | MVS | Yes | 717 | 0 | 0 | 717 | 46.15 | 0 | 0 | 46.15
627 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs | SM/07277 | TSM/006098 | Retrofitting | MVS | Yes | 572 | 0 | 0 | 572 | 51.55 | 0 | 0 | 51.55
628 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilaspur Nachharerpara (314639) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Mu | SM/07286 | TSM/006112 | Retrofitting | SVS | Yes | 1352 | 153 | 0 | 1505 | 98.3 | 0 | 0 | 98.3
629 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramchandrapur ground water supply scheme | SM/07232 | TSM/006067 | Retrofitting | SVS | Yes | 250 | 0 | 0 | 250 | 21.55 | 0 | 0 | 21.55
630 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Paschim Gobindapur (VillageCode-314448)& Barbaria(Village Code-314462) under command area of Gobra ground water s | SM/07234 | TSM/006073 | Retrofitting | SVS | Yes | 1305 | 0 | 0 | 1305 | 87.8 | 0 | 0 | 87.8
631 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harharia Chak (CT) (314806) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PA | SM/07685 | TSM/006107 | Retrofitting | SVS | Yes | 1955 | 0 | 0 | 1955 | 146.33 | 0 | 0 | 146.33
632 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) | SM/07236 | TSM/006024 | Retrofitting | MVS | Yes | 837 | 0 | 0 | 837 | 58.14 | 0 | 0 | 58.14
633 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Islampur (CT) (314805) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-II | SM/07683 | TSM/006103 | Retrofitting | SVS | Yes | 2122 | 0 | 0 | 2122 | 158.56 | 0 | 0 | 158.56
634 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) | SM/07770 | TSM/006548 | Retrofitting | SVS | Yes | 2167 | 0 | 0 | 2167 | 162.06 | 0 | 0 | 162.06
635 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram | SM/07682 | TSM/006097 | Retrofitting | MVS | Yes | 1684 | 0 | 0 | 1684 | 131.02 | 0 | 0 | 131.02
636 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mahatpur (Code-314442) In The Command Area Of Telia Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block In Murshidabad | SM/07786 | TSM/006455 | Retrofitting | SVS | Yes | 235 | 151 | 0 | 386 | 16.62 | 0 | 0 | 16.62
637 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Karttikpur (Code-314220) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-C) Under Lalgola Block | SM/07787 | TSM/006460 | Retrofitting | SVS | Yes | 1220 | 0 | 0 | 1220 | 76.68 | 0 | 0 | 76.68
638 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | TSM/006709 | Retrofitting | MVS | Yes | 0 | 7823 | 0 | 7823 | 532.59 | 0 | 0 | 532.59
639 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-II Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08903 | TSM/006488 | Retrofitting | SVS | Yes | 5343 | 0 | 0 | 5343 | 362.25 | 0 | 0 | 362.25
640 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | TSM/006500 | Retrofitting | MVS | Yes | 9334 | 0 | 4842 | 4492 | 650.52 | 0 | 0 | 650.52
641 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begunbari (Zone-I) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08909 | TSM/006504 | Retrofitting | MVS | Yes | 6617 | 2879 | 0 | 9496 | 460.21 | 0 | 0 | 460.21
642 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | TSM/006887 | Retrofitting | MVS | Yes | 13110 | 0 | 7447 | 5663 | 964.85 | 0 | 0 | 964.85
643 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Popara ( 314326 ) of Sagardighi Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of Murshidabad District under M | SM/09748 | TSM/007512 | Retrofitting | SVS | Yes | 2183 | 0 | 0 | 2183 | 157.21 | 0 | 0 | 157.21
644 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dudhsar ( 315521 ) of Sarbangapur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad D | SM/09840 | TSM/007498 | Retrofitting | SVS | Yes | 361 | 0 | 0 | 361 | 29.12 | 0 | 0 | 29.12
645 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kishorpur (313961) of Kishorpur and adjonining mouzas under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad Dis | SM/09760 | TSM/007526 | Retrofitting | SVS | Yes | 847 | 0 | 0 | 847 | 66.1 | 0 | 0 | 66.1
646 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Jitpur ( 314713 ) of Garibpur (Zone- I & Zone - II) under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad D | SM/09848 | TSM/007506 | Retrofitting | SVS | Yes | 435 | 0 | 0 | 435 | 34.24 | 0 | 0 | 34.24
647 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Santoshpur (314329) &Chandanbati ( 314330 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of M | SM/09850 | TSM/007510 | Retrofitting | MVS | Yes | 1173 | 0 | 0 | 1173 | 91.63 | 0 | 0 | 91.63
648 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pradipdanga ( 315470 ) of Kismat Imadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Hariharpara Block of Murshidabad District under | SM/09851 | TSM/007495 | Retrofitting | SVS | Yes | 392 | 0 | 0 | 392 | 28.53 | 0 | 0 | 28.53
649 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | TSM/010737 | Augmentation | MVS | Yes | 3549 | 0 | 3185 | 364 | 939.08 | 0 | 0 | 939.08
650 | MURSHIDABAD | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | TSM/011687 | Augmentation | MVS | Yes | 6603 | 2783 | 0 | 9386 | 998.51 | 0 | 0 | 998.51
651 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo | SM/08908 | TSM/006882 | Retrofitting | MVS | Yes | 5174 | 0 | 1681 | 3493 | 384.82 | 0 | 0 | 384.82
652 | MURSHIDABAD | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. | SM/10811 | TSM/008652 | Augmentation | SVS | Yes | 5465 | 0 | 5291 | 174 | 694.67 | 0 | 0 | 694.67
653 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | TSM/011654 | Augmentation | MVS | Yes | 5483 | 0 | 0 | 5483 | 892.32 | 0 | 0 | 892.32
654 | MURSHIDABAD | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Melanpur, Durgapur (314744,314745,314746,314747,314753,314754,314755,314756) of Purusottampur under ground w | SM/11216 | TSM/008703 | Augmentation | MVS | Yes | 304 | 0 | 0 | 304 | 162.44 | 0 | 0 | 162.44
655 | MURSHIDABAD | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Bilpachakopra (314584) of Nabipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District under Murshidabad Divisio | SM/11218 | TSM/008705 | Augmentation | MVS | Yes | 379 | 0 | 0 | 379 | 178.49 | 0 | 0 | 178.49
656 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11565 | TSM/010750 | Augmentation | MVS | Yes | 6648 | 0 | 5506 | 1142 | 556.61 | 0 | 0 | 556.61
657 | MURSHIDABAD | JUGASWARA AND ADJOINING MOUJAS PWSS | SM/13724 | TSM/014911 | New | MVS | Yes | 792 | 0 | 0 | 792 | 369.94 | 0 | 0 | 369.94
658 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11792 | TSM/010855 | Augmentation | SVS | Yes | 3040 | 0 | 1583 | 1457 | 902.45 | 0 | 64.35 | 838.11
659 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | TSM/006894 | Retrofitting | MVS | Yes | 10847 | 0 | 4010 | 6837 | 777.42 | 0 | 0 | 777.42
660 | MURSHIDABAD | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS | SM/13488 | TSM/014516 | New | MVS | Yes | 3631 | 0 | 0 | 3631 | 640.11 | 0 | 0 | 640.11
661 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | TSM/011874 | Augmentation | MVS | Yes | 2695 | 0 | 0 | 2695 | 899.98 | 0 | 0 | 899.98
662 | MURSHIDABAD | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/13486 | TSM/014188 | Augmentation | MVS | Yes | 1222 | 0 | 456 | 766 | 655.64 | 0 | 18.54 | 637.11
663 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. | SM/12738 | TSM/011934 | Augmentation | MVS | Yes | 299 | 0 | 0 | 299 | 231.37 | 0 | 0 | 231.37
664 | MURSHIDABAD | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | TSM/015025 | New | MVS | Yes | 2218 | 0 | 0 | 2218 | 669.58 | 0 | 0 | 669.58
665 | MURSHIDABAD | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | TSM/014465 | Augmentation | MVS | Yes | 671 | 0 | 0 | 671 | 838.18 | 0 | 0 | 838.18
666 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | TSM/017204 | Augmentation | MVS | Yes | 857 | 518 | 0 | 1375 | 499.1 | 0 | 0 | 499.1
667 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | TSM/014664 | Augmentation | MVS | Yes | 3301 | 0 | 1214 | 2087 | 978.6 | 0 | 49.35 | 929.25
668 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | TSM/015850 | Augmentation | MVS | Yes | 1495 | 0 | 80 | 1415 | 390.02 | 0 | 3.25 | 386.77
669 | MURSHIDABAD | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | TSM/016325 | Augmentation | SVS | Yes | 342 | 0 | 0 | 342 | 804.99 | 0 | 0 | 804.99
670 | MURSHIDABAD | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | TSM/014461 | Augmentation | MVS | Yes | 369 | 0 | 0 | 369 | 775.12 | 0 | 0 | 775.12
671 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . | SM/14739 | TSM/011839 | Augmentation | MVS | Yes | 214 | 583 | 0 | 797 | 244.16 | 0 | 0 | 244.16
672 | MURSHIDABAD | AUGMENTATION OF KAKRAMARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK - SUTI-II , DISTRICT - MURSHIDABAD. | SM/14945 | TSM/014906 | Augmentation | MVS | Yes | 3685 | 360 | 0 | 4045 | 941.94 | 0 | 0 | 941.94
673 | MURSHIDABAD | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | TSM/014454 | New | MVS | Yes | 1203 | 0 | 0 | 1203 | 492.25 | 0 | 0 | 492.25
674 | MURSHIDABAD | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15069 | TSM/017552 | Augmentation | SVS | Yes | 2416 | 0 | 504 | 1912 | 998.83 | 0 | 20.49 | 978.35
675 | MURSHIDABAD | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | TSM/014919 | New | MVS | Yes | 4429 | 0 | 0 | 4429 | 1141.76 | 0 | 0 | 1141.76
676 | MURSHIDABAD | Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16243 | TSM/015916 | Augmentation | MVS | Yes | 1419 | 0 | 0 | 1419 | 660.65 | 0 | 0 | 660.65
677 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16265 | TSM/016696 | Augmentation | SVS | Yes | 123 | 0 | 121 | 2 | 429.02 | 0 | 4.92 | 424.1
678 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-B) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/15267 | TSM/015134 | Augmentation | MVS | Yes | 4965 | 0 | 1740 | 3225 | 888.21 | 0 | 70.73 | 817.48
679 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | TSM/017208 | Augmentation | MVS | Yes | 1329 | 0 | 170 | 1159 | 820.5 | 0 | 6.91 | 813.59
680 | MURSHIDABAD | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | TSM/016301 | Augmentation | MVS | Yes | 250 | 0 | 0 | 250 | 436.62 | 0 | 0 | 436.62
681 | MURSHIDABAD | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Sibnagar Zone IV, Block- Nawda, District- Murshidabad. | SM/16437 | TSM/017930 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
682 | MURSHIDABAD | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16546 | TSM/016061 | Augmentation | MVS | Yes | 614 | 0 | 302 | 312 | 541.56 | 0 | 12.28 | 529.29
683 | MURSHIDABAD | BAURIPUNI PIPED WATER SUPPLY SCHEME. | SM/16551 | TSM/016580 | New | SVS | Yes | 1222 | 0 | 0 | 1222 | 813.92 | 0 | 0 | 813.92
684 | MURSHIDABAD | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - DURGAPUR ZONE-IV, BLOCK - LALGOLA, DISTRICT - MURSHIDABAD. | SM/16049 | TSM/017920 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
685 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16402 | TSM/017462 | Augmentation | SVS | Yes | 995 | 0 | 993 | 2 | 681.2 | 0 | 40.28 | 640.92
686 | MURSHIDABAD | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | TSM/018304 | Augmentation | SVS | Yes | 1014 | 0 | 0 | 1014 | 800.01 | 0 | 0 | 800.01
687 | MURSHIDABAD | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | TSM/018058 | Augmentation | SVS | Yes | 360 | 0 | 0 | 360 | 471.99 | 0 | 0 | 471.99
688 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. | SM/16177 | TSM/017716 | Augmentation | SVS | Yes | 735 | 0 | 0 | 735 | 662.59 | 0 | 0 | 662.59
689 | MURSHIDABAD | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16410 | TSM/017905 | Augmentation | MVS | Yes | 1149 | 0 | 0 | 1149 | 453.71 | 0 | 0 | 453.71
690 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | TSM/016012 | Augmentation | MVS | Yes | 1308 | 0 | 1024 | 284 | 610.97 | 0 | 0 | 610.97
691 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15923 | TSM/016730 | Augmentation | SVS | Yes | 1621 | 0 | 1182 | 439 | 633 | 0 | 48.05 | 584.95
692 | MURSHIDABAD | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16274 | TSM/015891 | New | MVS | Yes | 3629 | 0 | 0 | 3629 | 932.74 | 0 | 0 | 932.74
693 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Accoan (315979) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Buwan Block of Murshidabad District under Murshidabad Divisi | SM/09835 | TSM/007492 | Retrofitting | SVS | Yes | 146 | 0 | 0 | 146 | 13.03 | 0 | 0 | 13.03
694 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II | SM/11198 | TSM/008642 | Augmentation | MVS | Yes | 6929 | 0 | 5385 | 1544 | 592.03 | 0 | 0 | 592.03
695 | MURSHIDABAD | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. | SM/16412 | TSM/017922 | Augmentation | MVS | Yes | 1108 | 0 | 0 | 1108 | 466.43 | 0 | 0 | 466.43
696 | MURSHIDABAD | Augmentation of Panchthupi Zone-I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/16413 | TSM/017923 | Augmentation | MVS | Yes | 2801 | 0 | 0 | 2801 | 720.5 | 0 | 0 | 720.5
697 | MURSHIDABAD | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | TSM/015748 | New | SVS | Yes | 814 | 0 | 0 | 814 | 439.33 | 0 | 0 | 439.33
698 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. | SM/16418 | TSM/017431 | Augmentation | MVS | Yes | 370 | 0 | 0 | 370 | 578.91 | 0 | 0 | 578.91
699 | MURSHIDABAD | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16565 | TSM/018597 | Augmentation | SVS | Yes | 1078 | 0 | 0 | 1078 | 803.55 | 0 | 0 | 803.55
700 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15918 | TSM/016006 | Augmentation | MVS | Yes | 4135 | 0 | 1827 | 2308 | 518.94 | 0 | 74.27 | 444.67
701 | MURSHIDABAD | GUNDIRIA AND ADJIONING MOUJAS PWSS | SM/16110 | TSM/017594 | New | SVS | Yes | 687 | 0 | 0 | 687 | 216.8 | 0 | 0 | 216.8
702 | MURSHIDABAD | MALIPUR PIPED WATER SUPPLY SCHEME. | SM/16785 | TSM/017831 | New | SVS | Yes | 446 | 0 | 0 | 446 | 421.98 | 0 | 0 | 421.98
703 | MURSHIDABAD | Augmentation of Salar Zone-IIA Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15743 | TSM/018003 | Augmentation | MVS | Yes | 931 | 0 | 0 | 931 | 480.14 | 0 | 0 | 480.14
704 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | TSM/006041 | Retrofitting | MVS | Yes | 8286 | 0 | 0 | 8286 | 601.79 | 0 | 0 | 601.79
705 | MURSHIDABAD | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15745 | TSM/018005 | Augmentation | MVS | Yes | 532 | 0 | 0 | 532 | 558.5 | 0 | 0 | 558.5
706 | MURSHIDABAD | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IV)to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16987 | TSM/019263 | Retrofitting | MVS | Yes | 10197 | 0 | 0 | 10197 | 950.83 | 0 | 0 | 950.83
707 | MURSHIDABAD | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | TSM/018230 | Augmentation | SVS | Yes | 2634 | 0 | 0 | 2634 | 863.66 | 0 | 0 | 863.66
708 | MURSHIDABAD | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | TSM/017896 | New | SVS | Yes | 204 | 0 | 0 | 204 | 81.23 | 0 | 0 | 81.23
709 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Char Alampur Village (Code-314767), Maheswarpur Village (Code-314768), Chatra Village (Code-314769) Under Command Area Of Moktarp | SM/07703 | TSM/006489 | Retrofitting | MVS | Yes | 856 | 0 | 0 | 856 | 65.9 | 0 | 0 | 65.9
710 | MURSHIDABAD | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | TSM/016512 | New | MVS | Yes | 3460 | 0 | 0 | 3460 | 1265.2 | 0 | 0 | 1265.2
711 | MURSHIDABAD | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. | SM/19126 | TSM/017380 | New | MVS | Yes | 3357 | 0 | 0 | 3357 | 1098.41 | 0 | 0 | 1098.41
712 | MURSHIDABAD | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | TSM/015843 | New | MVS | Yes | 4374 | 0 | 0 | 4374 | 1442.05 | 0 | 0 | 1442.05
713 | MURSHIDABAD | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. | SM/18556 | TSM/017329 | New | MVS | Yes | 3683 | 2362 | 0 | 6045 | 1383.64 | 0 | 0 | 1383.64
714 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18515 | TSM/018634 | Augmentation | MVS | Yes | 8111 | 0 | 0 | 8111 | 3298.88 | 0 | 0 | 3298.88
715 | MURSHIDABAD | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. | SM/18665 | TSM/018281 | Augmentation | MVS | Yes | 360 | 0 | 0 | 360 | 2200.3 | 0 | 0 | 2200.3
716 | MURSHIDABAD | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/18755 | TSM/015932 | Augmentation | SVS | Yes | 2935 | 0 | 625 | 2310 | 1126.44 | 0 | 0 | 1126.44
717 | MURSHIDABAD | DETAILED PROJECT REPORT FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR BEWA (JJM REVISION) | SM/18916 | TSM/010146 | New | MVS | Yes | 16539 | 0 | 0 | 16539 | 8264.61 | 0 | 0 | 8264.61
718 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sarkarpara ground water supply scheme | SM/07225 | TSM/006037 | Retrofitting | SVS | Yes | 420 | 0 | 0 | 420 | 30.52 | 0 | 0 | 30.52
719 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | TSM/006507 | Retrofitting | MVS | Yes | 12527 | 0 | 4589 | 7938 | 886.86 | 0 | 0 | 886.86
720 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code | SM/06977 | TSM/006030 | Retrofitting | SVS | Yes | 1544 | 0 | 0 | 1544 | 99.54 | 0 | 0 | 99.54
721 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 | SM/06978 | TSM/006031 | Retrofitting | SVS | Yes | 1389 | 0 | 0 | 1389 | 90.08 | 0 | 0 | 90.08
722 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Lochanpur Village (Code-314758), Char Pirojpur Village (Code-314760) Under Command Area Of Lochanpur Ground Water Supply Scheme(P | SM/07697 | TSM/006483 | Retrofitting | MVS | Yes | 2316 | 0 | 260 | 2056 | 168.17 | 0 | 0 | 168.17
723 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gopalpur Village (Code-315686) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-B) | SM/07699 | TSM/006485 | Retrofitting | SVS | Yes | 1343 | 0 | 0 | 1343 | 96.83 | 0 | 0 | 96.83
724 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric | SM/07292 | TSM/006126 | Retrofitting | MVS | Yes | 782 | 0 | 0 | 782 | 63.73 | 0 | 0 | 63.73
725 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid | SM/07294 | TSM/006132 | Retrofitting | MVS | Yes | 1255 | 0 | 0 | 1255 | 95.06 | 0 | 0 | 95.06
726 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Fulpur (Code-314511), Rajabati (Code-314552) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-B) | SM/07722 | TSM/006518 | Retrofitting | MVS | Yes | 506 | 0 | 0 | 506 | 43.55 | 0 | 0 | 43.55
727 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jogopur (Code-314533), Kamari (Code-314551) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-A) | SM/07723 | TSM/006519 | Retrofitting | MVS | Yes | 1041 | 0 | 0 | 1041 | 89.7 | 0 | 0 | 89.7
728 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Paranpur Village (Code-314173), Fatepur(Code-314174) In The Command Area Of Maiya Ground Water Supply Scheme (Part-C) Under Lalgo | SM/07785 | TSM/006454 | Retrofitting | SVS | Yes | 650 | 0 | 1 | 649 | 44.45 | 0 | 0 | 44.45
729 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Saralpur (Code-314538), Debaipur (Code-314548) In The Command Area Of Benipur Ground Water Supply Scheme (Part-D) | SM/07792 | TSM/006465 | Retrofitting | MVS | Yes | 1430 | 0 | 0 | 1430 | 94.73 | 0 | 0 | 94.73
730 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa | SM/08187 | TSM/006088 | Retrofitting | MVS | Yes | 6610 | 0 | 0 | 6610 | 489.6 | 0 | 0 | 489.6
731 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | TSM/006091 | Retrofitting | MVS | Yes | 14747 | 0 | 4547 | 10200 | 1045.27 | 0 | 0 | 1045.27
732 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nazirpur Village (Code-315684), Andulberia Village (Code-315690) Under Command Area Of Andulberia Ground Water Supply Scheme (P | SM/08901 | TSM/006481 | Retrofitting | MVS | Yes | 4844 | 0 | 0 | 4844 | 310.52 | 0 | 0 | 310.52
733 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | TSM/006541 | Retrofitting | MVS | Yes | 7197 | 0 | 0 | 7197 | 521.6 | 0 | 0 | 521.6
734 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B | SM/08202 | TSM/006564 | Retrofitting | MVS | Yes | 11345 | 5 | 0 | 11350 | 873.95 | 0 | 0 | 873.95
735 | MURSHIDABAD | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | TSM/005463 | New | MVS | Yes | 8993 | 3718 | 0 | 12711 | 2776.84 | 0 | 0 | 2776.84
736 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | TSM/006057 | Retrofitting | MVS | Yes | 9199 | 0 | 0 | 9199 | 665.47 | 0 | 0 | 665.47
737 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | TSM/006058 | Retrofitting | MVS | Yes | 5022 | 0 | 0 | 5022 | 384.16 | 0 | 0 | 384.16
738 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In Murshid | SM/08910 | TSM/006884 | Retrofitting | MVS | Yes | 7354 | 0 | 1207 | 6147 | 487.62 | 0 | 0 | 487.62
739 | MURSHIDABAD | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLDTAP CONNECTION (FHTC) IN CONNECTION WITH JALJEEVAN MISSION AND JAL SWAPNA AT KASIMBAZAR CT(CODE-315444) UNDER COMMAND AREA OF (ZONE-A) OFSURFACE WATER BASED WATER SUPPLY SCHEME IN THEARSENIC AFFECTED AREAS OF | SM/08918 | TSM/007705 | Retrofitting | SVS | Yes | 2821 | 0 | 0 | 2821 | 229.8 | 0 | 0 | 229.8
740 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Surangapur (315540) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad | SM/09741 | TSM/007539 | Retrofitting | SVS | Yes | 167 | 0 | 0 | 167 | 11.7 | 0 | 0 | 11.7
741 | MURSHIDABAD | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi | SM/09744 | TSM/007542 | Retrofitting | SVS | Yes | 1974 | 0 | 0 | 1974 | 186.4 | 0 | 0 | 186.4
742 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc | SM/08688 | TSM/006042 | Retrofitting | MVS | Yes | 6215 | 800 | 0 | 7015 | 461.79 | 0 | 0 | 461.79
743 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amdahara Haziganja ( 314497) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis | SM/09749 | TSM/007513 | Retrofitting | SVS | Yes | 1078 | 0 | 0 | 1078 | 81.3 | 0 | 0 | 81.3
744 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jehelinagar ( 313928 ) and Rosanpur ( 313930 )of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Bloc | SM/09751 | TSM/007517 | Retrofitting | MVS | Yes | 963 | 0 | 0 | 963 | 71.75 | 0 | 0 | 71.75
745 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block | SM/09753 | TSM/007519 | Retrofitting | MVS | Yes | 5437 | 0 | 2191 | 3246 | 389.19 | 0 | 0 | 389.19
746 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh | SM/09838 | TSM/007496 | Retrofitting | SVS | Yes | 323 | 0 | 0 | 323 | 25.62 | 0 | 0 | 25.62
747 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Batkamari ( 314689 ) of Jorgachha under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad | SM/09842 | TSM/007500 | Retrofitting | SVS | Yes | 419 | 0 | 0 | 419 | 34.36 | 0 | 0 | 34.36
748 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba | SM/09762 | TSM/007529 | Retrofitting | SVS | Yes | 979 | 811 | 0 | 1790 | 85.85 | 0 | 0 | 85.85
749 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | TSM/007530 | Retrofitting | SVS | Yes | 2439 | 0 | 0 | 2439 | 184.33 | 0 | 0 | 184.33
750 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M | SM/09765 | TSM/007532 | Retrofitting | SVS | Yes | 909 | 0 | 0 | 909 | 79.54 | 0 | 0 | 79.54
751 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sungai ( 315363 ) of Sungai under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad D | SM/09766 | TSM/007533 | Retrofitting | SVS | Yes | 116 | 0 | 0 | 116 | 13.96 | 0 | 0 | 13.96
752 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | TSM/007534 | Retrofitting | SVS | Yes | 1394 | 0 | 0 | 1394 | 107.76 | 0 | 0 | 107.76
753 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10612 | TSM/010290 | Augmentation | MVS | Yes | 2174 | 0 | 734 | 1440 | 480.94 | 0 | 29.84 | 451.1
754 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/11008 | TSM/010729 | Augmentation | MVS | Yes | 1229 | 0 | 26 | 1203 | 231.96 | 0 | 1.06 | 230.91
755 | MURSHIDABAD | Source Augmentation & Functional House Hold tap Connection (FHTC) under Mouza Kadkhali (315657)of Bachhara Ground water based water supply scheme for arsenic affected areas of Beldanga - II Block in Murshidabad District under Murshidabad Division, P.H.E. | SM/11161 | TSM/008737 | Augmentation | MVS | Yes | 958 | 0 | 690 | 268 | 205.19 | 0 | 28.05 | 177.15
756 | MURSHIDABAD | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | TSM/011576 | Augmentation | MVS | Yes | 3937 | 0 | 1561 | 2376 | 766.32 | 0 | 63.45 | 702.87
757 | MURSHIDABAD | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/11716 | TSM/011689 | Augmentation | MVS | Yes | 357 | 0 | 0 | 357 | 174.5 | 0 | 0 | 174.5
758 | MURSHIDABAD | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/08099 | TSM/006572 | Retrofitting | MVS | Yes | 4688 | 2 | 0 | 4690 | 366.99 | 0 | 0 | 366.99
759 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | TSM/011636 | Augmentation | MVS | Yes | 794 | 360 | 0 | 1154 | 582.29 | 0 | 0 | 582.29
760 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | TSM/011873 | Augmentation | MVS | Yes | 1976 | 372 | 0 | 2348 | 851.94 | 0 | 0 | 851.94
761 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME OF RAMKANTAPUR, BLOCK- SUTI - I, DIST- MURSHIDABAD | SM/10812 | TSM/008643 | Augmentation | MVS | Yes | 5156 | 0 | 1283 | 3873 | 705.89 | 0 | 52.15 | 653.74
762 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11561 | TSM/010381 | Augmentation | MVS | Yes | 2576 | 0 | 1764 | 812 | 930.14 | 0 | 0 | 930.14
763 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | TSM/010706 | Augmentation | MVS | Yes | 3431 | 0 | 3067 | 364 | 939.3 | 0 | 124.67 | 814.63
764 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11570 | TSM/010848 | Augmentation | SVS | Yes | 4515 | 0 | 3434 | 1081 | 943.42 | 0 | 0 | 943.42
765 | MURSHIDABAD | MAHISAR AND ADJOINING MOUJAS PWSS | SM/13725 | TSM/014734 | New | MVS | Yes | 3006 | 0 | 0 | 3006 | 852.84 | 0 | 0 | 852.84
766 | MURSHIDABAD | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Amarkunda, Bagor, Nandigram, Madhunia, Chayan Nagar, Sankuria, Rainda ( ) of Amarkundu under Ground Water Based Water Supply Scheme for arsenic affected areas of Nabagram Block of | SM/11230 | TSM/008712 | Augmentation | MVS | Yes | 1556 | 0 | 0 | 1556 | 273.1 | 0 | 0 | 273.1
767 | MURSHIDABAD | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | TSM/014523 | New | MVS | Yes | 2776 | 0 | 0 | 2776 | 927.78 | 0 | 0 | 927.78
768 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | TSM/006038 | Retrofitting | MVS | Yes | 2269 | 0 | 0 | 2269 | 170.09 | 0 | 0 | 170.09
769 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur | SM/12739 | TSM/011875 | Augmentation | MVS | Yes | 1858 | 0 | 0 | 1858 | 833.08 | 0 | 0 | 833.08
770 | MURSHIDABAD | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | TSM/015352 | New | MVS | Yes | 1372 | 0 | 0 | 1372 | 440.16 | 0 | 0 | 440.16
771 | MURSHIDABAD | AUGMENTATION OF BALI (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/14426 | TSM/016001 | Augmentation | SVS | Yes | 216 | 0 | 0 | 216 | 501.29 | 0 | 0 | 501.29
772 | MURSHIDABAD | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | TSM/015999 | Augmentation | SVS | Yes | 379 | 0 | 0 | 379 | 679.22 | 0 | 0 | 679.22
773 | MURSHIDABAD | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14428 | TSM/014463 | Augmentation | SVS | Yes | 355 | 0 | 0 | 355 | 338.02 | 0 | 0 | 338.02
774 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED KISHOREPUR PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13993 | TSM/015131 | Augmentation | MVS | Yes | 577 | 0 | 21 | 556 | 689.2 | 0 | 0.85 | 688.35
775 | MURSHIDABAD | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13824 | TSM/014987 | Augmentation | MVS | Yes | 1596 | 0 | 857 | 739 | 638.6 | 0 | 34.84 | 603.76
776 | MURSHIDABAD | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | TSM/014988 | Augmentation | MVS | Yes | 1109 | 0 | 1106 | 3 | 843.11 | 0 | 44.96 | 798.15
777 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. | SM/14630 | TSM/015758 | Augmentation | MVS | Yes | 379 | 0 | 79 | 300 | 466.17 | 0 | 0 | 466.17
778 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I | SM/15230 | TSM/017877 | Augmentation | SVS | Yes | 1093 | 0 | 0 | 1093 | 540.38 | 0 | 0 | 540.38
779 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. | SM/15232 | TSM/017976 | Augmentation | MVS | Yes | 1576 | 0 | 0 | 1576 | 903.97 | 0 | 0 | 903.97
780 | MURSHIDABAD | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | TSM/017776 | Augmentation | SVS | Yes | 715 | 0 | 0 | 715 | 989.95 | 0 | 0 | 989.95
781 | MURSHIDABAD | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS | SM/14497 | TSM/015606 | New | MVS | Yes | 2262 | 0 | 0 | 2262 | 770.2 | 0 | 0 | 770.2
782 | MURSHIDABAD | KAPASDANGA & ADJOINING MOUJAS PWSS | SM/15054 | TSM/017107 | New | MVS | Yes | 1416 | 0 | 0 | 1416 | 593 | 0 | 0 | 593
783 | MURSHIDABAD | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . | SM/14737 | TSM/012744 | Augmentation | MVS | Yes | 789 | 270 | 0 | 1059 | 808.29 | 0 | 0 | 808.29
784 | MURSHIDABAD | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. | SM/14943 | TSM/014415 | Augmentation | SVS | Yes | 4099 | 0 | 2708 | 1391 | 733.18 | 0 | 0 | 733.18
785 | MURSHIDABAD | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | TSM/014416 | Augmentation | SVS | Yes | 2237 | 0 | 1587 | 650 | 548.31 | 0 | 64.51 | 483.8
786 | MURSHIDABAD | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | TSM/017558 | Augmentation | MVS | Yes | 978 | 0 | 712 | 266 | 853.48 | 0 | 28.94 | 824.53
787 | MURSHIDABAD | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15070 | TSM/017144 | Augmentation | MVS | Yes | 1051 | 0 | 716 | 335 | 847.95 | 0 | 29.11 | 818.84
788 | MURSHIDABAD | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-B) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. | SM/15837 | TSM/015223 | Augmentation | SVS | Yes | 594 | 0 | 589 | 5 | 408.6 | 0 | 23.94 | 384.65
789 | MURSHIDABAD | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15838 | TSM/016059 | Augmentation | MVS | Yes | 923 | 0 | 610 | 313 | 745.29 | 0 | 24.8 | 720.49
790 | MURSHIDABAD | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | TSM/017619 | New | MVS | Yes | 2619 | 0 | 0 | 2619 | 948.13 | 0 | 0 | 948.13
791 | MURSHIDABAD | GAYSEPUR PIPED WATER SUPPLY SCHEME | SM/16018 | TSM/017605 | New | SVS | Yes | 491 | 0 | 0 | 491 | 396.07 | 0 | 0 | 396.07
792 | MURSHIDABAD | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAK CHANDPARA , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. | SM/16440 | TSM/013373 | New | SVS | Yes | 85 | 0 | 0 | 85 | 38.92 | 0 | 0 | 38.92
793 | MURSHIDABAD | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16547 | TSM/015929 | Augmentation | SVS | Yes | 586 | 0 | 343 | 243 | 996.9 | 0 | 13.94 | 982.95
794 | MURSHIDABAD | UTTAR MAHAMMADPUR PIPE WATER SUPPLY SCHEME. | SM/16550 | TSM/016547 | New | SVS | Yes | 2165 | 0 | 0 | 2165 | 979.6 | 0 | 0 | 979.6
795 | MURSHIDABAD | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | TSM/017534 | New | SVS | Yes | 665 | 0 | 0 | 665 | 660.39 | 0 | 0 | 660.39
796 | MURSHIDABAD | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/16553 | TSM/018440 | New | SVS | Yes | 820 | 0 | 0 | 820 | 245.29 | 0 | 0 | 245.29
797 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-III, Block- Berhampore, District- Murshidabad. | SM/16045 | TSM/018027 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
798 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-II, Block- Berhampore, District- Murshidabad. | SM/16497 | TSM/017989 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
799 | MURSHIDABAD | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-II, Block- Nawda, District- Murshidabad. | SM/16498 | TSM/017964 | New | SVS | Yes | 100 | 0 | 0 | 100 | 40.62 | 0 | 0 | 40.62
800 | MURSHIDABAD | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Arazi Narayanpur, Block- Lalgola, District- Murshidabad. | SM/16502 | TSM/017910 | New | SVS | Yes | 75 | 0 | 0 | 75 | 38.62 | 0 | 0 | 38.62
801 | MURSHIDABAD | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. | SM/16179 | TSM/016032 | Augmentation | SVS | Yes | 666 | 0 | 0 | 666 | 898.14 | 0 | 0 | 898.14
802 | MURSHIDABAD | AUGUMENTATION OF GARIBPUR PIPE WATER SUPPLY SCHEME (ZONE- II) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/15922 | TSM/016530 | Augmentation | SVS | Yes | 748 | 0 | 746 | 2 | 522.7 | 0 | 30.32 | 492.38
803 | MURSHIDABAD | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Darura, Block- Murshidabad Jiaganj, District- Murshidabad. | SM/16212 | TSM/017953 | New | SVS | Yes | 38 | 0 | 0 | 38 | 32.81 | 0 | 0 | 32.81
804 | MURSHIDABAD | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | TSM/019380 | New | SVS | Yes | 498 | 0 | 0 | 498 | 162.46 | 0 | 0 | 162.46
805 | MURSHIDABAD | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | TSM/006096 | Retrofitting | MVS | Yes | 6813 | 0 | 0 | 6813 | 494.79 | 0 | 0 | 494.79
806 | MURSHIDABAD | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I ) Part - A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15916 | TSM/016297 | Augmentation | MVS | Yes | 581 | 0 | 399 | 182 | 982.94 | 0 | 17.28 | 965.66
807 | MURSHIDABAD | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16415 | TSM/018053 | Augmentation | MVS | Yes | 1729 | 0 | 0 | 1729 | 541.33 | 0 | 0 | 541.33
808 | MURSHIDABAD | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | TSM/016155 | New | SVS | Yes | 1198 | 0 | 0 | 1198 | 620.94 | 0 | 0 | 620.94
809 | MURSHIDABAD | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16420 | TSM/018607 | Augmentation | MVS | Yes | 1370 | 0 | 0 | 1370 | 890.75 | 0 | 0 | 890.75
810 | MURSHIDABAD | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16558 | TSM/016518 | Augmentation | MVS | Yes | 350 | 144 | 0 | 494 | 275.73 | 0 | 4.92 | 270.81
811 | MURSHIDABAD | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/16621 | TSM/015325 | Augmentation | MVS | Yes | 228 | 96 | 0 | 324 | 842.44 | 0 | 0 | 842.44
812 | MURSHIDABAD | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | TSM/017629 | New | MVS | Yes | 782 | 0 | 0 | 782 | 562.54 | 0 | 0 | 562.54
813 | MURSHIDABAD | Augmentation of Nagar Zone- I Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/15726 | TSM/018306 | Augmentation | SVS | Yes | 3091 | 0 | 0 | 3091 | 763.92 | 0 | 0 | 763.92
814 | MURSHIDABAD | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/15750 | TSM/018291 | Augmentation | MVS | Yes | 646 | 0 | 0 | 646 | 697.42 | 0 | 0 | 697.42
815 | MURSHIDABAD | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16752 | TSM/010380 | Augmentation | SVS | Yes | 2723 | 0 | 0 | 2723 | 778.66 | 0 | 0 | 778.66
816 | MURSHIDABAD | BADDA AND IT'S ADJOINING MOUJAS | SM/15678 | TSM/018458 | New | MVS | Yes | 2297 | 0 | 0 | 2297 | 813.42 | 0 | 0 | 813.42
817 | MURSHIDABAD | BADUA AND IT'S ADJOINING MOUJAS | SM/15682 | TSM/018455 | New | MVS | Yes | 2253 | 0 | 0 | 2253 | 736.24 | 0 | 0 | 736.24
818 | MURSHIDABAD | GAYESPUR AND ADJOINING MOUJAS PWSS | SM/15690 | TSM/017711 | New | MVS | Yes | 1295 | 0 | 0 | 1295 | 427.3 | 0 | 0 | 427.3
819 | MURSHIDABAD | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | TSM/015938 | New | MVS | Yes | 1781 | 0 | 0 | 1781 | 698.09 | 0 | 0 | 698.09
820 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED KEYADANGA PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16754 | TSM/014663 | Augmentation | SVS | Yes | 685 | 0 | 675 | 10 | 526.89 | 0 | 27.44 | 499.45
821 | MURSHIDABAD | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16986 | TSM/019260 | Retrofitting | MVS | Yes | 7403 | 0 | 0 | 7403 | 733.3 | 0 | 0 | 733.3
822 | MURSHIDABAD | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XIV & XVI )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16990 | TSM/019258 | Retrofitting | MVS | Yes | 10370 | 0 | 0 | 10370 | 928.12 | 0 | 0 | 928.12
823 | MURSHIDABAD | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme | SM/07227 | TSM/006051 | Retrofitting | MVS | Yes | 1412 | 1 | 0 | 1413 | 92.47 | 0 | 0 | 92.47
824 | MURSHIDABAD | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | TSM/017535 | New | SVS | Yes | 704 | 0 | 0 | 704 | 613.23 | 0 | 0 | 613.23
825 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | TSM/014915 | Augmentation | SVS | Yes | 1706 | 0 | 282 | 1424 | 469.54 | 0 | 11.46 | 458.08
826 | MURSHIDABAD | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | TSM/015953 | Augmentation | SVS | Yes | 1223 | 0 | 1221 | 2 | 1278.27 | 0 | 0 | 1278.27
827 | MURSHIDABAD | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. | SM/18364 | TSM/018696 | Augmentation | SVS | Yes | 356 | 0 | 0 | 356 | 1761.66 | 0 | 0 | 1761.66
828 | MURSHIDABAD | Augmentation of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundabag GP Murshidabad District under Murshidabad Division PHE Dte . | SM/18393 | TSM/019936 | Augmentation | MVS | Yes | 0 | 0 | 0 | 0 | 1119.66 | 0 | 0 | 1119.66
829 | MURSHIDABAD | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | TSM/006509 | Retrofitting | MVS | Yes | 10249 | 0 | 7649 | 2600 | 746.48 | 0 | 0 | 746.48
830 | MURSHIDABAD | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | TSM/017345 | Augmentation | MVS | Yes | 796 | 114 | 0 | 910 | 1068.33 | 0 | 0 | 1068.33
831 | MURSHIDABAD | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/18444 | TSM/015294 | Augmentation | MVS | Yes | 5077 | 0 | 61 | 5016 | 1407.24 | 0 | 0 | 1407.24
Grand Total | [7 empty] | 2070508 | 71057 | 334344 | 1807221 | 550300.32 | 0 | 3244.26 | 547056.08