## FHTC correction
FHTC correction (Rs. in Lakh)
Sl No. | District | Scheme | Scheme SM Code | TSM Code | Scheme Type | Scheme coverage type | Is Scheme correction completed | FHTC approved | Increased | Decreased | FHTC Modified | Cost Clear | Increased | Decreased | Modified Cost
1 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). | SM/08041 | TSM/007086 | Retrofitting | SVS | Yes | 1692 | 0 | 1507 | 185 | 89.3 | 0 | 0 | 89.3
2 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Chandpur Water Supply Scheme at Bagdah Block under (Phase-I) | SM/08042 | TSM/007085 | Retrofitting | MVS | Yes | 1235 | 0 | 110 | 1125 | 75.47 | 0 | 0 | 75.47
3 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-VIII) at Kanchiara OHR site under (Phase-I) for Arsenic affected areas of N | SM/08045 | TSM/007089 | Retrofitting | MVS | Yes | 1446 | 6 | 0 | 1452 | 93.98 | 0 | 0 | 93.98
4 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Water Supply Scheme at Swarupnagar Block (Phase-I) | SM/07854 | TSM/006771 | Retrofitting | SVS | Yes | 380 | 0 | 275 | 105 | 24.84 | 0 | 0 | 24.84
5 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-II) | SM/07616 | TSM/006784 | Retrofitting | MVS | Yes | 987 | 0 | 0 | 987 | 64.05 | 0 | 0 | 64.05
6 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamlabas Water Supply Scheme at Bagdah Block (Phase-II) | SM/07620 | TSM/006787 | Retrofitting | SVS | Yes | 2338 | 0 | 2240 | 98 | 133.68 | 0 | 0 | 133.68
7 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kulia Water Supply Scheme at Baduria Block, Dist.-North 24 Parganas (Phase-I) | SM/07843 | TSM/006766 | Retrofitting | SVS | Yes | 700 | 0 | 0 | 700 | 47.8 | 0 | 0 | 47.8
8 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | TSM/007045 | Retrofitting | MVS | Yes | 2724 | 0 | 1100 | 1624 | 419.92 | 0 | 0 | 419.92
9 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chikanpara Piped Water Supply Scheme, Gaighata Block (Phase-I) | SM/08269 | TSM/007378 | Retrofitting | MVS | Yes | 3550 | 0 | 0 | 3550 | 230.73 | 0 | 0 | 230.73
10 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Parmadan Water Supply Scheme atBagdah Block (Phase-I). | SM/08234 | TSM/007277 | Retrofitting | SVS | Yes | 1008 | 423 | 0 | 1431 | 57.5 | 0 | 0 | 57.5
11 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block | SM/08243 | TSM/007435 | Retrofitting | MVS | Yes | 1595 | 324 | 0 | 1919 | 99.94 | 0 | 0 | 99.94
12 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur mouza (rest part after Phase-I) & Bakpukhuria mouza of Akipur Piped Water Supply Scheme, Basirhat-II Block under B | SM/08771 | TSM/007356 | Retrofitting | MVS | Yes | 550 | 0 | 0 | 550 | 60.85 | 0 | 0 | 60.85
13 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of PIFA W/S Scheme at Basirhat -I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | SM/08789 | TSM/007640 | Retrofitting | MVS | Yes | 1200 | 0 | 0 | 1200 | 80.66 | 0 | 0 | 80.66
14 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08264 | TSM/007364 | Retrofitting | MVS | Yes | 2407 | 0 | 0 | 2407 | 177.55 | 0 | 0 | 177.55
15 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10505 | TSM/010489 | Retrofitting | SVS | Yes | 2213 | 0 | 500 | 1713 | 404.01 | 0 | 0 | 404.01
16 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | TSM/010492 | Retrofitting | MVS | Yes | 4537 | 0 | 800 | 3737 | 603.79 | 0 | 0 | 603.79
17 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10508 | TSM/010495 | Retrofitting | MVS | Yes | 3439 | 0 | 600 | 2839 | 455.09 | 0 | 0 | 455.09
18 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | TSM/009496 | Augmentation | MVS | Yes | 8463 | 0 | 300 | 8163 | 866.8 | 0 | 0 | 866.8
19 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | TSM/009515 | Augmentation | MVS | Yes | 5976 | 0 | 0 | 5976 | 788.19 | 0 | 0 | 788.19
20 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | SM/10693 | TSM/009762 | Augmentation | MVS | Yes | 1254 | 0 | 100 | 1154 | 399.28 | 0 | 0 | 399.28
21 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | TSM/010456 | Augmentation | MVS | Yes | 5060 | 0 | 371 | 4689 | 880.49 | 0 | 0 | 880.49
22 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | SM/10565 | TSM/010453 | Augmentation | MVS | Yes | 2129 | 0 | 200 | 1929 | 666.15 | 0 | 0 | 666.15
23 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection under command area of Bermajur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | SM/10616 | TSM/010695 | Retrofitting | SVS | Yes | 896 | 0 | 500 | 396 | 158.22 | 0 | 0 | 158.22
24 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | TSM/010452 | Augmentation | MVS | Yes | 192 | 0 | 0 | 192 | 497.76 | 0 | 0 | 497.76
25 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | TSM/009735 | Augmentation | SVS | Yes | 1210 | 0 | 300 | 910 | 772.26 | 0 | 0 | 772.26
26 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC | SM/11656 | TSM/011371 | Augmentation | MVS | Yes | 1127 | 0 | 0 | 1127 | 610.62 | 0 | 0 | 610.62
27 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | TSM/009737 | Augmentation | SVS | Yes | 1224 | 0 | 600 | 624 | 745.57 | 0 | 0 | 745.57
28 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | SM/11703 | TSM/011421 | Augmentation | MVS | Yes | 1718 | 0 | 150 | 1568 | 393.65 | 0 | 0 | 393.65
29 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11971 | TSM/011826 | Augmentation | MVS | Yes | 3371 | 0 | 950 | 2421 | 850.12 | 0 | 0 | 850.12
30 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | TSM/011031 | Augmentation | MVS | Yes | 6025 | 0 | 300 | 5725 | 934.91 | 0 | 0 | 934.91
31 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | SM/11530 | TSM/011075 | Augmentation | MVS | Yes | 1891 | 0 | 150 | 1741 | 505.56 | 0 | 0 | 505.56
32 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | TSM/011076 | Augmentation | MVS | Yes | 1065 | 0 | 100 | 965 | 315 | 0 | 0 | 315
33 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC | SM/11753 | TSM/011429 | Augmentation | MVS | Yes | 938 | 0 | 0 | 938 | 433.45 | 0 | 0 | 433.45
34 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | SM/13531 | TSM/011524 | Retrofitting | MVS | Yes | 13080 | 0 | 900 | 12180 | 678.06 | 0 | 0 | 678.06
35 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Krishnachandrapur Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08265 | TSM/007360 | Retrofitting | MVS | Yes | 1880 | 0 | 0 | 1880 | 144.14 | 0 | 0 | 144.14
36 | NORTH 24 PARGANAS | Sankardaha Piped water supply scheme | SM/13518 | TSM/015446 | New | MVS | Yes | 1217 | 0 | 0 | 1217 | 920.98 | 0 | 0 | 920.98
37 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/13537 | TSM/011508 | Retrofitting | MVS | Yes | 12685 | 0 | 600 | 12085 | 660.09 | 0 | 0 | 660.09
38 | NORTH 24 PARGANAS | Phulbari Abad Piped Water Supply Scheme. | SM/12717 | TSM/014714 | New | MVS | Yes | 958 | 0 | 0 | 958 | 647.71 | 0 | 0 | 647.71
39 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | TSM/011247 | Augmentation | SVS | Yes | 1920 | 2464 | 0 | 4384 | 808.59 | 0 | 0 | 808.59
40 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | TSM/011170 | Augmentation | MVS | Yes | 4479 | 0 | 500 | 3979 | 1446.05 | 0 | 0 | 1446.05
41 | NORTH 24 PARGANAS | SULANGGARI Piped Water Supply Scheme | SM/14634 | TSM/016291 | New | SVS | Yes | 3786 | 0 | 0 | 3786 | 1224.19 | 0 | 0 | 1224.19
42 | NORTH 24 PARGANAS | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | TSM/018807 | Augmentation | MVS | Yes | 0 | 0 | 0 | 0 | 811.68 | 0 | 0 | 811.68
43 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/14540 | TSM/011513 | Retrofitting | MVS | Yes | 20272 | 0 | 1896 | 18376 | 1050.88 | 0 | 0 | 1050.88
44 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | TSM/014790 | Augmentation | MVS | Yes | 4667 | 0 | 1000 | 3667 | 1294.9 | 0 | 8.5 | 1286.4
45 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15822 | TSM/014788 | Augmentation | MVS | Yes | 4893 | 0 | 1300 | 3593 | 1300.14 | 0 | 0 | 1300.14
46 | NORTH 24 PARGANAS | Khariat Abad Piped Water Supply Scheme | SM/15829 | TSM/015513 | New | MVS | Yes | 1936 | 0 | 0 | 1936 | 1521.01 | 0 | 0 | 1521.01
47 | NORTH 24 PARGANAS | Ketarchak Piped Water Supply Scheme | SM/15833 | TSM/015343 | New | MVS | Yes | 1519 | 0 | 0 | 1519 | 1333.54 | 0 | 0 | 1333.54
48 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | TSM/015251 | Augmentation | MVS | Yes | 3626 | 0 | 1060 | 2566 | 1188.71 | 0 | 0 | 1188.71
49 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18265 | TSM/015249 | Augmentation | MVS | Yes | 3203 | 0 | 500 | 2703 | 1079.23 | 0 | 0 | 1079.23
50 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | SM/18712 | TSM/011242 | Augmentation | MVS | Yes | 1903 | 0 | 150 | 1753 | 882.07 | 0 | 0 | 882.07
51 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | SM/11606 | TSM/011027 | Augmentation | MVS | Yes | 3804 | 0 | 800 | 3004 | 753.37 | 0 | 0 | 753.37
52 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | TSM/011105 | Augmentation | MVS | Yes | 2541 | 0 | 250 | 2291 | 838.59 | 0 | 0 | 838.59
53 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Noorpur Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08259 | TSM/007365 | Retrofitting | MVS | Yes | 1400 | 0 | 0 | 1400 | 98.93 | 0 | 0 | 98.93
54 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | TSM/011307 | Augmentation | MVS | Yes | 6552 | 0 | 1000 | 5552 | 1089.94 | 0 | 0 | 1089.94
55 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kola Water Supply Scheme at Bagdah Block (Phase-I) | SM/08069 | TSM/007038 | Retrofitting | SVS | Yes | 528 | 0 | 0 | 528 | 34.3 | 0 | 0 | 34.3
56 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | SM/10574 | TSM/010446 | Augmentation | MVS | Yes | 3609 | 0 | 300 | 3309 | 872.16 | 0 | 0 | 872.16
57 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12372 | TSM/011863 | Augmentation | MVS | Yes | 4762 | 0 | 750 | 4012 | 1216.5 | 0 | 0 | 1216.5
58 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamlabas Water Supply Scheme at Bagdah Block (Phase-I) | SM/07849 | TSM/006774 | Retrofitting | MVS | Yes | 883 | 0 | 248 | 635 | 55.2 | 0 | 0 | 55.2
59 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | TSM/009318 | Augmentation | MVS | Yes | 3585 | 0 | 400 | 3185 | 567.55 | 0 | 0 | 567.55
60 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | TSM/007046 | Retrofitting | SVS | Yes | 693 | 0 | 75 | 618 | 68.38 | 0 | 0 | 68.38
61 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/07853 | TSM/006772 | Retrofitting | SVS | Yes | 420 | 0 | 0 | 420 | 50.97 | 0 | 0 | 50.97
62 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DIGHARI Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07599 | TSM/006919 | Retrofitting | MVS | Yes | 1093 | 3 | 0 | 1096 | 70.98 | 0 | 0 | 70.98
63 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07604 | TSM/006916 | Retrofitting | MVS | Yes | 875 | 14 | 0 | 889 | 56.87 | 0 | 0 | 56.87
64 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) | SM/07605 | TSM/006914 | Retrofitting | MVS | Yes | 1131 | 346 | 0 | 1477 | 73.51 | 0 | 0 | 73.51
65 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Deora Water Supply Scheme at Swarupnagar Block (Phase-II) | SM/07618 | TSM/006786 | Retrofitting | SVS | Yes | 346 | 0 | 0 | 346 | 22.12 | 0 | 0 | 22.12
66 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-I) | SM/07846 | TSM/006769 | Retrofitting | SVS | Yes | 506 | 0 | 0 | 506 | 44.61 | 0 | 0 | 44.61
67 | NORTH 24 PARGANAS | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08728 | TSM/007657 | Retrofitting | MVS | Yes | 1637 | 0 | 272 | 1365 | 136.39 | 0 | 0 | 136.39
68 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khulna Bhanderkhali Piped Water Supply Scheme (Zone-I), Sandeshkhali-II Block (Phase-I) | SM/08762 | TSM/007357 | Retrofitting | MVS | Yes | 1150 | 0 | 0 | 1150 | 98.91 | 0 | 0 | 98.91
69 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-I WaterSupply Scheme at Bongaon Block (Phase-II). | SM/08236 | TSM/007285 | Retrofitting | MVS | Yes | 1299 | 4 | 0 | 1303 | 77.55 | 0 | 0 | 77.55
70 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Santoshpur Zone-II Water SupplyScheme at Bongaon Block (Phase-II). | SM/08238 | TSM/007281 | Retrofitting | MVS | Yes | 1200 | 2 | 0 | 1202 | 76.1 | 0 | 0 | 76.1
71 | NORTH 24 PARGANAS | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . | SM/08245 | TSM/007340 | Retrofitting | MVS | Yes | 1394 | 0 | 179 | 1215 | 99.08 | 0 | 0 | 99.08
72 | NORTH 24 PARGANAS | Retrofitting of Jashaikati Zone II & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . | SM/08246 | TSM/007341 | Retrofitting | MVS | Yes | 1348 | 4 | 0 | 1352 | 95.17 | 0 | 0 | 95.17
73 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Piped Water Supply Scheme, Swarupnagar Block under Barasat Division, P.H.E.Dte. (Phase-II) | SM/08769 | TSM/007347 | Retrofitting | SVS | Yes | 214 | 0 | 0 | 214 | 17.35 | 0 | 0 | 17.35
74 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Piped Water Supply Scheme, Basirhat-II Block under Barasat Division, P.H.E.Dte. (Phase-II) | SM/08772 | TSM/007352 | Retrofitting | SVS | Yes | 329 | 0 | 0 | 329 | 25.42 | 0 | 0 | 25.42
75 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area DHOPABERIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08638 | TSM/007644 | Retrofitting | MVS | Yes | 900 | 0 | 0 | 900 | 61.11 | 0 | 0 | 61.11
76 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Mirzanagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08639 | TSM/007613 | Retrofitting | MVS | Yes | 1500 | 0 | 0 | 1500 | 100.22 | 0 | 0 | 100.22
77 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Jadavpur, Khanpur, Odhanpur, Kumarpur, Fazilpur, Rampur & Sohai mouzas (Part) within Sohai Swetpur Zone-II Piped Water Sup | SM/08652 | TSM/007630 | Retrofitting | MVS | Yes | 3356 | 0 | 1369 | 1987 | 276.49 | 0 | 0 | 276.49
78 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kachua Swarupnagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08660 | TSM/007645 | Retrofitting | MVS | Yes | 1500 | 0 | 0 | 1500 | 100.06 | 0 | 0 | 100.06
79 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/09735 | TSM/008770 | Retrofitting | MVS | Yes | 1200 | 0 | 0 | 1200 | 180.22 | 0 | 0 | 180.22
80 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Janaphul Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08780 | TSM/007610 | Retrofitting | SVS | Yes | 1394 | 0 | 0 | 1394 | 91.28 | 0 | 0 | 91.28
81 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Magurali Piped Water Supply Scheme at Baduria Block (Phase-I) | SM/08785 | TSM/007608 | Retrofitting | MVS | Yes | 2134 | 0 | 0 | 2134 | 253.71 | 0 | 0 | 253.71
82 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Itinda Panitor Piped Water Supply Scheme at Basirhat-I Block (Phase-I) | SM/08786 | TSM/007636 | Retrofitting | MVS | Yes | 3000 | 0 | 0 | 3000 | 197.7 | 0 | 0 | 197.7
83 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of ARSULA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/08787 | TSM/007637 | Retrofitting | MVS | Yes | 3500 | 1000 | 0 | 4500 | 230.14 | 0 | 0 | 230.14
84 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | TSM/009761 | Augmentation | MVS | Yes | 3694 | 0 | 350 | 3344 | 726.34 | 0 | 0 | 726.34
85 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10556 | TSM/010696 | Retrofitting | MVS | Yes | 3056 | 0 | 0 | 3056 | 430.12 | 0 | 0 | 430.12
86 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Bhangatushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10510 | TSM/010490 | Retrofitting | SVS | Yes | 2074 | 0 | 1000 | 1074 | 371.96 | 0 | 0 | 371.96
87 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | TSM/010459 | Augmentation | MVS | Yes | 163 | 0 | 0 | 163 | 414.14 | 0 | 0 | 414.14
88 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | TSM/010566 | Augmentation | MVS | Yes | 4021 | 0 | 350 | 3671 | 983.01 | 0 | 0 | 983.01
89 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-I) | SM/07615 | TSM/006781 | Retrofitting | SVS | Yes | 1036 | 0 | 0 | 1036 | 67.21 | 0 | 0 | 67.21
90 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/A (Kharki) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12563 | TSM/010887 | Augmentation | MVS | Yes | 5775 | 0 | 700 | 5075 | 1024.61 | 0 | 0 | 1024.61
91 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC | SM/11704 | TSM/011389 | Augmentation | MVS | Yes | 2392 | 769 | 0 | 3161 | 703.83 | 0 | 0 | 703.83
92 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | TSM/011065 | Augmentation | SVS | Yes | 2449 | 0 | 250 | 2199 | 684.44 | 0 | 0 | 684.44
93 | NORTH 24 PARGANAS | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | TSM/009609 | Augmentation | MVS | Yes | 2641 | 0 | 200 | 2441 | 575.56 | 0 | 0 | 575.56
94 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | SM/11756 | TSM/011318 | Augmentation | MVS | Yes | 1497 | 897 | 0 | 2394 | 841.9 | 0 | 0 | 841.9
95 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC | SM/11759 | TSM/011374 | Augmentation | MVS | Yes | 3360 | 0 | 300 | 3060 | 690.28 | 0 | 0 | 690.28
96 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-A (Kanchiyara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11922 | TSM/011824 | Augmentation | MVS | Yes | 2827 | 0 | 350 | 2477 | 695.71 | 0 | 0 | 695.71
97 | NORTH 24 PARGANAS | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | TSM/011245 | Augmentation | SVS | Yes | 3977 | 2501 | 0 | 6478 | 985.92 | 0 | 0 | 985.92
98 | NORTH 24 PARGANAS | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | TSM/015451 | New | SVS | Yes | 623 | 0 | 0 | 623 | 619.01 | 0 | 0 | 619.01
99 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/13521 | TSM/011549 | Retrofitting | MVS | Yes | 18551 | 0 | 1621 | 16930 | 961.66 | 0 | 0 | 961.66
100 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/13532 | TSM/011517 | Retrofitting | MVS | Yes | 13185 | 0 | 0 | 13185 | 683.5 | 0 | 0 | 683.5
101 | NORTH 24 PARGANAS | Niruli Abad Piped Water Supply Scheme. | SM/12716 | TSM/014701 | New | MVS | Yes | 581 | 0 | 0 | 581 | 491.85 | 0 | 0 | 491.85
102 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proje | SM/13533 | TSM/011516 | Retrofitting | MVS | Yes | 12611 | 0 | 700 | 11911 | 653.74 | 0 | 0 | 653.74
103 | NORTH 24 PARGANAS | Kachurhula Zone-II Piped Water Supply Scheme | SM/13445 | TSM/015445 | New | MVS | Yes | 411 | 0 | 0 | 411 | 413.72 | 0 | 0 | 413.72
104 | NORTH 24 PARGANAS | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | TSM/015553 | Augmentation | SVS | Yes | 1991 | 0 | 150 | 1841 | 896.27 | 0 | 0 | 896.27
105 | NORTH 24 PARGANAS | Augmentation of Rajbari Piped water supply scheme | SM/14515 | TSM/018704 | Augmentation | SVS | Yes | 0 | 0 | 0 | 0 | 625.64 | 0 | 0 | 625.64
106 | NORTH 24 PARGANAS | Electrocoagulation based package Surface water based water supply scheme (Solar Power) in Minakhan Block | SM/14625 | TSM/015125 | New | MVS | Yes | 50 | 0 | 0 | 50 | 46.97 | 0 | 0 | 46.97
107 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | TSM/012006 | Augmentation | SVS | Yes | 3219 | 0 | 300 | 2919 | 1072.81 | 0 | 0 | 1072.81
108 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | TSM/011276 | Augmentation | MVS | Yes | 3526 | 0 | 360 | 3166 | 1713.12 | 0 | 0 | 1713.12
109 | NORTH 24 PARGANAS | Augmentation of Sultanpur Piped water supply scheme | SM/14510 | TSM/018805 | Augmentation | MVS | Yes | 0 | 0 | 0 | 0 | 393.61 | 0 | 0 | 393.61
110 | NORTH 24 PARGANAS | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | TSM/015721 | Augmentation | MVS | Yes | 4690 | 0 | 500 | 4190 | 1445.85 | 0 | 0 | 1445.85
111 | NORTH 24 PARGANAS | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | TSM/015764 | Augmentation | SVS | Yes | 4185 | 0 | 400 | 3785 | 1003.28 | 0 | 0 | 1003.28
112 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/15824 | TSM/011543 | Retrofitting | MVS | Yes | 20012 | 0 | 3300 | 16712 | 1037.4 | 0 | 0 | 1037.4
113 | NORTH 24 PARGANAS | Ambaria Piped Water Supply Scheme | SM/15831 | TSM/015378 | New | MVS | Yes | 1376 | 0 | 0 | 1376 | 1121.04 | 0 | 0 | 1121.04
114 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su | SM/08773 | TSM/007631 | Retrofitting | MVS | Yes | 4050 | 0 | 0 | 4050 | 296.54 | 0 | 0 | 296.54
115 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18263 | TSM/015074 | Augmentation | MVS | Yes | 3248 | 0 | 600 | 2648 | 1172.77 | 0 | 0 | 1172.77
116 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VII (Amulia) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18264 | TSM/015086 | Augmentation | MVS | Yes | 3562 | 0 | 766 | 2796 | 1252.7 | 0 | 0 | 1252.7
117 | NORTH 24 PARGANAS | Augmentation of TYANTRA NEORA (POND) WATER SUPPLY SCHEME | SM/17680 | TSM/015003 | Augmentation | SVS | Yes | 440 | 0 | 0 | 440 | 261 | 0 | 0 | 261
118 | NORTH 24 PARGANAS | Augmentation of Mathurabil Zone-I in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19108 | TSM/020571 | Augmentation | MVS | No | 0 | 0 | 0 | 0 | 985.92 | 0 | 0 | 985.92
119 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | TSM/011169 | Augmentation | MVS | Yes | 1343 | 0 | 100 | 1243 | 402.48 | 0 | 0 | 402.48
120 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | TSM/011206 | Augmentation | MVS | Yes | 4240 | 0 | 0 | 4240 | 1342.36 | 0 | 0 | 1342.36
121 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | TSM/011388 | Augmentation | MVS | Yes | 1519 | 0 | 100 | 1419 | 817.01 | 0 | 0 | 817.01
122 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Diara Water Supply Scheme at Bagdah Block (Phase-I) | SM/08070 | TSM/007040 | Retrofitting | MVS | Yes | 412 | 0 | 0 | 412 | 26.81 | 0 | 0 | 26.81
123 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dighari Water Supply Scheme at Bongaon Block (Phase-II). | SM/08048 | TSM/007083 | Retrofitting | MVS | Yes | 1156 | 8 | 0 | 1164 | 62.67 | 0 | 0 | 62.67
124 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme for Arsenic affected areas at Deganga Block of North 24 Parganas | SM/08049 | TSM/007087 | Retrofitting | MVS | Yes | 2000 | 0 | 996 | 1004 | 99.22 | 0 | 0 | 99.22
125 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07600 | TSM/006920 | Retrofitting | MVS | Yes | 1478 | 283 | 0 | 1761 | 92.84 | 0 | 0 | 92.84
126 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) | SM/07617 | TSM/006780 | Retrofitting | MVS | Yes | 1260 | 0 | 0 | 1260 | 99.98 | 0 | 0 | 99.98
127 | NORTH 24 PARGANAS | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection | SM/07021 | TSM/006283 | Retrofitting | SVS | Yes | 500 | 0 | 0 | 500 | 58.16 | 0 | 0 | 58.16
128 | NORTH 24 PARGANAS | Rejuvenation of Krishnapara Water Supply scheme under Hasnabad Block for providing Functional House Tap Connection | SM/07024 | TSM/006281 | Retrofitting | MVS | Yes | 1417 | 92 | 0 | 1509 | 99.35 | 0 | 0 | 99.35
129 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Korakati Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | SM/08761 | TSM/007368 | Retrofitting | SVS | Yes | 1160 | 0 | 500 | 660 | 98.6 | 0 | 0 | 98.6
130 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Baunia Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | SM/08763 | TSM/007372 | Retrofitting | SVS | Yes | 1100 | 0 | 100 | 1000 | 98.97 | 0 | 0 | 98.97
131 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Boyermari Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | SM/08766 | TSM/007373 | Retrofitting | SVS | Yes | 1400 | 0 | 488 | 912 | 98.79 | 0 | 0 | 98.79
132 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Patua W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | SM/09730 | TSM/009440 | Retrofitting | MVS | Yes | 2300 | 0 | 0 | 2300 | 197.1 | 0 | 0 | 197.1
133 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of BANGLANI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08640 | TSM/007626 | Retrofitting | MVS | Yes | 4000 | 0 | 0 | 4000 | 260.99 | 0 | 0 | 260.99
134 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MATHURAPUR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08656 | TSM/007646 | Retrofitting | MVS | Yes | 1500 | 0 | 0 | 1500 | 100.07 | 0 | 0 | 100.07
135 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gabberia Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | SM/08256 | TSM/007343 | Retrofitting | SVS | Yes | 842 | 0 | 0 | 842 | 97.57 | 0 | 0 | 97.57
136 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) | SM/08644 | TSM/007615 | Retrofitting | MVS | Yes | 2731 | 0 | 0 | 2731 | 291.24 | 0 | 0 | 291.24
137 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DHANYAKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/08788 | TSM/007647 | Retrofitting | MVS | Yes | 1350 | 0 | 0 | 1350 | 89.79 | 0 | 0 | 89.79
138 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | TSM/009733 | Augmentation | SVS | Yes | 1498 | 0 | 100 | 1398 | 974.51 | 0 | 0 | 974.51
139 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P | SM/10504 | TSM/010488 | Retrofitting | SVS | Yes | 1423 | 0 | 0 | 1423 | 324.12 | 0 | 0 | 324.12
140 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | TSM/010388 | Augmentation | MVS | Yes | 1799 | 0 | 0 | 1799 | 572.23 | 0 | 0 | 572.23
141 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | TSM/010570 | Augmentation | MVS | Yes | 2045 | 0 | 200 | 1845 | 767.45 | 0 | 0 | 767.45
142 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10550 | TSM/010491 | Retrofitting | SVS | Yes | 2699 | 0 | 1000 | 1699 | 448.57 | 0 | 0 | 448.57
143 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | TSM/009320 | Augmentation | MVS | Yes | 5884 | 0 | 500 | 5384 | 621.84 | 0 | 0 | 621.84
144 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Auldanga Water Supply Scheme at Bagdah Block (Phase-II) | SM/08039 | TSM/007047 | Retrofitting | MVS | Yes | 4277 | 11 | 0 | 4288 | 252.36 | 0 | 0 | 252.36
145 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | TSM/009251 | Augmentation | MVS | Yes | 4288 | 0 | 500 | 3788 | 603.88 | 0 | 0 | 603.88
146 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | TSM/010276 | Augmentation | MVS | Yes | 1886 | 0 | 0 | 1886 | 933.78 | 0 | 0 | 933.78
147 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | TSM/009323 | Augmentation | MVS | Yes | 4618 | 0 | 500 | 4118 | 586.51 | 0 | 0 | 586.51
148 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | TSM/010275 | Augmentation | MVS | Yes | 3129 | 0 | 300 | 2829 | 995.76 | 0 | 0 | 995.76
149 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | TSM/011317 | Augmentation | MVS | Yes | 7863 | 0 | 700 | 7163 | 1383.8 | 0 | 0 | 1383.8
150 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | TSM/011383 | Augmentation | MVS | Yes | 11539 | 0 | 900 | 10639 | 1866.7 | 0 | 0 | 1866.7
151 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | TSM/011034 | Augmentation | MVS | Yes | 5083 | 0 | 500 | 4583 | 1362.92 | 0 | 0 | 1362.92
152 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12275 | TSM/011157 | Augmentation | MVS | Yes | 4879 | 0 | 2000 | 2879 | 1321.92 | 0 | 0 | 1321.92
153 | NORTH 24 PARGANAS | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10153 | TSM/009497 | Augmentation | MVS | Yes | 8873 | 0 | 1050 | 7823 | 979.14 | 0 | 0 | 979.14
154 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Joy Gaopalpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10501 | TSM/010431 | Retrofitting | MVS | Yes | 4243 | 0 | 0 | 4243 | 570.78 | 0 | 0 | 570.78
155 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10502 | TSM/010485 | Retrofitting | SVS | Yes | 1266 | 0 | 500 | 766 | 329.73 | 0 | 0 | 329.73
156 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | TSM/010860 | Augmentation | MVS | Yes | 1931 | 0 | 200 | 1731 | 651.86 | 0 | 0 | 651.86
157 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | TSM/011110 | Augmentation | MVS | Yes | 2440 | 0 | 300 | 2140 | 633 | 0 | 0 | 633
158 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | TSM/011213 | Augmentation | MVS | Yes | 3085 | 0 | 300 | 2785 | 944.75 | 0 | 0 | 944.75
159 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | TSM/011147 | Augmentation | MVS | Yes | 1124 | 0 | 100 | 1024 | 447.89 | 0 | 0 | 447.89
160 | NORTH 24 PARGANAS | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | TSM/018399 | Augmentation | MVS | Yes | 0 | 0 | 0 | 0 | 9483.34 | 0 | 0 | 9483.34
161 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12111 | TSM/010457 | Augmentation | MVS | Yes | 2809 | 0 | 800 | 2009 | 932.15 | 0 | 0 | 932.15
162 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC | SM/11626 | TSM/011033 | Augmentation | MVS | Yes | 2832 | 0 | 250 | 2582 | 996.87 | 0 | 0 | 996.87
163 | NORTH 24 PARGANAS | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | TSM/009584 | Augmentation | MVS | Yes | 3395 | 0 | 520 | 2875 | 632.75 | 0 | 0 | 632.75
164 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | TSM/011074 | Augmentation | SVS | Yes | 200 | 0 | 0 | 200 | 168.18 | 0 | 0 | 168.18
165 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC | SM/11604 | TSM/011023 | Augmentation | MVS | Yes | 2624 | 0 | 950 | 1674 | 607.32 | 0 | 0 | 607.32
166 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | TSM/011746 | Augmentation | MVS | Yes | 7093 | 0 | 0 | 7093 | 1227.6 | 0 | 0 | 1227.6
167 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kulia to accommodate FHTC | SM/11755 | TSM/011309 | Augmentation | SVS | Yes | 249 | 0 | 0 | 249 | 240.56 | 0 | 0 | 240.56
168 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC | SM/11757 | TSM/011377 | Augmentation | MVS | Yes | 2215 | 0 | 200 | 2015 | 484.84 | 0 | 0 | 484.84
169 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | TSM/011200 | Augmentation | MVS | Yes | 5900 | 0 | 600 | 5300 | 1555.96 | 0 | 0 | 1555.96
170 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC | SM/11758 | TSM/011385 | Augmentation | MVS | Yes | 898 | 0 | 0 | 898 | 294.81 | 0 | 0 | 294.81
171 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | TSM/011177 | Augmentation | SVS | Yes | 1882 | 0 | 700 | 1182 | 668.55 | 0 | 0 | 668.55
172 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped W/S Scheme for Gainpur in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/11940 | TSM/012009 | Augmentation | MVS | Yes | 300 | 0 | 100 | 200 | 188.87 | 0 | 0 | 188.87
173 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Chhaimalpur | SM/13767 | TSM/012028 | Augmentation | MVS | Yes | 1050 | 0 | 0 | 1050 | 370.05 | 0 | 0 | 370.05
174 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | TSM/011193 | Augmentation | MVS | Yes | 3494 | 0 | 896 | 2598 | 1253.12 | 0 | 0 | 1253.12
175 | NORTH 24 PARGANAS | Hatbhanga Piped Water Supply Scheme | SM/13525 | TSM/015443 | New | MVS | Yes | 789 | 0 | 0 | 789 | 752.17 | 0 | 0 | 752.17
176 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | SM/13527 | TSM/011540 | Retrofitting | MVS | Yes | 12462 | 0 | 1000 | 11462 | 646.01 | 0 | 0 | 646.01
177 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | SM/13530 | TSM/011527 | Retrofitting | MVS | Yes | 16667 | 0 | 1200 | 15467 | 864.01 | 0 | 0 | 864.01
178 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. | SM/14127 | TSM/011254 | Augmentation | MVS | Yes | 1147 | 0 | 100 | 1047 | 423.52 | 0 | 0 | 423.52
179 | NORTH 24 PARGANAS | Purana Bongaon Piped water supply scheme | SM/13896 | TSM/016339 | New | SVS | Yes | 2307 | 0 | 0 | 2307 | 934.47 | 0 | 0 | 934.47
180 | NORTH 24 PARGANAS | Garibpur Piped water supply scheme | SM/13897 | TSM/016336 | New | MVS | Yes | 755 | 0 | 0 | 755 | 594.36 | 0 | 0 | 594.36
181 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas D | SM/13534 | TSM/011515 | Retrofitting | MVS | Yes | 12031 | 0 | 800 | 11231 | 621.18 | 0 | 0 | 621.18
182 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/14541 | TSM/011509 | Retrofitting | MVS | Yes | 20479 | 11802 | 0 | 32281 | 1061.62 | 0 | 0 | 1061.62
183 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/15823 | TSM/011565 | Retrofitting | MVS | Yes | 19414 | 8724 | 0 | 28138 | 1006.41 | 0 | 0 | 1006.41
184 | NORTH 24 PARGANAS | Katakhali Piped Water Supply Scheme | SM/15826 | TSM/015510 | New | SVS | Yes | 1341 | 0 | 0 | 1341 | 1183.01 | 0 | 0 | 1183.01
185 | NORTH 24 PARGANAS | Kusangra Piped Water Supply Scheme | SM/15832 | TSM/015447 | New | MVS | Yes | 1977 | 0 | 0 | 1977 | 1105.8 | 0 | 0 | 1105.8
186 | NORTH 24 PARGANAS | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08729 | TSM/007656 | Retrofitting | MVS | Yes | 1188 | 0 | 57 | 1131 | 110.61 | 0 | 0 | 110.61
187 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10608 | TSM/010405 | Augmentation | MVS | Yes | 662 | 0 | 0 | 662 | 309.27 | 0 | 0 | 309.27
188 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | TSM/010857 | Augmentation | MVS | Yes | 2049 | 0 | 200 | 1849 | 703.03 | 0 | 0 | 703.03
189 | NORTH 24 PARGANAS | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08178 | TSM/007029 | Retrofitting | MVS | Yes | 1694 | 0 | 342 | 1352 | 97.62 | 0 | 0 | 97.62
190 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | TSM/011234 | Augmentation | SVS | Yes | 391 | 0 | 0 | 391 | 504.63 | 0 | 0 | 504.63
191 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11864 | TSM/011948 | Augmentation | MVS | Yes | 1808 | 0 | 0 | 1808 | 737.67 | 0 | 0 | 737.67
192 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | TSM/010949 | Augmentation | MVS | Yes | 5054 | 0 | 1200 | 3854 | 1715.28 | 0 | 0 | 1715.28
193 | NORTH 24 PARGANAS | Augmentation of ShridharKati water supply scheme in Sundarban Island area (Island no. 61) | null | TSM/017888 | Augmentation | MVS | Yes | 10449 | 0 | 0 | 10449 | 18026.49 | 0 | 0 | 18026.49
194 | NORTH 24 PARGANAS | Retrofitting of Paltadanga & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) | SM/08176 | TSM/007028 | Retrofitting | MVS | Yes | 1226 | 3 | 0 | 1229 | 76.13 | 0 | 0 | 76.13
195 | NORTH 24 PARGANAS | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08179 | TSM/007030 | Retrofitting | MVS | Yes | 1608 | 14 | 0 | 1622 | 94.55 | 0 | 0 | 94.55
196 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARAKPUR Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07602 | TSM/006915 | Retrofitting | SVS | Yes | 1612 | 3 | 0 | 1615 | 94.17 | 0 | 0 | 94.17
197 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07609 | TSM/006924 | Retrofitting | MVS | Yes | 830 | 613 | 0 | 1443 | 53.91 | 0 | 0 | 53.91
198 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | TSM/006775 | Retrofitting | SVS | Yes | 2624 | 355 | 0 | 2979 | 223.92 | 0 | 0 | 223.92
199 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) | SM/07613 | TSM/006778 | Retrofitting | SVS | Yes | 700 | 0 | 61 | 639 | 60.66 | 0 | 0 | 60.66
200 | NORTH 24 PARGANAS | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07712 | TSM/006713 | Retrofitting | MVS | Yes | 1097 | 0 | 0 | 1097 | 84.96 | 0 | 0 | 84.96
201 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Deora Water Supply Scheme at Swarupnagar Block (Phase-I) | SM/07844 | TSM/006777 | Retrofitting | SVS | Yes | 730 | 0 | 0 | 730 | 50.79 | 0 | 0 | 50.79
202 | NORTH 24 PARGANAS | Retrofitting of Jeliakhali Paschim khanda water supply scheme under sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08726 | TSM/007655 | Retrofitting | SVS | Yes | 811 | 1511 | 0 | 2322 | 74.61 | 0 | 0 | 74.61
203 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Nabatkati W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | SM/09729 | TSM/009443 | Retrofitting | MVS | Yes | 1700 | 0 | 0 | 1700 | 200.79 | 0 | 0 | 200.79
204 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) | SM/07851 | TSM/006763 | Retrofitting | MVS | Yes | 867 | 0 | 0 | 867 | 84.15 | 0 | 0 | 84.15
205 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dakshin Bagundi Piped Water Supply Scheme, Basirhat-I Block under Barasat Division, P.H.E.Dte. (Phase-II) | SM/08768 | TSM/007345 | Retrofitting | SVS | Yes | 202 | 0 | 0 | 202 | 17 | 0 | 0 | 17
206 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kulia Piped Water Supply Scheme, Baduria Block under Barasat Division, P.H.E.Dte. (Phase-II) | SM/08770 | TSM/007355 | Retrofitting | SVS | Yes | 273 | 0 | 0 | 273 | 22.44 | 0 | 0 | 22.44
207 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08776 | TSM/007618 | Retrofitting | MVS | Yes | 1328 | 0 | 0 | 1328 | 91.53 | 0 | 0 | 91.53
208 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-II) Piped Water Supply Scheme at Baduria Block (Phase-I) | SM/08654 | TSM/007660 | Retrofitting | SVS | Yes | 1997 | 0 | 0 | 1997 | 154.44 | 0 | 0 | 154.44
209 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Raghunathpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08657 | TSM/007617 | Retrofitting | MVS | Yes | 900 | 0 | 0 | 900 | 61.11 | 0 | 0 | 61.11
210 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khosdelpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08784 | TSM/007620 | Retrofitting | MVS | Yes | 2085 | 0 | 0 | 2085 | 134.94 | 0 | 0 | 134.94
211 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BANSJHARI MALLIKPUR W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08650 | TSM/007629 | Retrofitting | MVS | Yes | 800 | 0 | 0 | 800 | 54.59 | 0 | 0 | 54.59
212 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | TSM/009123 | Augmentation | MVS | Yes | 2699 | 0 | 0 | 2699 | 406.31 | 0 | 0 | 406.31
213 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gobindapur Water Supply Scheme at Bagdah Block (Phase-II) | SM/07624 | TSM/006783 | Retrofitting | SVS | Yes | 1043 | 0 | 0 | 1043 | 67.83 | 0 | 0 | 67.83
214 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08260 | TSM/007366 | Retrofitting | MVS | Yes | 1113 | 0 | 0 | 1113 | 99.12 | 0 | 0 | 99.12
215 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PASCHIM PANCHBERIA ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07606 | TSM/006921 | Retrofitting | MVS | Yes | 465 | 2 | 0 | 467 | 40.1 | 0 | 0 | 40.1
216 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10511 | TSM/010487 | Retrofitting | MVS | Yes | 3195 | 0 | 1000 | 2195 | 464.15 | 0 | 0 | 464.15
217 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | TSM/009219 | Augmentation | MVS | Yes | 4017 | 0 | 250 | 3767 | 860.25 | 0 | 0 | 860.25
218 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | SM/10758 | TSM/010573 | Augmentation | MVS | Yes | 4150 | 0 | 400 | 3750 | 1273.39 | 0 | 0 | 1273.39
219 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | TSM/009764 | Augmentation | MVS | Yes | 1097 | 0 | 0 | 1097 | 329.58 | 0 | 0 | 329.58
220 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | SM/10577 | TSM/009759 | Augmentation | SVS | Yes | 205 | 0 | 0 | 205 | 153.49 | 0 | 0 | 153.49
221 | NORTH 24 PARGANAS | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | TSM/009939 | Augmentation | MVS | Yes | 2928 | 0 | 300 | 2628 | 660.77 | 0 | 0 | 660.77
222 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | TSM/010263 | Augmentation | MVS | Yes | 3351 | 0 | 300 | 3051 | 929.85 | 0 | 0 | 929.85
223 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | TSM/006764 | Retrofitting | SVS | Yes | 698 | 0 | 0 | 698 | 57.27 | 0 | 0 | 57.27
224 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | TSM/011071 | Augmentation | MVS | Yes | 8360 | 0 | 750 | 7610 | 1376.36 | 0 | 0 | 1376.36
225 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC | SM/11655 | TSM/011314 | Augmentation | MVS | Yes | 2639 | 0 | 700 | 1939 | 978.15 | 0 | 0 | 978.15
226 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC | SM/11586 | TSM/011072 | Augmentation | MVS | Yes | 824 | 0 | 0 | 824 | 420.97 | 0 | 0 | 420.97
227 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | TSM/011107 | Augmentation | MVS | Yes | 3308 | 0 | 350 | 2958 | 815.25 | 0 | 0 | 815.25
228 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | TSM/011168 | Augmentation | MVS | Yes | 6631 | 0 | 600 | 6031 | 996.66 | 0 | 0 | 996.66
229 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | TSM/011164 | Augmentation | MVS | Yes | 225 | 0 | 0 | 225 | 363.83 | 0 | 0 | 363.83
230 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC | SM/11668 | TSM/011165 | Augmentation | MVS | Yes | 2412 | 0 | 250 | 2162 | 738.24 | 0 | 0 | 738.24
231 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | SM/11669 | TSM/011167 | Augmentation | MVS | Yes | 3070 | 0 | 1800 | 1270 | 899.67 | 0 | 0 | 899.67
232 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/11212 | TSM/010262 | Augmentation | MVS | Yes | 4011 | 0 | 400 | 3611 | 1269.72 | 0 | 0 | 1269.72
233 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | SM/11525 | TSM/011067 | Augmentation | MVS | Yes | 3181 | 0 | 300 | 2881 | 697.66 | 0 | 0 | 697.66
234 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIII (Aziznagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12413 | TSM/014786 | Augmentation | MVS | Yes | 2867 | 0 | 1324 | 1543 | 956.05 | 0 | 0 | 956.05
235 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | TSM/011197 | Augmentation | MVS | Yes | 2453 | 0 | 200 | 2253 | 606.65 | 0 | 0 | 606.65
236 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | TSM/011198 | Augmentation | MVS | Yes | 902 | 0 | 0 | 902 | 709.91 | 0 | 0 | 709.91
237 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC | SM/11763 | TSM/011373 | Augmentation | MVS | Yes | 1121 | 0 | 100 | 1021 | 425.28 | 0 | 0 | 425.28
238 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Kendua mouza, Jagatpur mouza and Chaita mouza (Rest part after phase-I) of Sadiknagar Zone-II Piped Water Supply Scheme, Basirh | SM/08767 | TSM/007349 | Retrofitting | MVS | Yes | 900 | 0 | 0 | 900 | 60.31 | 0 | 0 | 60.31
239 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-B (Maricha) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12729 | TSM/011825 | Augmentation | MVS | Yes | 4647 | 0 | 1350 | 3297 | 1320.45 | 0 | 0 | 1320.45
240 | NORTH 24 PARGANAS | Pipuldaha Piped Water Supply Scheme. | SM/12721 | TSM/014691 | New | MVS | Yes | 584 | 0 | 0 | 584 | 570.24 | 0 | 0 | 570.24
241 | NORTH 24 PARGANAS | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | TSM/015722 | Augmentation | MVS | Yes | 3570 | 0 | 350 | 3220 | 998.54 | 0 | 0 | 998.54
242 | NORTH 24 PARGANAS | Paschim Huda Piped water supply scheme | SM/13895 | TSM/016341 | New | MVS | Yes | 1209 | 0 | 0 | 1209 | 697.08 | 0 | 0 | 697.08
243 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/13543 | TSM/011559 | Retrofitting | MVS | Yes | 13904 | 0 | 2000 | 11904 | 720.77 | 0 | 0 | 720.77
244 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/13545 | TSM/011560 | Retrofitting | MVS | Yes | 12584 | 0 | 2200 | 10384 | 652.34 | 0 | 0 | 652.34
245 | NORTH 24 PARGANAS | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | TSM/018809 | Augmentation | MVS | Yes | 0 | 0 | 0 | 0 | 999.82 | 0 | 0 | 999.82
246 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/14539 | TSM/011541 | Retrofitting | MVS | Yes | 19952 | 0 | 2575 | 17377 | 1034.29 | 0 | 0 | 1034.29
247 | NORTH 24 PARGANAS | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | TSM/015718 | Augmentation | MVS | Yes | 3995 | 0 | 400 | 3595 | 1327.23 | 0 | 0 | 1327.23
248 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | TSM/012030 | Augmentation | MVS | Yes | 5054 | 0 | 500 | 4554 | 2059.51 | 0 | 0 | 2059.51
249 | NORTH 24 PARGANAS | Augmentation of Bermajur Piped water supply scheme | SM/14511 | TSM/018703 | Augmentation | SVS | Yes | 0 | 0 | 0 | 0 | 858.68 | 0 | 0 | 858.68
250 | NORTH 24 PARGANAS | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | TSM/015278 | Augmentation | MVS | Yes | 109879 | 0 | 109879 | 0 | 8915.09 | 0 | 0 | 8915.09
251 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15817 | TSM/014836 | Augmentation | MVS | Yes | 1569 | 0 | 400 | 1169 | 1114.63 | 0 | 0 | 1114.63
252 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | TSM/014881 | Augmentation | MVS | Yes | 3839 | 0 | 900 | 2939 | 1214.7 | 0 | 0 | 1214.7
253 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | TSM/011241 | Augmentation | MVS | Yes | 1178 | 213 | 0 | 1391 | 1022.72 | 0 | 0 | 1022.72
254 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | TSM/007042 | Retrofitting | MVS | Yes | 2100 | 0 | 1000 | 1100 | 226.61 | 0 | 0 | 226.61
255 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection under command area of Chotto Sehara W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | SM/10554 | TSM/010694 | Retrofitting | MVS | Yes | 863 | 0 | 0 | 863 | 150.09 | 0 | 0 | 150.09
256 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | TSM/009255 | Augmentation | MVS | Yes | 2929 | 0 | 300 | 2629 | 601.14 | 0 | 0 | 601.14
257 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | TSM/011275 | Augmentation | SVS | Yes | 2800 | 0 | 200 | 2600 | 812.18 | 0 | 0 | 812.18
258 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-II) | SM/08066 | TSM/007034 | Retrofitting | SVS | Yes | 100 | 0 | 0 | 100 | 6.6 | 0 | 0 | 6.6
259 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Palla Water Supply Scheme at Bongaon Block (Phase-I) | SM/08047 | TSM/007048 | Retrofitting | MVS | Yes | 1129 | 0 | 81 | 1048 | 73.37 | 0 | 0 | 73.37
260 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHLAMPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07601 | TSM/006918 | Retrofitting | MVS | Yes | 1369 | 2 | 0 | 1371 | 85.45 | 0 | 0 | 85.45
261 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Matiagacha Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-I) | SM/07621 | TSM/006790 | Retrofitting | SVS | Yes | 848 | 0 | 0 | 848 | 54.83 | 0 | 0 | 54.83
262 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Matiagacha Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) | SM/07622 | TSM/006791 | Retrofitting | SVS | Yes | 467 | 0 | 0 | 467 | 32.21 | 0 | 0 | 32.21
263 | NORTH 24 PARGANAS | Retrofitting of Chaumuha Water Supply scheme under Barasat - II Block for providing Functional House Tap Connection | SM/07023 | TSM/006274 | Retrofitting | SVS | Yes | 1040 | 0 | 59 | 981 | 94.95 | 0 | 0 | 94.95
264 | NORTH 24 PARGANAS | Retrofiting of Jeliakhali Paschim khanda water supply scheme under sandeshkhali- II Block for providing Functional House Tap Conection | SM/07025 | TSM/006278 | Retrofitting | SVS | Yes | 1206 | 1116 | 0 | 2322 | 99.86 | 0 | 0 | 99.86
265 | NORTH 24 PARGANAS | Retrofitting of Konanagar water supply scheme under Hasnabad Block for providing Functional House Tap Conection | SM/07027 | TSM/006279 | Retrofitting | MVS | Yes | 1050 | 93 | 0 | 1143 | 84.77 | 0 | 0 | 84.77
266 | NORTH 24 PARGANAS | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07713 | TSM/006714 | Retrofitting | MVS | Yes | 1008 | 0 | 2 | 1006 | 79.93 | 0 | 0 | 79.93
267 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dakshin Bagundi Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) | SM/07845 | TSM/006765 | Retrofitting | SVS | Yes | 300 | 0 | 0 | 300 | 22.88 | 0 | 0 | 22.88
268 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | TSM/007044 | Retrofitting | MVS | Yes | 4853 | 0 | 1400 | 3453 | 589.31 | 0 | 0 | 589.31
269 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mollahati Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. (Phase-I). | SM/08731 | TSM/007652 | Retrofitting | MVS | Yes | 798 | 4 | 0 | 802 | 99.33 | 0 | 0 | 99.33
270 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ichhapur Piped Water Supply Scheme, Gaighata Block (Phase-I) | SM/08270 | TSM/007376 | Retrofitting | MVS | Yes | 2236 | 0 | 755 | 1481 | 145.34 | 0 | 0 | 145.34
271 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Bangangram (Zone-II) Water SupplyScheme at Bongaon Block (Phase-II). | SM/08237 | TSM/007283 | Retrofitting | SVS | Yes | 1073 | 12 | 0 | 1085 | 61.96 | 0 | 0 | 61.96
272 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Taranipur W/S Scheme (Zone-II) at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | SM/09728 | TSM/009446 | Retrofitting | MVS | Yes | 1100 | 0 | 0 | 1100 | 148.48 | 0 | 0 | 148.48
273 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08642 | TSM/007633 | Retrofitting | MVS | Yes | 1500 | 0 | 0 | 1500 | 99.01 | 0 | 0 | 99.01
274 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08659 | TSM/007634 | Retrofitting | MVS | Yes | 3500 | 0 | 0 | 3500 | 225.64 | 0 | 0 | 225.64
275 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of RAHARHATI W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08646 | TSM/007642 | Retrofitting | MVS | Yes | 1000 | 0 | 0 | 1000 | 67.63 | 0 | 0 | 67.63
276 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08647 | TSM/007641 | Retrofitting | MVS | Yes | 4000 | 0 | 0 | 4000 | 262.67 | 0 | 0 | 262.67
277 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection under command area of Rajbari W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | SM/10553 | TSM/010693 | Retrofitting | SVS | Yes | 544 | 0 | 400 | 144 | 89.4 | 0 | 0 | 89.4
278 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC | SM/10558 | TSM/010450 | Augmentation | MVS | Yes | 2452 | 0 | 1139 | 1313 | 774.12 | 0 | 0 | 774.12
279 | NORTH 24 PARGANAS | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) | SM/10559 | TSM/009206 | Augmentation | SVS | Yes | 180 | 0 | 0 | 180 | 69.7 | 0 | 0 | 69.7
280 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hariharpur Water Supply Scheme at Bagdah Block (Phase-II) | SM/08071 | TSM/007039 | Retrofitting | SVS | Yes | 222 | 0 | 0 | 222 | 14.47 | 0 | 0 | 14.47
281 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | TSM/010005 | Augmentation | MVS | Yes | 2282 | 0 | 200 | 2082 | 789.43 | 0 | 0 | 789.43
282 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | TSM/009519 | Augmentation | MVS | Yes | 9490 | 0 | 500 | 8990 | 990.56 | 0 | 0 | 990.56
283 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | TSM/009254 | Augmentation | MVS | Yes | 3430 | 0 | 300 | 3130 | 474.07 | 0 | 0 | 474.07
284 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | TSM/010451 | Augmentation | MVS | Yes | 2485 | 0 | 200 | 2285 | 745.73 | 0 | 0 | 745.73
285 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | TSM/010461 | Augmentation | MVS | Yes | 3502 | 0 | 300 | 3202 | 1038.21 | 0 | 0 | 1038.21
286 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | TSM/010599 | Augmentation | MVS | Yes | 6589 | 0 | 800 | 5789 | 993.32 | 0 | 0 | 993.32
287 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | TSM/010408 | Augmentation | MVS | Yes | 1297 | 0 | 0 | 1297 | 635.36 | 0 | 0 | 635.36
288 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12566 | TSM/011870 | Augmentation | MVS | Yes | 3286 | 0 | 650 | 2636 | 1121.01 | 0 | 0 | 1121.01
289 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC | SM/11630 | TSM/011079 | Augmentation | SVS | Yes | 557 | 0 | 0 | 557 | 171.91 | 0 | 0 | 171.91
290 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC | SM/11701 | TSM/011316 | Augmentation | MVS | Yes | 1639 | 0 | 250 | 1389 | 522.67 | 0 | 0 | 522.67
291 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | SM/11702 | TSM/011080 | Augmentation | MVS | Yes | 1702 | 0 | 300 | 1402 | 472.02 | 0 | 0 | 472.02
292 | NORTH 24 PARGANAS | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | TSM/010752 | Augmentation | MVS | Yes | 1990 | 0 | 200 | 1790 | 578.98 | 0 | 0 | 578.98
293 | NORTH 24 PARGANAS | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | TSM/010751 | Augmentation | MVS | Yes | 248 | 0 | 0 | 248 | 260.23 | 0 | 0 | 260.23
294 | NORTH 24 PARGANAS | Retrofitting of Bagband Saiberia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07709 | TSM/006717 | Retrofitting | MVS | Yes | 1230 | 50 | 0 | 1280 | 89.02 | 0 | 0 | 89.02
295 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | TSM/011976 | Augmentation | MVS | Yes | 2468 | 0 | 200 | 2268 | 749.37 | 0 | 0 | 749.37
296 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC | SM/11760 | TSM/011379 | Augmentation | MVS | Yes | 1278 | 0 | 100 | 1178 | 455.04 | 0 | 0 | 455.04
297 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-A (Kharu) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11941 | TSM/011892 | Augmentation | MVS | Yes | 2255 | 0 | 200 | 2055 | 828.52 | 0 | 0 | 828.52
298 | NORTH 24 PARGANAS | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | TSM/014697 | New | MVS | Yes | 1847 | 0 | 0 | 1847 | 1020.87 | 0 | 0 | 1020.87
299 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13902 | TSM/011942 | Augmentation | MVS | Yes | 7793 | 0 | 200 | 7593 | 1028.82 | 0 | 0 | 1028.82
300 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | TSM/011319 | Augmentation | MVS | Yes | 14065 | 0 | 3638 | 10427 | 2478.35 | 0 | 0 | 2478.35
301 | NORTH 24 PARGANAS | Niruli Piped Water Supply Scheme | SM/12714 | TSM/014715 | New | MVS | Yes | 1435 | 0 | 0 | 1435 | 786.23 | 0 | 0 | 786.23
302 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | TSM/015250 | Augmentation | MVS | Yes | 2777 | 0 | 600 | 2177 | 920.04 | 0 | 0 | 920.04
303 | NORTH 24 PARGANAS | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | SM/13894 | TSM/015720 | Augmentation | MVS | Yes | 2885 | 1398 | 0 | 4283 | 998.95 | 0 | 0 | 998.95
304 | NORTH 24 PARGANAS | Uchildaha Piped water supply scheme | SM/13815 | TSM/014828 | New | SVS | Yes | 2107 | 0 | 0 | 2107 | 1165.33 | 0 | 0 | 1165.33
305 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proje | SM/13535 | TSM/011511 | Retrofitting | MVS | Yes | 18529 | 0 | 900 | 17629 | 960.53 | 0 | 0 | 960.53
306 | NORTH 24 PARGANAS | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | TSM/017800 | Augmentation | MVS | Yes | 750 | 0 | 0 | 750 | 308.06 | 0 | 0 | 308.06
307 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/14542 | TSM/011507 | Retrofitting | MVS | Yes | 20010 | 0 | 900 | 19110 | 1138.26 | 0 | 0 | 1138.26
308 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15821 | TSM/014754 | Augmentation | MVS | Yes | 3232 | 0 | 695 | 2537 | 1038.35 | 0 | 0 | 1038.35
309 | NORTH 24 PARGANAS | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | SM/07706 | TSM/006712 | Retrofitting | SVS | Yes | 650 | 612 | 0 | 1262 | 74.7 | 0 | 0 | 74.7
310 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18261 | TSM/015092 | Augmentation | MVS | Yes | 4444 | 0 | 704 | 3740 | 1312.14 | 0 | 0 | 1312.14
311 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC | SM/17408 | TSM/011322 | Augmentation | MVS | Yes | 3543 | 0 | 0 | 3543 | 649.79 | 0 | 0 | 649.79
312 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | TSM/010006 | Augmentation | MVS | Yes | 2890 | 0 | 300 | 2590 | 837.91 | 0 | 0 | 837.91
313 | NORTH 24 PARGANAS | Kaugachhi Zone-III Piped Water Supply Scheme | SM/14502 | TSM/016342 | New | SVS | Yes | 1561 | 0 | 500 | 1061 | 660.36 | 0 | 0 | 660.36
314 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | TSM/010996 | Augmentation | MVS | Yes | 1606 | 0 | 201 | 1405 | 518 | 0 | 0 | 518
315 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC | SM/11523 | TSM/011066 | Augmentation | MVS | Yes | 948 | 0 | 0 | 948 | 437.19 | 0 | 0 | 437.19
316 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-A (Algaria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13794 | TSM/012002 | Augmentation | MVS | Yes | 2931 | 0 | 200 | 2731 | 845.42 | 0 | 0 | 845.42
317 | NORTH 24 PARGANAS | RAIGACHHI Piped Water Supply Scheme. | SM/18599 | TSM/016043 | New | SVS | Yes | 2070 | 0 | 0 | 2070 | 1046.62 | 0 | 0 | 1046.62
318 | NORTH 24 PARGANAS | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13420 | TSM/015209 | Augmentation | MVS | Yes | 567 | 0 | 0 | 567 | 414.24 | 0 | 0 | 414.24
319 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | TSM/011175 | Augmentation | MVS | Yes | 1663 | 0 | 100 | 1563 | 1299.65 | 0 | 0 | 1299.65
320 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | TSM/011116 | Augmentation | MVS | Yes | 279 | 0 | 0 | 279 | 324.63 | 0 | 0 | 324.63
321 | NORTH 24 PARGANAS | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | TSM/015719 | Augmentation | MVS | Yes | 2997 | 0 | 300 | 2697 | 905.25 | 0 | 0 | 905.25
322 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-I) | SM/08067 | TSM/007036 | Retrofitting | MVS | Yes | 2110 | 0 | 0 | 2110 | 135.21 | 0 | 0 | 135.21
323 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-II) | SM/08068 | TSM/007037 | Retrofitting | MVS | Yes | 1368 | 0 | 385 | 983 | 87.78 | 0 | 0 | 87.78
324 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Paikpara Water Supply Scheme at Bongaon Block (Phase-II). | SM/08043 | TSM/007082 | Retrofitting | SVS | Yes | 1241 | 1 | 0 | 1242 | 99.82 | 0 | 0 | 99.82
325 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-I) | SM/07848 | TSM/006767 | Retrofitting | MVS | Yes | 711 | 0 | 0 | 711 | 59.57 | 0 | 0 | 59.57
326 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAIKPARA Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07603 | TSM/006917 | Retrofitting | SVS | Yes | 1066 | 2 | 0 | 1068 | 69.29 | 0 | 0 | 69.29
327 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. | SM/07611 | TSM/006776 | Retrofitting | SVS | Yes | 2525 | 0 | 1440 | 1085 | 198.98 | 0 | 0 | 198.98
328 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) | SM/07612 | TSM/006782 | Retrofitting | SVS | Yes | 1306 | 0 | 270 | 1036 | 87.47 | 0 | 0 | 87.47
329 | NORTH 24 PARGANAS | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07707 | TSM/006716 | Retrofitting | MVS | Yes | 1390 | 0 | 0 | 1390 | 97.68 | 0 | 0 | 97.68
330 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) | SM/07842 | TSM/006770 | Retrofitting | SVS | Yes | 1417 | 0 | 0 | 1417 | 92.43 | 0 | 0 | 92.43
331 | NORTH 24 PARGANAS | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08723 | TSM/007659 | Retrofitting | MVS | Yes | 1333 | 152 | 0 | 1485 | 95.59 | 0 | 0 | 95.59
332 | NORTH 24 PARGANAS | Retrofitting of Jashaikati Zone - I and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase- II) | SM/08724 | TSM/007658 | Retrofitting | SVS | Yes | 1900 | 0 | 93 | 1807 | 130.03 | 0 | 0 | 130.03
333 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Piped Water Supply Scheme at Bagdah Block (Phase-I) | SM/08266 | TSM/007377 | Retrofitting | MVS | Yes | 1431 | 907 | 0 | 2338 | 93.01 | 0 | 0 | 93.01
334 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08267 | TSM/007379 | Retrofitting | SVS | Yes | 679 | 0 | 0 | 679 | 44.13 | 0 | 0 | 44.13
335 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) | SM/08777 | TSM/007616 | Retrofitting | MVS | Yes | 2393 | 0 | 0 | 2393 | 164.51 | 0 | 0 | 164.51
336 | NORTH 24 PARGANAS | Retrofitting of Rohanda & Its adjoining Mouzas Water Supply Scheme under Barasat II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | SM/08247 | TSM/007342 | Retrofitting | MVS | Yes | 1396 | 1 | 0 | 1397 | 97.98 | 0 | 0 | 97.98
337 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-I) at Habra-I Block (Phase-I) | SM/08778 | TSM/007612 | Retrofitting | MVS | Yes | 2027 | 0 | 0 | 2027 | 139.9 | 0 | 0 | 139.9
338 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08263 | TSM/007361 | Retrofitting | MVS | Yes | 2765 | 0 | 719 | 2046 | 193.64 | 0 | 0 | 193.64
339 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | TSM/009758 | Augmentation | SVS | Yes | 1316 | 0 | 100 | 1216 | 377.53 | 0 | 0 | 377.53
340 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10557 | TSM/010697 | Retrofitting | MVS | Yes | 1727 | 0 | 0 | 1727 | 309.66 | 0 | 0 | 309.66
341 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). | SM/08239 | TSM/007278 | Retrofitting | SVS | Yes | 1615 | 0 | 119 | 1496 | 92.02 | 0 | 0 | 92.02
342 | NORTH 24 PARGANAS | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | TSM/008650 | New | MVS | Yes | 2277 | 0 | 0 | 2277 | 1219.24 | 0 | 0 | 1219.24
343 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | TSM/011109 | Augmentation | SVS | Yes | 1229 | 0 | 100 | 1129 | 365.57 | 0 | 0 | 365.57
344 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | TSM/011171 | Augmentation | MVS | Yes | 1178 | 0 | 600 | 578 | 922.45 | 0 | 0 | 922.45
345 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | TSM/011166 | Augmentation | MVS | Yes | 5062 | 0 | 350 | 4712 | 1244.2 | 0 | 0 | 1244.2
346 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. | SM/10781 | TSM/009736 | Augmentation | SVS | Yes | 145 | 0 | 0 | 145 | 449.15 | 0 | 0 | 449.15
347 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | SM/11627 | TSM/011073 | Augmentation | MVS | Yes | 783 | 0 | 0 | 783 | 375 | 0 | 0 | 375
348 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | SM/11658 | TSM/011370 | Augmentation | MVS | Yes | 3154 | 0 | 350 | 2804 | 607.13 | 0 | 0 | 607.13
349 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | TSM/010998 | Augmentation | MVS | Yes | 1560 | 0 | 200 | 1360 | 540.65 | 0 | 0 | 540.65
350 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | TSM/011203 | Augmentation | MVS | Yes | 499 | 0 | 0 | 499 | 461.21 | 0 | 0 | 461.21
351 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | TSM/010859 | Augmentation | MVS | Yes | 873 | 0 | 0 | 873 | 438.9 | 0 | 0 | 438.9
352 | NORTH 24 PARGANAS | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | TSM/009082 | Augmentation | MVS | Yes | 4558 | 0 | 300 | 4258 | 1290.69 | 0 | 0 | 1290.69
353 | NORTH 24 PARGANAS | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | TSM/010753 | Augmentation | MVS | Yes | 128 | 0 | 0 | 128 | 231.78 | 0 | 0 | 231.78
354 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC | SM/11528 | TSM/011070 | Augmentation | MVS | Yes | 4192 | 0 | 400 | 3792 | 807.83 | 0 | 0 | 807.83
355 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC | SM/11531 | TSM/011077 | Augmentation | MVS | Yes | 564 | 0 | 0 | 564 | 303.04 | 0 | 0 | 303.04
356 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | TSM/011192 | Augmentation | SVS | Yes | 2260 | 0 | 200 | 2060 | 655.97 | 0 | 0 | 655.97
357 | NORTH 24 PARGANAS | Bachhra piped Water supply scheme | SM/12712 | TSM/014837 | New | MVS | Yes | 634 | 0 | 0 | 634 | 642.14 | 0 | 0 | 642.14
358 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC | SM/12123 | TSM/010932 | Augmentation | MVS | Yes | 5111 | 0 | 167 | 4944 | 1321.26 | 0 | 0 | 1321.26
359 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bayra Water Supply Scheme at Bagdah Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. (Phase-I). | SM/08732 | TSM/007650 | Retrofitting | SVS | Yes | 900 | 868 | 0 | 1768 | 91.82 | 0 | 0 | 91.82
360 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Zafarpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08645 | TSM/007606 | Retrofitting | SVS | Yes | 1500 | 0 | 0 | 1500 | 100.07 | 0 | 0 | 100.07
361 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m | SM/08653 | TSM/007627 | Retrofitting | MVS | Yes | 3882 | 0 | 2487 | 1395 | 297.03 | 0 | 0 | 297.03
362 | NORTH 24 PARGANAS | Retrofitting of Rajapura water supply scheme under Hasnabad Block for providing Functional House Tap Connection | SM/07022 | TSM/006284 | Retrofitting | MVS | Yes | 1559 | 135 | 0 | 1694 | 99.68 | 0 | 0 | 99.68
363 | NORTH 24 PARGANAS | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | TSM/015450 | New | MVS | Yes | 976 | 0 | 0 | 976 | 759.76 | 0 | 0 | 759.76
364 | NORTH 24 PARGANAS | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | TSM/015511 | New | SVS | Yes | 564 | 0 | 0 | 564 | 602.01 | 0 | 0 | 602.01
365 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | SM/13547 | TSM/011538 | Retrofitting | MVS | Yes | 16596 | 0 | 1500 | 15096 | 860.32 | 0 | 0 | 860.32
366 | NORTH 24 PARGANAS | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | TSM/018702 | Augmentation | MVS | Yes | 0 | 0 | 0 | 0 | 681.04 | 0 | 0 | 681.04
367 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | TSM/012029 | Augmentation | SVS | Yes | 3639 | 0 | 300 | 3339 | 1151.22 | 0 | 0 | 1151.22
368 | NORTH 24 PARGANAS | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | TSM/015769 | Augmentation | MVS | Yes | 8977 | 0 | 500 | 8477 | 2742.81 | 0 | 0 | 2742.81
369 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of CHAMPAPUKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08658 | TSM/007648 | Retrofitting | MVS | Yes | 1200 | 0 | 0 | 1200 | 80.66 | 0 | 0 | 80.66
370 | NORTH 24 PARGANAS | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | SM/13984 | TSM/014709 | Augmentation | MVS | Yes | 2050 | 11 | 0 | 2061 | 273.98 | 0 | 0 | 273.98
371 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | TSM/009319 | Augmentation | MVS | Yes | 2254 | 0 | 250 | 2004 | 459.65 | 0 | 0 | 459.65
372 | NORTH 24 PARGANAS | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19110 | TSM/020569 | Augmentation | MVS | No | 0 | 0 | 0 | 0 | 874.94 | 0 | 0 | 874.94
373 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | TSM/009253 | Augmentation | MVS | Yes | 2729 | 0 | 250 | 2479 | 439.11 | 0 | 0 | 439.11
374 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | TSM/009763 | Augmentation | MVS | Yes | 1499 | 0 | 100 | 1399 | 540.34 | 0 | 0 | 540.34
375 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | SM/12124 | TSM/010922 | Augmentation | MVS | Yes | 3558 | 0 | 400 | 3158 | 1066.99 | 0 | 0 | 1066.99
376 | NORTH 24 PARGANAS | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | TSM/015584 | Augmentation | MVS | Yes | 4361 | 0 | 800 | 3561 | 2249.01 | 0 | 0 | 2249.01
377 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV/A (Tentulia) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11921 | TSM/011601 | Augmentation | MVS | Yes | 3712 | 0 | 600 | 3112 | 722.76 | 0 | 0 | 722.76
378 | NORTH 24 PARGANAS | TARULIA Piped Water Supply Scheme | SM/18598 | TSM/016290 | New | MVS | Yes | 4266 | 0 | 0 | 4266 | 1481.95 | 0 | 0 | 1481.95
379 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | SM/11653 | TSM/011430 | Augmentation | MVS | Yes | 2561 | 0 | 250 | 2311 | 801.07 | 0 | 0 | 801.07
380 | NORTH 24 PARGANAS | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | TSM/011244 | Augmentation | SVS | Yes | 2387 | 0 | 200 | 2187 | 466.65 | 0 | 0 | 466.65
381 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block | SM/08244 | TSM/007437 | Retrofitting | MVS | Yes | 1454 | 10 | 0 | 1464 | 92.41 | 0 | 0 | 92.41
382 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block | SM/08073 | TSM/007041 | Retrofitting | MVS | Yes | 2132 | 0 | 298 | 1834 | 216.27 | 0 | 0 | 216.27
383 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-IV) at Tentulia OHR site under Phase-I for Arsenic affected areas of North | SM/08040 | TSM/007090 | Retrofitting | MVS | Yes | 1327 | 10 | 0 | 1337 | 84.03 | 0 | 0 | 84.03
384 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bangangram (Zone-I) Water Supply Scheme at Bongaon Block (Phase-II) | SM/08044 | TSM/007084 | Retrofitting | SVS | Yes | 610 | 1 | 0 | 611 | 39.06 | 0 | 0 | 39.06
385 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gobindapur Water Supply Scheme at Bagdah Block (Phase-I) | SM/07850 | TSM/006773 | Retrofitting | MVS | Yes | 1596 | 0 | 0 | 1596 | 97.77 | 0 | 0 | 97.77
386 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07608 | TSM/006923 | Retrofitting | MVS | Yes | 1146 | 781 | 0 | 1927 | 74.49 | 0 | 0 | 74.49
387 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ashudi Water Supply Scheme (Phase-I) | SM/07623 | TSM/006788 | Retrofitting | MVS | Yes | 790 | 0 | 0 | 790 | 50.43 | 0 | 0 | 50.43
388 | NORTH 24 PARGANAS | Retrofitting of Dwarir Jangle water supply scheme under sandeshkhali- II Block for providing Functional House Tap Conection | SM/07026 | TSM/006276 | Retrofitting | SVS | Yes | 1112 | 1634 | 0 | 2746 | 99.54 | 0 | 0 | 99.54
389 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MASIA- NABASTIA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/09226 | TSM/007639 | Retrofitting | MVS | Yes | 1000 | 0 | 0 | 1000 | 67.73 | 0 | 0 | 67.73
390 | NORTH 24 PARGANAS | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08727 | TSM/007653 | Retrofitting | MVS | Yes | 1117 | 0 | 211 | 906 | 99.62 | 0 | 0 | 99.62
391 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gainpur Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. | SM/08730 | TSM/007651 | Retrofitting | MVS | Yes | 462 | 2 | 0 | 464 | 53.55 | 0 | 0 | 53.55
392 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ghatpatila (Zone-I) Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08268 | TSM/007375 | Retrofitting | MVS | Yes | 1763 | 0 | 0 | 1763 | 132.23 | 0 | 0 | 132.23
393 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-II WaterSupply Scheme at Bongaon Block (Phase-I). | SM/08235 | TSM/007279 | Retrofitting | MVS | Yes | 1027 | 13 | 0 | 1040 | 66.16 | 0 | 0 | 66.16
394 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of EOJNAGAR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08655 | TSM/007643 | Retrofitting | MVS | Yes | 1500 | 0 | 0 | 1500 | 97.8 | 0 | 0 | 97.8
395 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of SANKCHURA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08649 | TSM/007628 | Retrofitting | MVS | Yes | 1400 | 0 | 0 | 1400 | 93.7 | 0 | 0 | 93.7
396 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08258 | TSM/007374 | Retrofitting | MVS | Yes | 1450 | 0 | 0 | 1450 | 98.58 | 0 | 0 | 98.58
397 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bira Rajibpur Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08782 | TSM/007607 | Retrofitting | MVS | Yes | 3674 | 0 | 0 | 3674 | 238.36 | 0 | 0 | 238.36
398 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kankpul Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08783 | TSM/007625 | Retrofitting | MVS | Yes | 1585 | 0 | 0 | 1585 | 108.98 | 0 | 0 | 108.98
399 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08262 | TSM/007370 | Retrofitting | SVS | Yes | 1051 | 0 | 0 | 1051 | 79.42 | 0 | 0 | 79.42
400 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | TSM/009732 | Augmentation | SVS | Yes | 728 | 0 | 0 | 728 | 578.18 | 0 | 0 | 578.18
401 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | TSM/010454 | Augmentation | MVS | Yes | 2938 | 0 | 300 | 2638 | 861.96 | 0 | 0 | 861.96
402 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | TSM/009938 | Augmentation | MVS | Yes | 4401 | 0 | 200 | 4201 | 999.1 | 0 | 0 | 999.1
403 | NORTH 24 PARGANAS | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | TSM/010664 | Augmentation | MVS | Yes | 1205 | 0 | 0 | 1205 | 555.72 | 0 | 0 | 555.72
404 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11827 | TSM/011868 | Augmentation | MVS | Yes | 4190 | 0 | 500 | 3690 | 759.19 | 0 | 0 | 759.19
405 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | TSM/010861 | Augmentation | MVS | Yes | 290 | 0 | 0 | 290 | 390.71 | 0 | 0 | 390.71
406 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC | SM/11634 | TSM/011024 | Augmentation | MVS | Yes | 1169 | 0 | 150 | 1019 | 422.18 | 0 | 0 | 422.18
407 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/12625 | TSM/012003 | Augmentation | MVS | Yes | 5714 | 0 | 300 | 5414 | 1198.69 | 0 | 0 | 1198.69
408 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | SM/12277 | TSM/010933 | Augmentation | MVS | Yes | 4638 | 0 | 450 | 4188 | 1728.4 | 0 | 0 | 1728.4
409 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12564 | TSM/011897 | Augmentation | MVS | Yes | 6283 | 0 | 1400 | 4883 | 1438.77 | 0 | 0 | 1438.77
410 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12565 | TSM/011891 | Augmentation | MVS | Yes | 4571 | 0 | 950 | 3621 | 1170.77 | 0 | 0 | 1170.77
411 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | SM/11700 | TSM/011315 | Augmentation | MVS | Yes | 2824 | 0 | 400 | 2424 | 934.27 | 0 | 0 | 934.27
412 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | TSM/011252 | Augmentation | SVS | Yes | 573 | 0 | 0 | 573 | 483.7 | 0 | 0 | 483.7
413 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10503 | TSM/010486 | Retrofitting | SVS | Yes | 2101 | 0 | 1000 | 1101 | 393.8 | 0 | 0 | 393.8
414 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | TSM/011059 | Augmentation | SVS | Yes | 720 | 0 | 0 | 720 | 225.51 | 0 | 0 | 225.51
415 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | TSM/010862 | Augmentation | MVS | Yes | 2998 | 0 | 250 | 2748 | 806.21 | 0 | 0 | 806.21
416 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | TSM/011106 | Augmentation | SVS | Yes | 2273 | 0 | 50 | 2223 | 628.27 | 0 | 0 | 628.27
417 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | TSM/010864 | Augmentation | SVS | Yes | 1296 | 0 | 100 | 1196 | 348.54 | 0 | 0 | 348.54
418 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | TSM/011084 | Augmentation | MVS | Yes | 432 | 415 | 0 | 847 | 376 | 0 | 0 | 376
419 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | TSM/011032 | Augmentation | MVS | Yes | 3115 | 0 | 200 | 2915 | 788.55 | 0 | 0 | 788.55
420 | NORTH 24 PARGANAS | Jhikra Piped Water Supply Scheme. | SM/12719 | TSM/014699 | New | MVS | Yes | 1421 | 0 | 0 | 1421 | 841.62 | 0 | 0 | 841.62
421 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-II) | SM/08075 | TSM/007043 | Retrofitting | SVS | Yes | 1586 | 0 | 555 | 1031 | 163.43 | 0 | 0 | 163.43
422 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10098 | TSM/009448 | Augmentation | MVS | Yes | 5274 | 0 | 0 | 5274 | 843.86 | 0 | 0 | 843.86
423 | NORTH 24 PARGANAS | Bamanpukuria Piped Water Supply Scheme. | SM/13814 | TSM/014705 | New | SVS | Yes | 1777 | 0 | 0 | 1777 | 1179.1 | 0 | 0 | 1179.1
424 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | TSM/011747 | Augmentation | MVS | Yes | 3822 | 0 | 400 | 3422 | 709.88 | 0 | 0 | 709.88
425 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area Shankarpur Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) | SM/07614 | TSM/006779 | Retrofitting | MVS | Yes | 1153 | 0 | 0 | 1153 | 99.79 | 0 | 0 | 99.79
426 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12728 | TSM/011949 | Augmentation | MVS | Yes | 5489 | 0 | 300 | 5189 | 1333.47 | 0 | 0 | 1333.47
427 | NORTH 24 PARGANAS | Debitala Piped Water Supply Scheme | SM/13523 | TSM/015448 | New | SVS | Yes | 1458 | 0 | 0 | 1458 | 978.01 | 0 | 0 | 978.01
428 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | SM/13528 | TSM/011539 | Retrofitting | MVS | Yes | 14740 | 0 | 900 | 13840 | 764.12 | 0 | 0 | 764.12
429 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proj | SM/13536 | TSM/011510 | Retrofitting | MVS | Yes | 14191 | 0 | 700 | 13491 | 735.64 | 0 | 0 | 735.64
430 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/13538 | TSM/011496 | Retrofitting | MVS | Yes | 16662 | 0 | 600 | 16062 | 863.74 | 0 | 0 | 863.74
431 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | SM/13546 | TSM/011562 | Retrofitting | MVS | Yes | 16783 | 0 | 1803 | 14980 | 870.02 | 0 | 0 | 870.02
432 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/14543 | TSM/011488 | Retrofitting | MVS | Yes | 20439 | 0 | 1165 | 19274 | 1059.55 | 0 | 0 | 1059.55
433 | NORTH 24 PARGANAS | Kaugachhi Zone-I Piped Water Supply Scheme | SM/14499 | TSM/016327 | New | SVS | Yes | 1561 | 0 | 500 | 1061 | 661.39 | 0 | 0 | 661.39
434 | NORTH 24 PARGANAS | Gar Shyamnagar Piped Water Supply Scheme | SM/14504 | TSM/016489 | New | SVS | Yes | 2223 | 0 | 500 | 1723 | 870.93 | 0 | 0 | 870.93
435 | NORTH 24 PARGANAS | TEGHARIA Piped Water Supply Scheme | SM/16457 | TSM/016121 | New | MVS | Yes | 1445 | 0 | 0 | 1445 | 806.96 | 0 | 0 | 806.96
436 | NORTH 24 PARGANAS | Bhandarkhali Piped Water Supply Scheme | SM/15827 | TSM/015379 | New | SVS | Yes | 1690 | 0 | 0 | 1690 | 1348.25 | 0 | 0 | 1348.25
437 | NORTH 24 PARGANAS | Bargan Gopalpur Piped Water Supply Scheme | SM/15902 | TSM/015449 | New | MVS | Yes | 789 | 0 | 0 | 789 | 1073.62 | 0 | 0 | 1073.62
438 | NORTH 24 PARGANAS | JATRAGACHHI Piped Water Supply Scheme | SM/16625 | TSM/016452 | New | SVS | Yes | 2053 | 0 | 0 | 2053 | 940.04 | 0 | 0 | 940.04
439 | NORTH 24 PARGANAS | BARDASIA Piped Water Supply Scheme | SM/16626 | TSM/016108 | New | MVS | Yes | 1968 | 0 | 0 | 1968 | 961.59 | 0 | 0 | 961.59
440 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC | SM/17409 | TSM/011381 | Augmentation | MVS | Yes | 711 | 0 | 0 | 711 | 319.7 | 0 | 0 | 319.7
441 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07607 | TSM/006922 | Retrofitting | SVS | Yes | 950 | 12 | 0 | 962 | 65.75 | 0 | 0 | 65.75
442 | NORTH 24 PARGANAS | KOLA Piped Water Supply Scheme | SM/18591 | TSM/016122 | New | MVS | Yes | 3283 | 0 | 0 | 3283 | 1532.91 | 0 | 0 | 1532.91
443 | NORTH 24 PARGANAS | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/11555 | TSM/011010 | Augmentation | MVS | Yes | 2314 | 0 | 200 | 2114 | 639.56 | 0 | 0 | 639.56
444 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18258 | TSM/013336 | Augmentation | MVS | Yes | 6662 | 0 | 500 | 6162 | 1416.18 | 0 | 0 | 1416.18
445 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18259 | TSM/015463 | Augmentation | MVS | Yes | 2938 | 0 | 500 | 2438 | 1062.34 | 0 | 0 | 1062.34
446 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC | SM/11629 | TSM/011078 | Augmentation | MVS | Yes | 2198 | 0 | 200 | 1998 | 589.15 | 0 | 0 | 589.15
447 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | TSM/011083 | Augmentation | MVS | Yes | 3205 | 994 | 0 | 4199 | 639.01 | 0 | 0 | 639.01
448 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/13434 | TSM/013337 | Augmentation | MVS | Yes | 2481 | 0 | 0 | 2481 | 834.96 | 0 | 0 | 834.96
449 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | TSM/011253 | Augmentation | SVS | Yes | 703 | 0 | 0 | 703 | 569.08 | 0 | 0 | 569.08
450 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. | SM/11664 | TSM/011212 | Augmentation | MVS | Yes | 2411 | 0 | 700 | 1711 | 856.02 | 0 | 0 | 856.02
451 | NORTH 24 PARGANAS | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07708 | TSM/006718 | Retrofitting | MVS | Yes | 1247 | 0 | 0 | 1247 | 89.98 | 0 | 0 | 89.98
452 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- | SM/08076 | TSM/007035 | Retrofitting | MVS | Yes | 2274 | 0 | 0 | 2274 | 144.46 | 0 | 0 | 144.46
453 | NORTH 24 PARGANAS | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . | SM/08177 | TSM/007027 | Retrofitting | MVS | Yes | 1762 | 11 | 0 | 1773 | 98.47 | 0 | 0 | 98.47
454 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-V) at Kharki OHR site under (Phase-I) for Arsenic affected areas of North 2 | SM/08046 | TSM/007088 | Retrofitting | MVS | Yes | 1293 | 58 | 0 | 1351 | 94.8 | 0 | 0 | 94.8
455 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ashudi Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) | SM/07619 | TSM/006789 | Retrofitting | SVS | Yes | 349 | 0 | 0 | 349 | 25.19 | 0 | 0 | 25.19
456 | NORTH 24 PARGANAS | Retrofitting of Mahishgadi & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07710 | TSM/006715 | Retrofitting | SVS | Yes | 1402 | 0 | 50 | 1352 | 99.71 | 0 | 0 | 99.71
457 | NORTH 24 PARGANAS | Retrofitting of Paltadanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07711 | TSM/006719 | Retrofitting | MVS | Yes | 1228 | 0 | 0 | 1228 | 89.46 | 0 | 0 | 89.46
458 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hariharpur Water Supply Scheme at Bagdah Block (Phase-I) | SM/07847 | TSM/006768 | Retrofitting | SVS | Yes | 413 | 0 | 0 | 413 | 37.68 | 0 | 0 | 37.68
459 | NORTH 24 PARGANAS | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08725 | TSM/007654 | Retrofitting | SVS | Yes | 765 | 1981 | 0 | 2746 | 70.12 | 0 | 0 | 70.12
460 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Durgamandop Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | SM/08764 | TSM/007371 | Retrofitting | SVS | Yes | 1200 | 0 | 0 | 1200 | 99.01 | 0 | 0 | 99.01
461 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of PASCHIM PANCHBERIA ZONE-II Water Supply Scheme at Bongaon Block (Phase-II). | SM/08240 | TSM/007287 | Retrofitting | MVS | Yes | 1041 | 0 | 1 | 1040 | 56.45 | 0 | 0 | 56.45
462 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block | SM/08241 | TSM/007436 | Retrofitting | MVS | Yes | 3452 | 0 | 672 | 2780 | 249.86 | 0 | 0 | 249.86
463 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamarpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08774 | TSM/007621 | Retrofitting | MVS | Yes | 1161 | 0 | 0 | 1161 | 79.82 | 0 | 0 | 79.82
464 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08775 | TSM/007619 | Retrofitting | MVS | Yes | 3230 | 0 | 0 | 3230 | 210.37 | 0 | 0 | 210.37
465 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of NITYANANDAKATI BALTI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08651 | TSM/007635 | Retrofitting | MVS | Yes | 1200 | 0 | 0 | 1200 | 78.68 | 0 | 0 | 78.68
466 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | TSM/007632 | Retrofitting | MVS | Yes | 4000 | 0 | 0 | 4000 | 253.69 | 0 | 0 | 253.69
467 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DEBOG W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08643 | TSM/007638 | Retrofitting | MVS | Yes | 1500 | 0 | 0 | 1500 | 100.22 | 0 | 0 | 100.22
468 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08257 | TSM/007358 | Retrofitting | MVS | Yes | 1000 | 0 | 200 | 800 | 98.87 | 0 | 0 | 98.87
469 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08261 | TSM/007369 | Retrofitting | SVS | Yes | 1495 | 0 | 0 | 1495 | 97.54 | 0 | 0 | 97.54
470 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | TSM/010391 | Augmentation | MVS | Yes | 1699 | 0 | 250 | 1449 | 662.45 | 0 | 0 | 662.45
471 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | TSM/009760 | Augmentation | MVS | Yes | 3857 | 0 | 400 | 3457 | 702.5 | 0 | 0 | 702.5
472 | NORTH 24 PARGANAS | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10546 | TSM/010666 | Augmentation | MVS | Yes | 3716 | 0 | 250 | 3466 | 685.5 | 0 | 0 | 685.5
473 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | TSM/009252 | Augmentation | MVS | Yes | 3329 | 0 | 350 | 2979 | 509.03 | 0 | 0 | 509.03
474 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | TSM/009738 | Augmentation | MVS | Yes | 1421 | 0 | 500 | 921 | 902.7 | 0 | 0 | 902.7
475 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | TSM/010494 | Retrofitting | MVS | Yes | 4230 | 0 | 0 | 4230 | 619.21 | 0 | 0 | 619.21
476 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | TSM/010493 | Retrofitting | MVS | Yes | 5666 | 0 | 900 | 4766 | 749.52 | 0 | 0 | 749.52
477 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | TSM/009271 | Augmentation | MVS | Yes | 3893 | 0 | 0 | 3893 | 635.68 | 0 | 0 | 635.68
478 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | TSM/009520 | Augmentation | MVS | Yes | 1810 | 0 | 0 | 1810 | 554.31 | 0 | 0 | 554.31
479 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | TSM/009270 | Augmentation | MVS | Yes | 2759 | 0 | 0 | 2759 | 593.99 | 0 | 0 | 593.99
480 | NORTH 24 PARGANAS | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) | SM/09934 | TSM/009214 | Retrofitting | MVS | Yes | 1435 | 0 | 0 | 1435 | 159.77 | 0 | 0 | 159.77
481 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11826 | TSM/011866 | Augmentation | MVS | Yes | 3783 | 0 | 800 | 2983 | 852.16 | 0 | 0 | 852.16
482 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | SM/11537 | TSM/011178 | Augmentation | MVS | Yes | 1237 | 0 | 0 | 1237 | 602.78 | 0 | 0 | 602.78
483 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC | SM/11974 | TSM/011372 | Augmentation | MVS | Yes | 1209 | 0 | 100 | 1109 | 492.05 | 0 | 0 | 492.05
484 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | TSM/011321 | Augmentation | MVS | Yes | 7170 | 0 | 900 | 6270 | 1243.43 | 0 | 0 | 1243.43
485 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC | SM/11657 | TSM/011160 | Augmentation | MVS | Yes | 2838 | 0 | 700 | 2138 | 854.92 | 0 | 0 | 854.92
486 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | TSM/011387 | Augmentation | MVS | Yes | 2131 | 0 | 200 | 1931 | 579.06 | 0 | 0 | 579.06
487 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV (Keyadanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12414 | TSM/014753 | Augmentation | MVS | Yes | 3313 | 0 | 1813 | 1500 | 980.73 | 0 | 0 | 980.73
488 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | TSM/009734 | Augmentation | SVS | Yes | 1463 | 0 | 125 | 1338 | 987.49 | 0 | 0 | 987.49
489 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | TSM/011108 | Augmentation | MVS | Yes | 3453 | 0 | 300 | 3153 | 982.59 | 0 | 0 | 982.59
490 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC | SM/11754 | TSM/011431 | Augmentation | MVS | Yes | 122 | 0 | 0 | 122 | 143.03 | 0 | 0 | 143.03
491 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | TSM/010982 | Augmentation | MVS | Yes | 174 | 0 | 0 | 174 | 301.4 | 0 | 0 | 301.4
492 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | SM/11591 | TSM/011082 | Augmentation | MVS | Yes | 2866 | 0 | 300 | 2566 | 665.35 | 0 | 0 | 665.35
493 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | TSM/011163 | Augmentation | MVS | Yes | 194 | 0 | 0 | 194 | 307.03 | 0 | 0 | 307.03
494 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | SM/11599 | TSM/010856 | Augmentation | MVS | Yes | 450 | 0 | 0 | 450 | 543.61 | 0 | 0 | 543.61
495 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | SM/11601 | TSM/010858 | Augmentation | MVS | Yes | 1075 | 0 | 100 | 975 | 458.81 | 0 | 0 | 458.81
496 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11663 | TSM/010997 | Augmentation | MVS | Yes | 150 | 0 | 0 | 150 | 417.93 | 0 | 0 | 417.93
497 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC | SM/11665 | TSM/011081 | Augmentation | MVS | Yes | 1513 | 0 | 100 | 1413 | 385.74 | 0 | 0 | 385.74
498 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | TSM/011068 | Augmentation | SVS | Yes | 1226 | 0 | 100 | 1126 | 580.98 | 0 | 0 | 580.98
499 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | SM/11527 | TSM/011069 | Augmentation | MVS | Yes | 1824 | 0 | 150 | 1674 | 619.07 | 0 | 0 | 619.07
500 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | TSM/011191 | Augmentation | MVS | Yes | 905 | 0 | 200 | 705 | 489.12 | 0 | 0 | 489.12
501 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC | SM/11541 | TSM/011028 | Augmentation | MVS | Yes | 743 | 0 | 0 | 743 | 214.46 | 0 | 0 | 214.46
502 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-II) at Habra-I Block (Phase-I) | SM/08779 | TSM/007614 | Retrofitting | MVS | Yes | 2765 | 0 | 0 | 2765 | 187.55 | 0 | 0 | 187.55
503 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | TSM/011313 | Augmentation | MVS | Yes | 687 | 0 | 0 | 687 | 347.67 | 0 | 0 | 347.67
504 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | SM/11633 | TSM/011030 | Augmentation | MVS | Yes | 3239 | 0 | 350 | 2889 | 834.18 | 0 | 0 | 834.18
505 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | SM/11635 | TSM/011025 | Augmentation | MVS | Yes | 2112 | 0 | 200 | 1912 | 531.4 | 0 | 0 | 531.4
506 | NORTH 24 PARGANAS | Ghipukuria Piped Water Supply Scheme. | SM/12718 | TSM/014711 | New | MVS | Yes | 955 | 0 | 0 | 955 | 756.27 | 0 | 0 | 756.27
507 | NORTH 24 PARGANAS | Tapla Kusangra Piped Water Supply Scheme. | SM/12720 | TSM/014693 | New | MVS | Yes | 1247 | 0 | 0 | 1247 | 807.9 | 0 | 0 | 807.9
508 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | TSM/011158 | Augmentation | MVS | Yes | 2807 | 0 | 800 | 2007 | 1001.57 | 0 | 0 | 1001.57
509 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | TSM/010863 | Augmentation | MVS | Yes | 3357 | 0 | 300 | 3057 | 1302.34 | 0 | 0 | 1302.34
510 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | TSM/011380 | Augmentation | MVS | Yes | 6343 | 0 | 500 | 5843 | 1175.82 | 0 | 0 | 1175.82
511 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-II-Berunanpukuria OHR) at Barasat-I Block | SM/08242 | TSM/007434 | Retrofitting | MVS | Yes | 1170 | 9 | 0 | 1179 | 88.07 | 0 | 0 | 88.07
512 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | TSM/011320 | Augmentation | MVS | Yes | 6862 | 0 | 600 | 6262 | 1211.19 | 0 | 0 | 1211.19
513 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/B (Gopalpur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12730 | TSM/011602 | Augmentation | MVS | Yes | 4743 | 0 | 300 | 4443 | 1112.7 | 0 | 0 | 1112.7
514 | NORTH 24 PARGANAS | Kharibaria Piped Water Supply Scheme. | SM/13519 | TSM/015444 | New | MVS | Yes | 1485 | 0 | 0 | 1485 | 978.77 | 0 | 0 | 978.77
515 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | SM/13529 | TSM/011536 | Retrofitting | MVS | Yes | 15411 | 0 | 1400 | 14011 | 798.89 | 0 | 0 | 798.89
516 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/13544 | TSM/011557 | Retrofitting | MVS | Yes | 11200 | 0 | 1400 | 9800 | 580.6 | 0 | 0 | 580.6
517 | NORTH 24 PARGANAS | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | TSM/015552 | Augmentation | SVS | Yes | 1584 | 0 | 100 | 1484 | 627.98 | 0 | 0 | 627.98
518 | NORTH 24 PARGANAS | Balibhara Piped Water Supply Scheme | SM/14498 | TSM/016295 | New | SVS | Yes | 2442 | 0 | 500 | 1942 | 939.28 | 0 | 0 | 939.28
519 | NORTH 24 PARGANAS | Kaugachhi Zone-II Piped Water Supply Scheme | SM/14500 | TSM/016488 | New | SVS | Yes | 2082 | 0 | 500 | 1582 | 865.1 | 0 | 0 | 865.1
520 | NORTH 24 PARGANAS | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. | SM/14501 | TSM/017266 | New | MVS | Yes | 129 | 0 | 0 | 129 | 121.26 | 0 | 0 | 121.26
521 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadpur Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08781 | TSM/007609 | Retrofitting | SVS | Yes | 1200 | 0 | 0 | 1200 | 80.33 | 0 | 0 | 80.33
522 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15818 | TSM/014884 | Augmentation | MVS | Yes | 4330 | 0 | 704 | 3626 | 1369.68 | 0 | 0 | 1369.68
523 | NORTH 24 PARGANAS | Matbari Abad Piped Water Supply Scheme | SM/15825 | TSM/015514 | New | SVS | Yes | 1601 | 0 | 0 | 1601 | 1326.01 | 0 | 0 | 1326.01
524 | NORTH 24 PARGANAS | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | TSM/015515 | New | MVS | Yes | 2029 | 0 | 0 | 2029 | 1127.24 | 0 | 0 | 1127.24
525 | NORTH 24 PARGANAS | Petua Dhanihati Piped Water Supply Scheme | SM/15830 | TSM/015512 | New | MVS | Yes | 1144 | 0 | 0 | 1144 | 1122.5 | 0 | 0 | 1122.5
526 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | SM/08765 | TSM/007367 | Retrofitting | SVS | Yes | 1300 | 0 | 0 | 1300 | 99.39 | 0 | 0 | 99.39
527 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GHONA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08648 | TSM/007649 | Retrofitting | MVS | Yes | 1000 | 0 | 0 | 1000 | 67.63 | 0 | 0 | 67.63
528 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18262 | TSM/015472 | Augmentation | MVS | Yes | 2691 | 0 | 500 | 2191 | 1228.72 | 0 | 0 | 1228.72
529 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | TSM/010571 | Augmentation | MVS | Yes | 2391 | 0 | 200 | 2191 | 846.22 | 0 | 0 | 846.22
530 | NORTH 24 PARGANAS | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | TSM/015754 | New | SVS | Yes | 3261 | 0 | 0 | 3261 | 2028.44 | 0 | 0 | 2028.44
531 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC | SM/18618 | TSM/011390 | Augmentation | SVS | Yes | 2811 | 0 | 0 | 2811 | 1018.08 | 0 | 0 | 1018.08
532 | NORTH 24 PARGANAS | Augmentation of Mathurabil Zone-II in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19109 | TSM/020570 | Augmentation | MVS | No | 0 | 0 | 0 | 0 | 940.91 | 0 | 0 | 940.91
533 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | TSM/010692 | Retrofitting | MVS | Yes | 874 | 0 | 0 | 874 | 122.05 | 0 | 0 | 122.05
534 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | TSM/011161 | Augmentation | MVS | Yes | 7789 | 0 | 700 | 7089 | 2154.42 | 0 | 0 | 2154.42
535 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12383 | TSM/014883 | Augmentation | MVS | Yes | 2750 | 0 | 600 | 2150 | 961.03 | 0 | 0 | 961.03
536 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | TSM/010448 | Augmentation | MVS | Yes | 1988 | 0 | 200 | 1788 | 539.33 | 0 | 0 | 539.33
537 | NORTH 24 PARGANAS | GHUNI Piped Water Supply Scheme | SM/18537 | TSM/016293 | New | SVS | Yes | 5806 | 0 | 0 | 5806 | 1721.16 | 0 | 0 | 1721.16
Grand Total | [7 empty] | 1649377 | 43686 | 256188 | 1436875 | 342333.86 | 0 | 8.5 | 342325.36