## Completed Schemes
Completed Schemes
Sl. No. | Division | District | Block | Scheme SM Code | Scheme Name | Scheme Type | Scheme Coverage Type | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Date of Completion | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %) | Name of JE entrusted
1 | South 24 Pgs. W/S Division - I | SOUTH 24 PARGANAS | Budge Budge - II | SM/06642 | Connection with prevention of Dengue in Different BPHC/RH/PHC locations under 8 nos. blocks of South 24 Parganas | New | MVS | 10/02/2020 |  |  | 31/08/2020 |  | 0 | 0 | 57.21 | 0 | 100 | 0
2 | Alipore Division | SOUTH 24 PARGANAS |  | SM/06643 | Different construction work for prevention of Dengue at different BPHC/RH/PHC in different locations under different blocks in the district of South 24 Parganas | New | MVS | 10/02/2020 |  |  | 31/08/2020 |  | 0 | 0 | 32.42 | 0 | 100 | 0
3 | South 24 Pgs. W/S Division - I | SOUTH 24 PARGANAS | Budge Budge - I | SM/07018 | Retrofitting of distribution System For Nischintipur W/S Scheme for Nischintipur Mouza near Head Work Site and Adjoining Areas under Budge Budge-I Block | Retrofitting | SVS | 18/11/2020 | 08/12/2020 | 31/03/2025 | 11/12/2025 | 23/07/2023 | 1 | 1500 | 94.23 | 160.03 | 100 | 170
4 | Alipore Division | SOUTH 24 PARGANAS | Kakdwip | SM/07397 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | Retrofitting | SVS | 29/12/2020 | 23/01/2018 | 31/03/2025 | 11/12/2025 | 31/08/2019 | 8 | 1016 | 93.47 | 123.8 | 100 | 132 | Juniour Engineer_4, Kakdwip Sub Division
5 | Alipore Division | SOUTH 24 PARGANAS | Kakdwip | SM/07399 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu | Retrofitting | SVS | 29/12/2020 | 20/12/2017 | 31/03/2025 | 11/12/2025 | 31/08/2019 | 5 | 1557 | 58.55 | 28.38 | 100 | 48 | Juniour Engineer_1, Kakdwip Sub Division
6 | Alipore Division | SOUTH 24 PARGANAS | Kakdwip | SM/07400 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme includ | Retrofitting | MVS | 29/12/2020 | 20/12/2017 | 31/03/2025 | 11/12/2025 | 31/08/2019 | 2 | 1774 | 72.43 | 112 | 100 | 155 | Juniour Engineer_1, Kakdwip Sub Division
7 | Alipore Division | SOUTH 24 PARGANAS | Namkhana | SM/07402 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kusumtala W/S Scheme includ | Retrofitting | SVS | 29/12/2020 | 09/05/2018 | 31/03/2025 | 11/12/2025 |  | 3 | 1276 | 92.72 | 119.03 | 100 | 128
8 | Alipore Division | SOUTH 24 PARGANAS | Kakdwip | SM/07576 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | Retrofitting | MVS | 31/12/2020 | 30/12/2016 | 31/03/2025 | 11/12/2025 | 31/08/2019 | 16 | 1104 | 88.57 | 85.71 | 100 | 97 | Juniour Engineer_4, Kakdwip Sub Division
9 | Alipore Division | SOUTH 24 PARGANAS | Kakdwip | SM/07579 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Koaberia W/S Scheme including | Retrofitting | MVS | 31/12/2020 | 04/05/2016 | 31/03/2025 | 11/12/2025 | 30/11/2018 | 8 | 1071 | 82.67 | 54.52 | 100 | 66 | Juniour Engineer_4, Kakdwip Sub Division
10 | Alipore Division | SOUTH 24 PARGANAS | Sagar | SM/07584 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | Retrofitting | MVS | 31/12/2020 | 25/03/2016 | 31/12/2025 | 11/12/2025 | 16/04/2018 | 1 | 1613 | 80.41 | 160.82 | 100 | 200 | Juniour Engineer_2, Kakdwip Sub Division
11 | Alipore Division | SOUTH 24 PARGANAS | Namkhana | SM/07585 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dwarikanagar W/S Scheme includ | Retrofitting | SVS | 31/12/2020 | 05/12/2017 | 31/03/2025 | 11/12/2025 | 31/12/2020 | 1 | 1888 | 61.06 | 0 | 100 | 0 | Juniour Engineer_1, Kakdwip Sub Division
12 | Alipore Division | SOUTH 24 PARGANAS | Namkhana | SM/07586 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dwarikanagar W/S Scheme includ | Retrofitting | SVS | 31/12/2020 | 05/12/2017 | 31/03/2025 | 11/12/2025 | 31/12/2020 | 2 | 877 | 61.02 | 19.32 | 100 | 32 | Juniour Engineer_1, Kakdwip Sub Division
13 | Alipore Division | SOUTH 24 PARGANAS | Sagar | SM/07587 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | Retrofitting | SVS | 31/12/2020 | 25/03/2016 | 31/12/2025 | 11/12/2025 | 16/04/2018 | 4 | 1074 | 79.53 | 45.46 | 100 | 57 | Juniour Engineer_2, Kakdwip Sub Division
14 | Alipore Division | SOUTH 24 PARGANAS | Canning - II | SM/07594 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Singheswar Water Supply S | Retrofitting | MVS | 31/12/2020 | 03/01/2017 | 31/05/2025 | 11/12/2025 | 30/11/2018 | 1 | 1349 | 72.82 | 107.85 | 100 | 148 | Junior Engineer, 2 CSD
15 | Alipore Division | SOUTH 24 PARGANAS | Gosaba | SM/07595 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Luxbagan Water Supply Sche | Retrofitting | SVS | 31/12/2020 | 22/01/2018 | 31/03/2025 | 11/12/2025 | 30/11/2020 | 1 | 1119 | 72.33 | 104.59 | 100 | 145 | Junior Engineer, 3 CSD
16 | Alipore Division | SOUTH 24 PARGANAS | Gosaba | SM/07597 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Puinjali Water Supply Sche | Retrofitting | SVS | 31/12/2020 | 29/12/2017 | 31/03/2025 | 11/12/2025 | 30/11/2020 | 2 | 1323 | 87.3 | 17.92 | 100 | 21 | Junior Engineer, 3 CSD
17 | Alipore Division | SOUTH 24 PARGANAS | Canning - I | SM/07598 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bhaleya Water Supply Sch | Retrofitting | MVS | 31/12/2020 | 30/05/2016 | 31/12/2025 | 11/12/2025 | 30/11/2018 | 1 | 1641 | 92.37 | 110.6 | 100 | 120 | Junior Engineer,1 CSD
18 | Alipore Division | SOUTH 24 PARGANAS | Patharpratima | SM/07626 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinarayanpur W/S Scheme in | Retrofitting | SVS | 07/01/2021 | 30/12/2016 | 30/09/2025 | 11/12/2025 | 31/08/2019 | 2 | 3074 | 225.98 | 252.84 | 100 | 112 | Juniour Engineer_3, Kakdwip Sub Division
19 | Alipore Division | SOUTH 24 PARGANAS | Basanti | SM/07627 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 04 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lot-126 Water Supply Sche | Retrofitting | SVS | 07/01/2021 | 08/05/2018 | 31/10/2025 | 11/12/2025 | 30/11/2020 | 3 | 3820 | 204.47 | 334.46 | 100 | 164
20 | Alipore Division | SOUTH 24 PARGANAS | Canning - I | SM/07628 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Sch | Retrofitting | MVS | 07/01/2021 | 30/11/2015 | 31/08/2025 | 11/12/2025 | 16/04/2018 | 6 | 2601 | 169.04 | 164.11 | 100 | 97 | Junior Engineer, 4 CSD
21 | Alipore Division | SOUTH 24 PARGANAS | Canning - II | SM/07632 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Narayanpur Water Supply Sc | Retrofitting | SVS | 07/01/2021 | 17/09/2015 | 31/03/2025 | 11/12/2025 | 08/03/2018 | 1 | 2005 | 126.68 | 114.06 | 100 | 90 | Junior Engineer, 2 CSD
22 | Alipore Division | SOUTH 24 PARGANAS | Canning - I | SM/07634 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Banibadabelekhali Wat | Retrofitting | MVS | 07/01/2021 | 05/01/2015 | 31/03/2025 | 11/12/2025 | 18/01/2018 | 2 | 3369 | 175.16 | 264.27 | 100 | 151 | Junior Engineer,1 CSD
23 | Alipore Division | SOUTH 24 PARGANAS | Canning - I | SM/07637 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Uttar Angadberia Water | Retrofitting | MVS | 07/01/2021 | 04/05/2016 | 31/12/2025 | 11/12/2025 | 31/08/2019 | 1 | 2101 | 114.83 | 98.61 | 100 | 86 | Junior Engineer,1 CSD
24 | Alipore Division | SOUTH 24 PARGANAS | Canning - I | SM/07641 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | Retrofitting | MVS | 07/01/2021 | 02/01/2017 | 31/12/2025 | 11/12/2025 | 30/11/2020 | 42 | 3908 | 207.07 | 185.32 | 100 | 89 | Junior Engineer, 4 CSD
25 | Alipore Division | SOUTH 24 PARGANAS | Basanti | SM/07642 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | Retrofitting | MVS | 07/01/2021 | 01/06/2016 | 31/03/2025 | 11/12/2025 | 16/04/2018 | 7 | 2122 | 117.22 | 179.21 | 100 | 153 | Junior Engineer,1 CSD
26 | Alipore Division | SOUTH 24 PARGANAS | Basanti | SM/07643 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jyotishpur Water Supply S | Retrofitting | MVS | 07/01/2021 | 22/01/2018 | 31/12/2025 | 11/12/2025 | 30/11/2020 | 1 | 2153 | 117.77 | 152.44 | 100 | 129 | Junior Engineer, 4 CSD
27 | Alipore Division | SOUTH 24 PARGANAS | Basanti | SM/07644 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Goran Bose Water Supply Sc | Retrofitting | SVS | 07/01/2021 | 17/01/2017 | 31/12/2025 | 11/12/2025 | 16/04/2018 | 5 | 2754 | 147.9 | 90.65 | 100 | 61 | Junior Engineer,1 CSD
28 | Alipore Division | SOUTH 24 PARGANAS | Sagar | SM/07754 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | Retrofitting | MVS | 08/01/2021 | 01/04/2016 | 30/09/2025 | 11/12/2025 | 16/04/2018 | 21 | 1417 | 150.06 | 108.11 | 100 | 72 | Juniour Engineer_5, Kakdwip Sub Division
29 | Alipore Division | SOUTH 24 PARGANAS | Sagar | SM/07757 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chemaguri W/S Scheme including | Retrofitting | SVS | 08/01/2021 | 18/12/2017 | 31/03/2025 | 11/12/2025 | 31/08/2019 | 4 | 1447 | 135.9 | 90.64 | 100 | 67 | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division
30 | Alipore Division | SOUTH 24 PARGANAS | Sagar | SM/07759 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | Retrofitting | SVS | 08/01/2021 | 25/01/2017 | 30/09/2025 | 11/12/2025 | 16/04/2018 | 7 | 987 | 101.4 | 127.86 | 100 | 126
31 | Alipore Division | SOUTH 24 PARGANAS | Gosaba | SM/07763 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | Retrofitting | SVS | 08/01/2021 | 29/12/2017 | 31/12/2025 | 11/12/2025 | 30/11/2020 | 29 | 1745 | 119.81 | 115.42 | 100 | 96 | Junior Engineer, 3 CSD
32 | Alipore Division | SOUTH 24 PARGANAS | Canning - I | SM/08028 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bansra Water Supply Scheme | Retrofitting | SVS | 29/01/2021 | 02/06/2016 | 31/03/2025 | 11/12/2025 | 16/04/2018 | 2 | 6607 | 352.06 | 208.81 | 100 | 59 | Junior Engineer, 2 CSD
33 | Alipore Division | SOUTH 24 PARGANAS | Canning - I | SM/08637 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year | Retrofitting | MVS | 27/05/2021 | 09/01/2018 | 31/12/2025 | 11/12/2025 | 30/11/2020 | 4 | 2953 | 157.43 | 154.7 | 100 | 98 | Junior Engineer, 2 CSD
34 | Alipore Division | SOUTH 24 PARGANAS | Canning - II | SM/09094 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one y | Retrofitting | SVS | 29/10/2021 | 02/05/2016 | 31/12/2025 | 11/12/2025 | 31/08/2019 | 4 | 1513 | 95.53 | 82.01 | 100 | 86 | Junior Engineer,1 CSD
35 | Alipore Division | SOUTH 24 PARGANAS | Canning - II | SM/09096 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daharani Water Supply Scheme including one year | Retrofitting | MVS | 29/10/2021 | 05/09/2017 | 31/03/2025 | 11/12/2025 | 30/11/2020 | 3 | 2857 | 165.49 | 73.69 | 100 | 45 | Junior Engineer, 2 CSD
36 | Alipore Division | SOUTH 24 PARGANAS | Basanti | SM/10560 | ADDITIONAL WORK FOR RETROFITTING OF DISTRIBUTION SYSTEM FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ADDITIONAL HOUSEHOLD (1219 NOS.) IN EXCESS OF IMIS IN CONNECTION FOR LOT NO. - 126 WATER SUPPLY SCHEME INCLUDING ONE YEAR OPERATION AND MAI | Augmentation | SVS | 18/04/2022 | 08/05/2018 | 31/10/2025 | 11/12/2025 | 30/11/2020 | 2 | 1219 | 73.48 | 11.34 | 100 | 15 | Junior Engineer,1 CSD
37 | South 24 Pgs. W/S Division - I | SOUTH 24 PARGANAS | Bhangar - I | SM/13512 | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | Augmentation | MVS | 02/11/2022 | 27/02/2023 | 31/05/2025 | 11/12/2025 | 23/05/2025 | 8 | 1406 | 797.02 | 507.9 | 100 | 64 | Junior Engineer
38 | Alipore Division | SOUTH 24 PARGANAS | Sagar | SM/13972 | AUGMENTATION FOR GROUND WATER BASED RADHAKRISHNAPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | Augmentation | SVS | 01/12/2022 | 25/01/2017 | 30/09/2025 | 11/12/2025 | 16/04/2018 | 15 | 806 | 688.41 | 231.26 | 100 | 34 | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division
39 | Investigation Unit | SOUTH 24 PARGANAS |  | SM/18986 | Additional Cost Requirement for Procurement of Service of Consultants for Preparation of DPR, District - Nadia, Bankura, Paschim Bardhaman, Kalimpong, North-24 Parganas, Purba Medinipur and Jhargram. |  | MVS | 12/10/2023 |  |  | 12/10/2023 |  | 0 | 0 | 478.84 | 955.33 | 100 | 200
Total | [12 empty] | 225 | 71046 | 6200.66 | 5753.07 | # | 93 | #