## A3- Land Parcel Status
A3- Land Parcel Status
SL No | District | Scheme Name | Scheme TSM Code | Scheme SM Code | Scheme Category | Scheme Coverage Type | Block | Village | Location | Purpose | Type | J.L. No. | Khatian No. | Plot No. | Area (in decimal) | Status | Remarks
1 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Gangaram Maler Chhat | TW SITE | Pump House | Vested | 60 | 1 | 12 | 3 | Possessed | null
2 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Bharia Dangir Chhat | TW SITE | Pump House | Vested | 24 | 1 | 68 | 3 | Possessed | null
3 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Pathar Hirhira | TW SITE | Pump House | Vested | 25 | 192 | 619 | 3 | Possessed | null
4 | DARJEELING | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III )(TSM/010330,SM/18321) | TSM/010330 | SM/18321 | New | MVS | Phansidewa | Narayan | OHR SITE | Pump House | Private | 75 | 1158 | 463 | 4 | Identified | Direct Purchase proposal sent to HQ 2nd lot
5 | DARJEELING | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME (TSM/010344,SM/11785) | TSM/010344 | SM/11785 | New | MVS | Phansidewa | Bansh Gaon Mangachh | TW SITE | Pump House | Private | 97 | 322 | 1250 | 8 | Identified | null
6 | DARJEELING | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME(TSM/018460,SM/18386) | TSM/018460 | SM/18386 | Augmentation | MVS | Matigara | Thiknikata | TW SITE | Pump House | Vested | 74 | 3624 | 109 | 3 | Possessed | Writ of possesion received in favour of PHED
7 | DARJEELING | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME(TSM/009101,SM/10476) | TSM/009101 | SM/10476 | Augmentation | SVS | Naxalbari | Dumriguri (CT) | TW SITE | Pump House | Private | 94 | 4545 | 707 | 3 | Identified | Direct Purchase proposal sent to HQ 2nd lot construction started
8 | DARJEELING | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME(TSM/009499,SM/10714) | TSM/009499 | SM/10714 | Augmentation | MVS | Phansidewa | Mahipal | TW SITE | Pump House | Private | 88 | 286 | 356 | 3 | Identified | Direct Purchase proposal sent to HQ 3RD LOT
9 | DARJEELING | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME(TSM/009555,SM/18421) | TSM/009555 | SM/18421 | Augmentation | MVS | Kharibari | Bhogbhita | OHR SITE | OHR | Vested | 44 | 623 | 139 | 18 | Identified | Writ of possession received in fever of PHED,IDT done
10 | DARJEELING | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010327,SM/13440) | TSM/010327 | SM/13440 | New | MVS | Naxalbari | Manjha Tea Garden | TW SITE | Pump House | Vested | 4 | 52 | 412 | 3 | Possessed | NOC FROM TG RECEIVED RESUMPTION IS IN PROCESS
11 | DARJEELING | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010333,SM/18614) | TSM/010333 | SM/18614 | New | MVS | Phansidewa | Meherulla | OHR SITE | OHR | Vested | 61 | 17 | 67 | 33 | Identified | DEVELOPED AREA OF TG CONVERTED TO VESTED , IDT to be initiated
12 | DARJEELING | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME (TSM/020169,SM/15270) | TSM/020169 | SM/15270 | Augmentation | MVS | Naxalbari | Gaziram | TW SITE | Pump House | Vested | 60 | 1 | 1 | 5 | Identified | NOC received from Merry View Tea Estate, Joint visit with BLLRO awaited to identify plot no
13 | DARJEELING | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME (TSM/020168,SM/15271) | TSM/020168 | SM/15271 | Augmentation | MVS | Naxalbari | Mirjangler Chhat | TW SITE | Pump House | Vested | 70 | 135 | 2 | 5 | Identified | joint inspection with BLLRO awaited, Pattta land NOC Received from patta holder, amalgamation process to be initiated
14 | DARJEELING | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009575,SM/10183) | TSM/009575 | SM/10183 | Augmentation | MVS | Naxalbari | Geni (CT) | TW SITE | Pump House | Vested | 26 | 2988 | 502 | 3 | Possessed | Writ of possesion received in favour of PHED construction started
15 | DARJEELING | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME (TSM/020165,SM/15274) | TSM/020165 | SM/15274 | Augmentation | MVS | Phansidewa | Purba Bansgaon | TW SITE | Pump House | Private | 113 | 671 | 668 | 5 | Identified | NOC receievd from Owner , Direct purchase proposal to be initiated
16 | DARJEELING | HETMURI PIPED WATER SUPPLY SCHEME (TSM/010346,SM/12750) | TSM/010346 | SM/12750 | New | MVS | Phansidewa | Hetmuri | 2ND TW | Pump House | Private | 85 | 262 | 942 | 3 | Identified | NOC received direct purchase proposal to be initiated
17 | DARJEELING | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME(TSM/012605,SM/12749) | TSM/012605 | SM/12749 | Augmentation | SVS | Naxalbari | Ord Terai Tea Garden | TW SITE | Pump House | Vested | 75 | 2 | 254 | 3 | Possessed | TG LAND Resumption is in process
18 | DARJEELING | HETMURI PIPED WATER SUPPLY SCHEME (TSM/010346,SM/12750) | TSM/010346 | SM/12750 | New | MVS | Phansidewa | Nembutari | TW SITE | Pump House | Vested | 86 | 421 | 34 | 10 | Possessed | Writ of possession received in favour of PHED
19 | DARJEELING | HETMURI PIPED WATER SUPPLY SCHEME (TSM/010346,SM/12750) | TSM/010346 | SM/12750 | New | MVS | Phansidewa | Kadmi | TW SITE | Pump House | Private | 90 | 193 | 867 | 5 | Identified | Direct Purchase proposal sent to HQ 3rd lot
20 | DARJEELING | DEBIGANJA PIPED WATER SUPPLY SCHEME (TSM/010335,SM/15925) | TSM/010335 | SM/15925 | New | MVS | Kharibari | Banchhabhita | OHR SITE | OHR | Vested | 35 | 50 | 187 | 33 | Identified | Writ of possession received in fever of PHED,IDT pending.
21 | DARJEELING | M.M.TERAI PIPED WATER SUPPLY SCHEME (TSM/010340,SM/11775) | TSM/010340 | SM/11775 | New | MVS | Naxalbari | M.M.Terai | TW SITE | Pump House | Vested | 77 | 77 | 24 | 5 | Possessed | TG land
22 | DARJEELING | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME(TSM/012588,SM/12773) | TSM/012588 | SM/12773 | Augmentation | MVS | Naxalbari | Barajharu | TW | Pump House | Private | 50 | 1 | 1 | 3 | Identified | Direct Purcahse proposal to be initiated PLOT no to be updated
23 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Kharibari | Fulbarir Chhat | TW SITE | Pump House | Vested | 47 | 1 | 11 | 3 | Possessed | null
24 | DARJEELING | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME(TSM/009292,SM/18637) | TSM/009292 | SM/18637 | Augmentation | MVS | Naxalbari | Rangapani | TW SITE | Pump House | Private | 105 | 2651 | 738 | 3 | Identified | Direct proposal to be sent previous plot of direct purchase 737 owner denied
25 | DARJEELING | BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME (TSM/010341,SM/11777) | TSM/010341 | SM/11777 | New | MVS | Naxalbari | Bhujia Banir Chhat | TW SITE | Pump House | Vested | 97 | 1 | 0 | 5 | Identified | Identified nearest to the Mouza at proposed Bhujiabani Health Center
26 | DARJEELING | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III)(TSM/010331,SM/13509) | TSM/010331 | SM/13509 | New | MVS | Kharibari | Fulbari | TW SITE | Pump House | Vested | 46 | 1 | 413 | 4 | Identified | TG Land under Fulbari Tea Estate,IDT Pending.
27 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Baraigachh | TW SITE | Pump House | Donated | 65 | 1 | 1 | 3 | Possessed | null
28 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Krishnapur Tea Garden | TW SITE | Pump House | Vested | 3 | 2 | 51 | 3 | Possessed | null
29 | DARJEELING | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III)(TSM/010325,SM/14150) | TSM/010325 | SM/14150 | New | MVS | Phansidewa | Sannyasi Thaner Chhat | TW SITE Z3 | Pump House | Vested | 4 | 2 | 242 | 5 | Identified | TG LAND
30 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Kadubhita | TW SITE | Pump House | Vested | 36 | 49 | 651 | 3 | Possessed | null
31 | DARJEELING | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III)(TSM/010331,SM/13509) | TSM/010331 | SM/13509 | New | MVS | Kharibari | Fulbari | TW SITE | Pump House | Vested | 46 | 500 | 404 | 5 | Identified | ActualyyJL NO 45 Vest Land,IDT done.
32 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Dhakna Gachh | TW SITE | Pump House | Vested | 37 | 26 | 59 | 3 | Possessed | null
33 | DARJEELING | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (TSM/010337,SM/12751) | TSM/010337 | SM/12751 | New | MVS | Matigara | Mohorgon Tea Garden | TW SITE | Pump House | Vested | 30 | 4 | 703 | 5 | Possessed | Writ of possesion received in favour of PHED
34 | DARJEELING | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME (TSM/020168,SM/15271) | TSM/020168 | SM/15271 | Augmentation | MVS | Naxalbari | Huchaimallik | TW SITE | Pump House | Vested | 64 | 729 | 279 | 4 | Identified | joint inspection with BLLRO awaited, Pattta land NOC Received from patta holder, amalgamation process to be initiated
35 | DARJEELING | Augmentation of Chuchur Muchur Piped Water Supply Scheme (TSM/015197,SM/13427) | TSM/015197 | SM/13427 | Augmentation | MVS | Kharibari | Chuchur Muchur | TW SITE | Pump House | Vested | 72 | 2 | 178 | 3 | Possessed | TG LAND Resumption is in process
36 | DARJEELING | AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME (TSM/020164,SM/15272) | TSM/020164 | SM/15272 | Augmentation | MVS | Phansidewa | Sahananda | TW SITE | Pump House | Private | 91 | 179 | 717 | 5 | Identified | NOC received from owner ,direct Purchase proposal to be initiated
37 | DARJEELING | Augmentation of Arjunmahal Piped Water Supply Scheme (TSM/015194,SM/13395) | TSM/015194 | SM/13395 | Augmentation | SVS | Kharibari | Arjunmahal | TW SITE | Pump House | Private | 73 | 81 | 62 | 3 | Identified | DLPC purchase to be initiated
38 | DARJEELING | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME (TSM/015582,SM/13467) | TSM/015582 | SM/13467 | Augmentation | MVS | Phansidewa | Dhakpara | TW SITE | Pump House | Private | 105 | 287 | 2433 | 4 | Identified | NOC received direct purchase proposal to be initiated
39 | DARJEELING | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010332,SM/15927) | TSM/010332 | SM/15927 | New | MVS | Naxalbari | Tarabarir Chhat | TW SITE | Pump House | Vested | 85 | 47 | 118 | 3 | Identified | ACTUAL LAND AT DHEMAL JL 83 SINCE IT IS OUTSIDE COVERAGE UNDER 100 HOUSEHOLD CANNOT BE ENTERED HERE
40 | DARJEELING | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme (TSM/015191,SM/13433) | TSM/015191 | SM/13433 | Augmentation | SVS | Phansidewa | Uttar Bansgaon Kismat | OHR SITE | OHR | Private | 96 | 2914 | 2341 | 23 | Identified | Direct purchase proposal to be initiated
41 | DARJEELING | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME (TSM/018448,SM/18385) | TSM/018448 | SM/18385 | Augmentation | MVS | Matigara | Palash | OHR SITE | OHR | Private | 43 | 1 | 1 | 33 | Identified | IDENTIFIED
42 | DARJEELING | Nichitpur Piped Water Supply Scheme (TSM/015201,SM/13438) | TSM/015201 | SM/13438 | New | SVS | Matigara | Nichitpur | TW SITE | Pump House | Vested | 54 | 3 | 260 | 25 | Identified | NICHITPUR TG LAND RESUMPTION OF LAND IS IN PROCESS
43 | DARJEELING | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME (TSM/018448,SM/18385) | TSM/018448 | SM/18385 | Augmentation | MVS | Matigara | Karaibari | OHR SITE | OHR | Vested | 39 | 1 | 0 | 33 | Identified | Identified at Karabari Jote Primary School, NOC from DPSC chairman received
44 | DARJEELING | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME(TSM/018460,SM/18386) | TSM/018460 | SM/18386 | Augmentation | MVS | Matigara | Thiknikata | TW SITE | Pump House | Vested | 74 | 3560 | 110 | 3 | Possessed | Writ of possesion received in favour of PHED
45 | DARJEELING | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME(TSM/012605,SM/12749) | TSM/012605 | SM/12749 | Augmentation | SVS | Naxalbari | Ord Terai Tea Garden | OHR SITE | OHR | Vested | 75 | 2 | 227 | 33 | Possessed | TG LAND Resumption is in process
46 | DARJEELING | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME(TSM/018460,SM/18386) | TSM/018460 | SM/18386 | Augmentation | MVS | Matigara | Pelku | OHR SITE | OHR | Vested | 73 | 2129 | 487 | 26 | Possessed | Writ of possesion received in favour of PHED
47 | DARJEELING | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME(TSM/009292,SM/18637) | TSM/009292 | SM/18637 | Augmentation | MVS | Naxalbari | Shaibhita | TW SITE | Pump House | Vested | 104 | 1917 | 920 | 3 | Possessed | Writ of possession received in favour of PHED
48 | DARJEELING | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME(TSM/009499,SM/10714) | TSM/009499 | SM/10714 | Augmentation | MVS | Phansidewa | Purbba Bansgaon Kismat | TW SITE | Pump House | Private | 95 | 137 | 218 | 3 | Identified | Direct Purchase proposal sent to HQ 2ND LOT
49 | DARJEELING | RUPSING PIPED WATER SUPPLY SCHEME (TSM/010342,SM/11776) | TSM/010342 | SM/11776 | New | SVS | Naxalbari | Rupsing | TW SITE | Pump House | Private | 95 | 0 | 0 | 3 | Not Identified | null
50 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Mohan Laler Chhat | TW SITE | Pump House | Vested | 28 | 0 | 0 | 0 | Not Identified | null
51 | DARJEELING | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III)(TSM/010331,SM/13509) | TSM/010331 | SM/13509 | New | MVS | Kharibari | Salbari | TW SITE | Pump House | Vested | 71 | 1 | 997 | 4 | Identified | TG Land under Fulbari Tea Estate ,IDT pending and actually village Bhogvita,JL NO-44.
52 | DARJEELING | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III)(TSM/010331,SM/13509) | TSM/010331 | SM/13509 | New | MVS | Kharibari | Subalbhita | TW SITE | Pump House | Vested | 66 | 335 | 159 | 3 | Identified | Writ of possession received in fever of PHED,IDT done.
53 | DARJEELING | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009575,SM/10183) | TSM/009575 | SM/10183 | Augmentation | MVS | Naxalbari | Bhimram (CT) | TW SITE | Pump House | Private | 32 | 451 | 2324 | 5 | Identified | Direct Purchase proposal sent to HQ 2nd lot construction started
54 | DARJEELING | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III)(TSM/010331,SM/13509) | TSM/010331 | SM/13509 | New | MVS | Kharibari | Subalbhita | TW SITE | Pump House | Private | 66 | 106 | 138 | 5 | Identified | Direct Purchase proposal sent to HQ 2nd lot
55 | DARJEELING | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009575,SM/10183) | TSM/009575 | SM/10183 | Augmentation | MVS | Naxalbari | Chhota Maniram | TW SITE | Pump House | Vested | 30 | 876 | 1 | 33 | Possessed | Writ of possesion received in favour of PHED construction started
56 | DARJEELING | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME(TSM/009555,SM/18421) | TSM/009555 | SM/18421 | Augmentation | MVS | Kharibari | Shyamdhan (CT) | TW SITE | Pump House | Private | 9 | 676 | 314 | 2 | Identified | Direct Purchase proposal sent to HQ 1st lot, Cabinet Approval received.
57 | DARJEELING | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME(TSM/012602,SM/12748) | TSM/012602 | SM/12748 | Augmentation | SVS | Naxalbari | Trihana Tea Garden | TW SITE | Pump House | Vested | 78 | 3 | 13 | 33 | Possessed | TG LAND Resumption is in process
58 | DARJEELING | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME (TSM/020161,SM/15273) | TSM/020161 | SM/15273 | Augmentation | MVS | Phansidewa | Fulbar | TW SITE | Pump House | Vested | 48 | 2 | 1 | 5 | Identified | TG LAND under Gayaganga TE NOC awaited
59 | DARJEELING | Mandila Jhar Piped Water Supply Scheme.(TSM/003869,SM/18784) | TSM/003869 | SM/18784 | New | SVS | Phansidewa | Mandila Jhar | 2ND TW SITE | Pump House | Private | 101 | 0 | 0 | 3 | Identified | null
60 | DARJEELING | BARA GHARIA PIPED WATER SUPLY SCHEME (TSM/010345,SM/11774) | TSM/010345 | SM/11774 | New | SVS | Matigara | Bara Gharia | OHR SITE | OHR | Vested | 82 | 0 | 0 | 33 | Not Identified | null
61 | DARJEELING | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME (TSM/018448,SM/18385) | TSM/018448 | SM/18385 | Augmentation | MVS | Matigara | Mahishmari | TW SITE | Pump House | Private | 47 | 71 | 32 | 3 | Identified | null
62 | DARJEELING | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME (TSM/018448,SM/18385) | TSM/018448 | SM/18385 | Augmentation | MVS | Matigara | Jadubhitar Chhat | OHR SITE | OHR | Vested | 48 | 1926 | 9 | 33 | Identified | Writ of possesion received in favour of PHED
63 | DARJEELING | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME(TSM/018158,SM/15924) | TSM/018158 | SM/15924 | Augmentation | MVS | Kharibari | Alokjhari | TW SITE | Pump House | Vested | 18 | 1 | 0 | 5 | Identified | identified vested land plot no yet to received from BLLRO
64 | DARJEELING | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME (TSM/010343,SM/11773) | TSM/010343 | SM/11773 | New | MVS | Naxalbari | Dakshin Bagdogra | TW SITE | Pump House | Vested | 99 | 0 | 0 | 3 | Identified | null
65 | DARJEELING | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME (TSM/010343,SM/11773) | TSM/010343 | SM/11773 | New | MVS | Naxalbari | Dakshin Bagdogra | OHR SITE | OHR | Vested | 99 | 0 | 0 | 33 | Identified | TG LAND
66 | DARJEELING | RUPSING PIPED WATER SUPPLY SCHEME (TSM/010342,SM/11776) | TSM/010342 | SM/11776 | New | SVS | Naxalbari | Rupsing | OHR SITE | OHR | Private | 95 | 0 | 0 | 33 | Not Identified | null
67 | DARJEELING | DEBIGANJA PIPED WATER SUPPLY SCHEME (TSM/010335,SM/15925) | TSM/010335 | SM/15925 | New | MVS | Kharibari | Bhajanpur | TW SITE | Pump House | Vested | 33 | 994 | 205 | 3 | Identified | Writ of possession received in fever of PHED
68 | DARJEELING | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III )(TSM/010330,SM/18321) | TSM/010330 | SM/18321 | New | MVS | Phansidewa | Chhota Pathuram | 2ND TW | Pump House | Private | 78 | 1 | 1 | 3 | Identified | Plot no yet to receive from BLLRO
69 | DARJEELING | Augmentation of Hatidoba Piped Water Supply Scheme (TSM/015198,SM/13428) | TSM/015198 | SM/13428 | Augmentation | SVS | Kharibari | Hatidoba | TW SITE | Pump House | Private | 63 | 204 | 234 | 33 | Identified | null
70 | DARJEELING | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010332,SM/15927) | TSM/010332 | SM/15927 | New | MVS | Naxalbari | Kamalpur | TW SITE | Pump House | Vested | 92 | 1 | 1 | 5 | Identified | identified at Kamalpur existing Swajaldhara
71 | DARJEELING | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III )(TSM/010330,SM/18321) | TSM/010330 | SM/18321 | New | MVS | Phansidewa | Narayan | OHR SITE | OHR | Private | 75 | 0 | 425 | 24 | Identified | Direct Purchase proposal sent to HQ 2nd lot
72 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Matigara | Fulbari Pataner Chhat | TW SITE | Pump House | Vested | 19 | 2 | 826 | 3 | Possessed | null
73 | DARJEELING | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme (TSM/015191,SM/13433) | TSM/015191 | SM/13433 | Augmentation | SVS | Phansidewa | Uttar Bansgaon Kismat | TW SITE | Pump House | Private | 96 | 2708 | 2677 | 3 | Identified | Direct purchase proposal to be initiated
74 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Matigara | Kamala Barir Chhat | TW SITE | Pump House | Vested | 8 | 1 | 43 | 3 | Identified | null
75 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Banur Chhat | TW SITE | Pump House | Vested | 19 | 1 | 44 | 3 | Possessed | null
76 | DARJEELING | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME(TSM/009121,SM/10026) | TSM/009121 | SM/10026 | Augmentation | SVS | Naxalbari | Uttar Bagdogra (CT) | TW SITE | Pump House | Private | 93 | 0 | 0 | 3 | Not Identified | null
77 | DARJEELING | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME(TSM/009121,SM/10026) | TSM/009121 | SM/10026 | Augmentation | SVS | Naxalbari | Uttar Bagdogra (CT) | OHR SITE | OHR | Private | 93 | 0 | 0 | 33 | Identified | null
78 | DARJEELING | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010334,SM/16753) | TSM/010334 | SM/16753 | New | MVS | Naxalbari | Siubar | OHR SITE | OHR | Vested | 14 | 322 | 304 | 35 | Possessed | Writ of possession received in favour of PHED
79 | DARJEELING | Mandila Jhar Piped Water Supply Scheme.(TSM/003869,SM/18784) | TSM/003869 | SM/18784 | New | SVS | Phansidewa | Mandila Jhar | OHR SITE | OHR | Private | 101 | 0 | 0 | 33 | Identified | null
80 | DARJEELING | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME(TSM/018158,SM/15924) | TSM/018158 | SM/15924 | Augmentation | MVS | Kharibari | Maynaguri | OHR SITE | OHR | Private | 21 | 134 | 448 | 29 | Identified | Direct Purchase proposal sent to HQ 1ST LOT
81 | DARJEELING | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME.(TSM/010966,SM/14517) | TSM/010966 | SM/14517 | Augmentation | MVS | Matigara | Mathapari | TW SITE | Pump House | Vested | 79 | 220 | 582 | 3 | Identified | noc RECEIVED MATIGRAHAT TEA ESTATE RESUMPTION IS IN PROCESS
82 | DARJEELING | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II )(TSM/010326,SM/15929) | TSM/010326 | SM/15929 | New | MVS | Phansidewa | Purbba Bansgaonchakla | TW SITE | Pump House | Private | 112 | 1 | 1 | 5 | Identified | NOC received from owner Plot noto be Updated
83 | DARJEELING | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME(TSM/009581,SM/10469) | TSM/009581 | SM/10469 | Augmentation | MVS | Matigara | Rangia | TW SITE | Pump House | Vested | 66 | 4253 | 604 | 3 | Possessed | Writ of possesion received in favour of PHED
84 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Naxalbari | Surajbar | TW SITE | Pump House | Vested | 18 | 1 | 307 | 3 | Possessed | null
85 | DARJEELING | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME(TSM/012597,SM/12807) | TSM/012597 | SM/12807 | Augmentation | MVS | Naxalbari | Putimari | TW | Pump House | Private | 100 | 1090 | 105 | 5 | Identified | Joint inspection with BLLRO awaited
86 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Naxalbari | Dhemal | TW SITE | Pump House | Vested | 83 | 1 | 357 | 3 | Possessed | null
87 | DARJEELING | Sona Chandi Piped Water Supply Scheme (TSM/015203,SM/13436) | TSM/015203 | SM/13436 | New | MVS | Kharibari | Sona Chandi | TW SITE | Pump House | Vested | 75 | 2 | 2 | 33 | Identified | TG land under Satish Chandra Tea Estate, Plot no yet to receive from BLLRO,NOC awaited
88 | DARJEELING | Khoklong Piped Water Supply Scheme (TSM/015200,SM/13437) | TSM/015200 | SM/13437 | New | MVS | Matigara | Khoklong | TW SITE | Pump House | Vested | 12 | 0 | 0 | 5 | Identified | null
89 | DARJEELING | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME(TSM/009103,SM/09829) | TSM/009103 | SM/09829 | Augmentation | MVS | Matigara | Kalam | TW SITE | Pump House | Vested | 76 | 2946 | 434 | 3 | Identified | Writ of possesion received in favour of PHED.Work Started
90 | DARJEELING | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010327,SM/13440) | TSM/010327 | SM/13440 | New | MVS | Naxalbari | Manjha Tea Garden | TW SITE | Pump House | Vested | 4 | 52 | 315 | 4 | Possessed | NOC FROM TG RECEIVED RESUMPTION IS IN PROCESS
91 | DARJEELING | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009592,SM/10073) | TSM/009592 | SM/10073 | Augmentation | MVS | Kharibari | Pataram | TW SITE | Pump House | Private | 37 | 930 | 1544 | 3 | Identified | Direct purchase proposal sent to HQ 1st lot, Cabinet Approval received.
92 | DARJEELING | KASHIRAM PIPED WATER SUPPLY SCHEME(TSM/010323,SM/18613) | TSM/010323 | SM/18613 | New | MVS | Phansidewa | Kashiram | 2ND TW SITE | Pump House | Vested | 83 | 1372 | 1366 | 3 | Possessed | Writ of possession received in favour of PHED
93 | DARJEELING | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009575,SM/10183) | TSM/009575 | SM/10183 | Augmentation | MVS | Naxalbari | Dhakna | TW SITE | Pump House | Private | 31 | 126 | 823 | 3 | Identified | Direct Purchase proposal sent to HQ 1ST lot construction started
94 | DARJEELING | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME(TSM/009121,SM/10026) | TSM/009121 | SM/10026 | Augmentation | SVS | Naxalbari | Uttar Bagdogra (CT) | TW SITE | Pump House | Vested | 93 | 5 | 1148 | 3 | Not Identified | DISTRICT BOARD LAND
95 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Naxalbari | Sirsia Tea Garden | TW SITE | Pump House | Vested | 71 | 1 | 42 | 3 | Possessed | NOC received from Belgachi TE
96 | DARJEELING | LOHASING PIPED WATER SUPPLY SCHEME(TSM/010324,SM/15926) | TSM/010324 | SM/15926 | New | MVS | Naxalbari | Lohasing | OHR SITE | Pump House | null | 69 | 0 | 0 | 33 | Not Identified | null
97 | DARJEELING | LOHASING PIPED WATER SUPPLY SCHEME(TSM/010324,SM/15926) | TSM/010324 | SM/15926 | New | MVS | Naxalbari | Lohasing | TW SITE | Pump House | Vested | 69 | 3 | 161 | 3 | Possessed | TG land under Merry view tea company, Resumption is in process
98 | DARJEELING | JOGIBHITA PIPED WATER SUPPLY SCHEME (TSM/010336,SM/15928) | TSM/010336 | SM/15928 | New | MVS | Phansidewa | Lachubhita | OHR SITE | OHR | Vested | 47 | 2 | 0 | 33 | Identified | identified TG land under Kamalpur TE,Plot no yet to received from BLLRO
99 | DARJEELING | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME(TSM/011531,SM/12035) | TSM/011531 | SM/12035 | Augmentation | MVS | Kharibari | Subal | TW SITE | Pump House | Vested | 52 | 20 | 41 | 33 | Identified | IDT Pending
100 | DARJEELING | Pathar Hirhirar Chhat Piped Water Supply Scheme (TSM/015192,SM/13508) | TSM/015192 | SM/13508 | New | MVS | Phansidewa | Pathar Hirhirar Chhat | TW SITE | Pump House | Vested | 26 | 2 | 62 | 3 | Identified | TG Land under Pahargoomia TE,Resumption proposal is in progress
101 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Bharia Danga | TW SITE | Pump House | Vested | 23 | 1 | 11 | 3 | Possessed | null
102 | DARJEELING | JOGIBHITA PIPED WATER SUPPLY SCHEME (TSM/010336,SM/15928) | TSM/010336 | SM/15928 | New | MVS | Phansidewa | Jogibhita | 2ND TW | Pump House | Vested | 46 | 2 | 0 | 3 | Identified | identified TG land under Kamalpur TE,Plot no yet to received from BLLRO
103 | DARJEELING | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME(TSM/009084,SM/09827) | TSM/009084 | SM/09827 | Augmentation | MVS | Phansidewa | Molani | TW SITE | Pump House | Vested | 41 | 1699 | 1103 | 3 | Possessed | Writ of possesion received in favour of PHED
104 | DARJEELING | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010327,SM/13440) | TSM/010327 | SM/13440 | New | MVS | Naxalbari | Manjha Tea Garden | TW SITE | Pump House | Vested | 4 | 52 | 450 | 4 | Possessed | NOC FROM TG RECEIVED RESUMPTION IS IN PROCESS
105 | DARJEELING | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME(TSM/011530,SM/12036) | TSM/011530 | SM/12036 | Augmentation | MVS | Naxalbari | Bhakatram | TW SITE | Pump House | Vested | 48 | 2 | 48 | 3 | Possessed | null
106 | DARJEELING | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME(TSM/009499,SM/10714) | TSM/009499 | SM/10714 | Augmentation | MVS | Phansidewa | Kantibhita | TW SITE | Pump House | Vested | 87 | 460 | 145 | 3 | Possessed | Writ of possesion received in favour of PHED
107 | DARJEELING | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II )(TSM/010326,SM/15929) | TSM/010326 | SM/15929 | New | MVS | Phansidewa | Bansgaonchakla | 2ND TW SITE | Pump House | Vested | 111 | 1373 | 1284 | 3 | Possessed | null
108 | DARJEELING | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME (TSM/020165,SM/15274) | TSM/020165 | SM/15274 | Augmentation | MVS | Phansidewa | Banshgaon | at Pachim Bansgaon Mouza JL109 | Pump House | Private | 110 | 194 | 3058 | 5 | Identified | NOC receievd from Owner , Direct purchase proposal to be initiated
109 | DARJEELING | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II )(TSM/010326,SM/15929) | TSM/010326 | SM/15929 | New | MVS | Phansidewa | Purbba Bansgaonchakla | TW SITE | Pump House | Private | 112 | 1 | 1 | 5 | Identified | NOC received from owner Plot noto be Updated
110 | DARJEELING | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009592,SM/10073) | TSM/009592 | SM/10073 | Augmentation | MVS | Kharibari | Kishordoba | OHR SITE | OHR | Private | 20 | 564 | 1084 | 16 | Identified | Direct purchase proposal sent to HQ 4rth lot.
111 | DARJEELING | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME (TSM/020162,SM/14835) | TSM/020162 | SM/14835 | Augmentation | MVS | Naxalbari | Atal | TW SITE | Pump House | Vested | 53 | 2 | 86 | 5 | Identified | TG land under Atal Tea Estate inside Existing Swajaldhara, NOC received, Joint visit with BLLRO awaited
112 | DARJEELING | Nichitpur Piped Water Supply Scheme (TSM/015201,SM/13438) | TSM/015201 | SM/13438 | New | SVS | Matigara | Nichitpur | TW SITE | Pump House | Vested | 54 | 383 | 665 | 3 | Identified | NICHITPUR TG LAND ACTUAL LAND IN MOUZA DHUKURIA JL 53
113 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Helakadam Chhat | TW SITE | Pump House | Vested | 62 | 1 | 11 | 3 | Possessed | DULUR CHHAT
114 | DARJEELING | Augmentation of Buraganja & Jatru Piped Water Supply Scheme (TSM/015196,SM/13393) | TSM/015196 | SM/13393 | Augmentation | MVS | Kharibari | Jatru | TW SITE | Pump House | Private | 61 | 146 | 395 | 17 | Identified | Direct purchase proposal to be initiated, Construction started
115 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Panaullar Chhat | TW SITE | Pump House | Vested | 17 | 1 | 1 | 3 | Possessed | null
116 | DARJEELING | KASHIRAM PIPED WATER SUPPLY SCHEME(TSM/010323,SM/18613) | TSM/010323 | SM/18613 | New | MVS | Phansidewa | Liusipukuri | 3RD TW | Pump House | Private | 84 | 648 | 1059 | 3 | Identified | Direct purchase proposal to be initiated
117 | DARJEELING | KASHIRAM PIPED WATER SUPPLY SCHEME(TSM/010323,SM/18613) | TSM/010323 | SM/18613 | New | MVS | Phansidewa | Hatiram | OHR SITE | OHR | Vested | 82 | 827 | 312 | 34 | Possessed | Writ of possession received in favour of PHED
118 | DARJEELING | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme (TSM/015191,SM/13433) | TSM/015191 | SM/13433 | Augmentation | SVS | Phansidewa | Uttar Bansgaon Kismat | TW SITE | Pump House | Vested | 96 | 1 | 596 | 3 | Identified | IDT to be initiated
119 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Matigara | Patan | TW SITE | Pump House | Vested | 18 | 2 | 63 | 3 | Possessed | null
120 | DARJEELING | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010333,SM/18614) | TSM/010333 | SM/18614 | New | MVS | Phansidewa | Meherulla | TW SITE | Pump House | Vested | 61 | 1 | 102 | 3 | Identified | IDT to be initiated
121 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Matigara | Gouri | TW SITE | Pump House | Vested | 60 | 2 | 22 | 3 | Possessed | null
122 | DARJEELING | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009588,SM/10108) | TSM/009588 | SM/10108 | Augmentation | MVS | Matigara | Bara Mohansingh (CT) | OHR SITE | OHR | Vested | 71 | 1 | 523 | 23 | Identified | IDT to be initiated
123 | DARJEELING | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010333,SM/18614) | TSM/010333 | SM/18614 | New | MVS | Phansidewa | Abhiram | TW SITE | Pump House | Private | 67 | 0 | 0 | 5 | Not Identified | null
124 | DARJEELING | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME(TSM/012592,SM/12799) | TSM/012592 | SM/12799 | Augmentation | MVS | Matigara | Daknikata (P) | TW SITE | Pump House | Vested | 83 | 1 | 423 | 3 | Identified | null
125 | DARJEELING | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME(TSM/009591,SM/10097) | TSM/009591 | SM/10097 | Augmentation | MVS | Matigara | Tari (CT) | TW SITE | Pump House | Vested | 68 | 7253 | 8 | 3 | Possessed | Writ of possesion received in favour of PHED
126 | DARJEELING | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME(TSM/009292,SM/18637) | TSM/009292 | SM/18637 | Augmentation | MVS | Naxalbari | Rangapani | OHR SITE | OHR | Vested | 105 | 1 | 178 | 31 | Identified | Awaiting writ of possession
127 | DARJEELING | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME(TSM/009103,SM/09829) | TSM/009103 | SM/09829 | Augmentation | MVS | Matigara | Kalam | TW SITE | Pump House | Private | 76 | 2226 | 22 | 3 | Identified | ACTUAL LAND IN MOUZA KAWAKHALI JL 75,NOC received owner, Direct Purchase proposal to be initiated.Construction started
128 | DARJEELING | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME.(TSM/010966,SM/14517) | TSM/010966 | SM/14517 | Augmentation | MVS | Matigara | Mathapari | TW SITE | Pump House | Vested | 79 | 1582 | 199 | 3 | Possessed | Writ of possesion received in favour of PHED
129 | DARJEELING | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme (TSM/015195,SM/13392) | TSM/015195 | SM/13392 | Augmentation | MVS | Kharibari | Bagulahagi | TW SITE | Pump House | Private | 74 | 36 | 528 | 3 | Identified | Direct Purchase Proposal to be initiated
130 | DARJEELING | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme (TSM/015195,SM/13392) | TSM/015195 | SM/13392 | Augmentation | MVS | Kharibari | Bagulahagi | OHR SITE | OHR | Private | 74 | 36 | 484 | 33 | Identified | Direct Purchase Proposal to be initiated
131 | DARJEELING | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009588,SM/10108) | TSM/009588 | SM/10108 | Augmentation | MVS | Matigara | Bara Mohansingh (CT) | TW SITE | Pump House | Vested | 71 | 0 | 0 | 0 | Identified | null
132 | DARJEELING | Augmentation of Arjunmahal Piped Water Supply Scheme (TSM/015194,SM/13395) | TSM/015194 | SM/13395 | Augmentation | SVS | Kharibari | Arjunmahal | TW SITE | Pump House | Private | 73 | 468 | 187 | 15 | Identified | Send to DLPC for 6th Lot
133 | DARJEELING | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME(TSM/009499,SM/10714) | TSM/009499 | SM/10714 | Augmentation | MVS | Phansidewa | Mahipal | TW | Pump House | Vested | 88 | 1409 | 81 | 3 | Possessed | Writ of possesion received in favour of PHED
134 | DARJEELING | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010332,SM/15927) | TSM/010332 | SM/15927 | New | MVS | Naxalbari | Barabhita | TW SITE | Pump House | Vested | 91 | 13 | 15 | 5 | Possessed | Writ of possession received in favour of PHED
135 | DARJEELING | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME (TSM/015582,SM/13467) | TSM/015582 | SM/13467 | Augmentation | MVS | Phansidewa | Budharugaon | TW SITE | Pump House | Vested | 106 | 1 | 0 | 3 | Identified | Identified vested land,plot no yet to received from BLLRO
136 | DARJEELING | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME (TSM/020159,SM/14834) | TSM/020159 | SM/14834 | Augmentation | MVS | Kharibari | Gayen | TW SITE | Pump House | Private | 31 | 1 | 1 | 5 | Identified | Joint visit done, plot noto be received from BLLRO
137 | DARJEELING | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III)(TSM/010325,SM/14150) | TSM/010325 | SM/14150 | New | MVS | Phansidewa | Dhemaler Chhar | TW SITE Z1 | Pump House | Vested | 21 | 0 | 0 | 0 | Identified | null
138 | DARJEELING | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (TSM/010337,SM/12751) | TSM/010337 | SM/12751 | New | MVS | Matigara | Mohorgon Tea Garden | TW SITE | Pump House | Vested | 30 | 4 | 510 | 3 | Possessed | Writ of possesion received in favour of PHED
139 | DARJEELING | Augmentation of Rangali Piped Water Supply Scheme (TSM/015199,SM/13429) | TSM/015199 | SM/13429 | Augmentation | SVS | Kharibari | Rangali | OHR SITE | OHR | Private | 54 | 96 | 184 | 33 | Identified | Direct Purchase proposal to be initiated
140 | DARJEELING | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME(TSM/009466,SM/10724) | TSM/009466 | SM/10724 | Augmentation | SVS | Phansidewa | Madhya Bansgaon | 3RD TW | Pump House | Vested | 98 | 2730 | 2752 | 33 | Possessed | Writ of possesion received in favour of PHED
141 | DARJEELING | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME(TSM/009466,SM/10724) | TSM/009466 | SM/10724 | Augmentation | SVS | Phansidewa | Paschim Bansgaon Kismat | 2ND TW SITE Z1 | Pump House | Private | 99 | 85 | 865 | 3 | Identified | Direct Purchase proposal sent to HQ 3rd lot
142 | DARJEELING | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010332,SM/15927) | TSM/010332 | SM/15927 | New | MVS | Naxalbari | Tarabarir Chhat | TW SITE | Pump House | Private | 85 | 33 | 98 | 30 | Identified | ACTUAL LAND AT DHEMAL JL 83 SINCE IT IS OUTSIDE COVERAGE UNDER 100 HOUSEHOLD CANNOT BE ENTERED HERE
143 | DARJEELING | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME (TSM/010339,SM/13439) | TSM/010339 | SM/13439 | New | MVS | Naxalbari | Dalkajhar Forest | TW SITE | Pump House | Vested | 80 | 0 | 0 | 5 | Identified | Forest land LR Map not available at BLLRO
144 | DARJEELING | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009575,SM/10183) | TSM/009575 | SM/10183 | Augmentation | MVS | Naxalbari | Dayaram | TW SITE | Pump House | Private | 28 | 138 | 139 | 3 | Identified | Direct Purchase proposal sent to HQ 2nd lot construction started
145 | DARJEELING | Pathar Hirhirar Chhat Piped Water Supply Scheme (TSM/015192,SM/13508) | TSM/015192 | SM/13508 | New | MVS | Phansidewa | Pathar Hirhirar Chhat | OHR SITE | OHR | Vested | 26 | 2 | 62 | 33 | Identified | TG Land under Pahargoomia TE,Resumption proposal is in progress
146 | DARJEELING | BARA GHARIA PIPED WATER SUPLY SCHEME (TSM/010345,SM/11774) | TSM/010345 | SM/11774 | New | SVS | Matigara | Bara Gharia | TW SITE | Pump House | Vested | 82 | 0 | 0 | 3 | Not Identified | null
147 | DARJEELING | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME(TSM/009124,SM/10025) | TSM/009124 | SM/10025 | Augmentation | MVS | Phansidewa | Bara Paikpara Arazi | TW SITE | Pump House | Private | 102 | 0 | 0 | 0 | Identified | null
148 | DARJEELING | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME(TSM/011530,SM/12036) | TSM/011530 | SM/12036 | Augmentation | MVS | Naxalbari | Uttam Chanded Chhat | TW SITE | Pump House | Vested | 35 | 2 | 1 | 4 | Possessed | null
149 | DARJEELING | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME(TSM/009124,SM/10025) | TSM/009124 | SM/10025 | Augmentation | MVS | Phansidewa | Bara Paikpara Arazi | OHR SITE | OHR | Private | 102 | 182 | 552 | 33 | Identified | Direct Purchase proposal sent to HQ 3rd lot, Construction work started
150 | DARJEELING | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III )(TSM/010330,SM/18321) | TSM/010330 | SM/18321 | New | MVS | Phansidewa | Chhota Pathuram | OHR SITE | OHR | Private | 78 | 1 | 1 | 33 | Not Identified | Plot no yet to receive from BLLRO
151 | DARJEELING | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II )(TSM/010326,SM/15929) | TSM/010326 | SM/15929 | New | MVS | Phansidewa | Bansgaonchakla | OHR SITE | OHR | Vested | 111 | 1355 | 1099 | 33 | Possessed | null
152 | DARJEELING | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME(TSM/010338,SM/11786) | TSM/010338 | SM/11786 | New | MVS | Matigara | Lalsara Chhat | OHR SITE | OHR | Vested | 62 | 1 | 2 | 15 | Identified | null
153 | DARJEELING | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme(TSM/015190,SM/13391) | TSM/015190 | SM/13391 | Augmentation | MVS | Phansidewa | Sarcargachher Chhat | 2ND TW SITE | Pump House | Vested | 63 | 2 | 87 | 4 | Possessed | HANSQUA TG NOC RECEIVED ,RESUMPTION OF LAND IS IN PROCESS
154 | DARJEELING | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme(TSM/015189,SM/13394) | TSM/015189 | SM/13394 | Augmentation | SVS | Phansidewa | Gangaram Tea Garden | 2ND TW SITE | Pump House | Vested | 31 | 2 | 133 | 3 | Identified | TG land under GANGARAM TG Resumption is in process
155 | DARJEELING | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010328,SM/15908) | TSM/010328 | SM/15908 | New | MVS | Phansidewa | Kuchia | 2ND TW SITE | Pump House | Vested | 34 | 658 | 160 | 5 | Identified | IDT to be initiated
156 | DARJEELING | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME(TSM/009555,SM/18421) | TSM/009555 | SM/18421 | Augmentation | MVS | Kharibari | Balahijhora | TW SITE | Pump House | Private | 16 | 366 | 724 | 3 | Identified | Direct Purchase proposal sent to HQ 2ND lot,
157 | DARJEELING | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010328,SM/15908) | TSM/010328 | SM/15908 | New | MVS | Phansidewa | Haribhita | OHR SITE | OHR | Vested | 42 | 658 | 65 | 34 | Possessed | Writ of possession received in favour of PHED
158 | DARJEELING | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME(TSM/009292,SM/18637) | TSM/009292 | SM/18637 | Augmentation | MVS | Naxalbari | Ranidanga | TW SITE | Pump House | Private | 103 | 1024 | 1075 | 3 | Identified | Direct Purchase Proposal Sent 1st lot
159 | DARJEELING | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME.(TSM/010966,SM/14517) | TSM/010966 | SM/14517 | Augmentation | MVS | Matigara | Mathapari | TW SITE | Pump House | Vested | 79 | 220 | 582 | 3 | Identified | noc RECEIVED MATIGRAHAT TEA ESTATE RESUMPTION IS IN PROCESS
160 | DARJEELING | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME.(TSM/010966,SM/14517) | TSM/010966 | SM/14517 | Augmentation | MVS | Matigara | Mathapari | OHR SITE | OHR | Vested | 79 | 220 | 582 | 33 | Identified | noc RECEIVED MATIGRAHAT TEA ESTATE RESUMPTION IS IN PROCESS
161 | DARJEELING | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III)(TSM/010331,SM/13509) | TSM/010331 | SM/13509 | New | MVS | Kharibari | Deoanbhita | TW SITE | Pump House | Vested | 65 | 1 | 42 | 5 | Identified | IDT Pending.
162 | DARJEELING | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME(TSM/009581,SM/10469) | TSM/009581 | SM/10469 | Augmentation | MVS | Matigara | Rangia | OHR SITE | OHR | Vested | 66 | 4253 | 611 | 33 | Possessed | Writ of possesion received in favour of PHED
163 | DARJEELING | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME(TSM/012597,SM/12807) | TSM/012597 | SM/12807 | Augmentation | MVS | Naxalbari | Lalman (CT) | TW | Pump House | Private | 96 | 239 | 1787 | 3 | Identified | Joint inspection with BLLRO awaited
164 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING(TSM/010030,SM/10824) | TSM/010030 | SM/10824 | New | MVS | Phansidewa | Bhisti | TW SITE | Pump House | Vested | 15 | 1 | 106 | 3 | Possessed | null
165 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Naxalbari | Tarabari | TW SITE | Pump House | Vested | 86 | 1 | 5 | 3 | Possessed | null
166 | DARJEELING | HETMURI PIPED WATER SUPPLY SCHEME (TSM/010346,SM/12750) | TSM/010346 | SM/12750 | New | MVS | Phansidewa | Hetmuri | OHR SITE | OHR | Vested | 85 | 2 | 1 | 33 | Identified | Identified TG land under BHOJNARAYAN TE NOC awaited,PLOT to be updated
167 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Kharibari | Dudha | TW SITE | Pump House | Donated | 68 | 28 | 110 | 3 | Possessed | null
168 | DARJEELING | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III)(TSM/010325,SM/14150) | TSM/010325 | SM/14150 | New | MVS | Phansidewa | Jabarali | OHR SITE Z3 | OHR | Vested | 6 | 2 | 1 | 33 | Identified | TG land under Singijhora TE,Joint visit with BLLRO awaited
169 | DARJEELING | Augmentation of Buraganja & Jatru Piped Water Supply Scheme (TSM/015196,SM/13393) | TSM/015196 | SM/13393 | Augmentation | MVS | Kharibari | Jatru | TW SITE | Pump House | Private | 61 | 201 | 441 | 3 | Identified | Direct purchase proposal to be initiated, Construction started
170 | DARJEELING | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III)(TSM/010325,SM/14150) | TSM/010325 | SM/14150 | New | MVS | Phansidewa | Dhemaler Chhar | OHR ZONE I | OHR | Vested | 21 | 61 | 38 | 33 | Possessed | Writ of possession received in favour of PHED
171 | DARJEELING | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III )(TSM/010330,SM/18321) | TSM/010330 | SM/18321 | New | MVS | Phansidewa | Mahammadbaksa | 2ND TW SITE | Pump House | Private | 74 | 1 | 1159 | 3 | Identified | Plot no & Khatian no to be verified, NOC to be collected from owner
172 | DARJEELING | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III)(TSM/010325,SM/14150) | TSM/010325 | SM/14150 | New | MVS | Phansidewa | Chaupukuria | OHR SITE Z2 NANIJOTE PRIMARY SCHOOL | OHR | Vested | 2 | 1 | 1 | 33 | Identified | Identified at Nanijote Primary School Plot no yet to receive from BLLRO
173 | DARJEELING | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III )(TSM/010330,SM/18321) | TSM/010330 | SM/18321 | New | MVS | Phansidewa | Mahammadbaksa | OHR SITE | OHR | Vested | 74 | 1398 | 602 | 33 | Possessed | Writ of possession received in favour of PHED
174 | DARJEELING | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME(TSM/009122,SM/09830) | TSM/009122 | SM/09830 | Augmentation | MVS | Matigara | Nunu Bairagi | TW | Pump House | Vested | 28 | 1 | 83 | 3 | Identified | TG land under Sukna TE,NOCreceived, Resumption Process to be initiated.
175 | DARJEELING | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010334,SM/16753) | TSM/010334 | SM/16753 | New | MVS | Naxalbari | Dhanibanir Chhat | TW SITE | Pump House | Vested | 62 | 3 | 1 | 5 | Identified | ASHAPUR TG LAND RESUMPTION IS IN PROCESS
176 | DARJEELING | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME (TSM/020167,SM/15269) | TSM/020167 | SM/15269 | Augmentation | MVS | Phansidewa | Tarbandha | TW SITE | Pump House | Vested | 69 | 1 | 686 | 5 | Identified | IDT to be initiated
177 | DARJEELING | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME(TSM/009122,SM/09830) | TSM/009122 | SM/09830 | Augmentation | MVS | Matigara | Udaysing | TW SITE | Pump House | Vested | 51 | 1 | 191 | 3 | Identified | Writ of possesion in favour of PHED received
178 | DARJEELING | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME (TSM/018448,SM/18385) | TSM/018448 | SM/18385 | Augmentation | MVS | Matigara | Mahishmari | TW SITE | Pump House | Vested | 47 | 1 | 165 | 3 | Identified | IDENTIFIED
179 | DARJEELING | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009588,SM/10108) | TSM/009588 | SM/10108 | Augmentation | MVS | Matigara | Bara Mohansingh (CT) | TW SITE | Pump House | Vested | 71 | 0 | 0 | 0 | Identified | null
180 | DARJEELING | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME(TSM/012602,SM/12748) | TSM/012602 | SM/12748 | Augmentation | SVS | Naxalbari | Trihana Tea Garden | TW SITE | Pump House | Vested | 78 | 3 | 24 | 3 | Possessed | TG LAND Resumption is in process
181 | DARJEELING | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME(TSM/011534,SM/12034) | TSM/011534 | SM/12034 | Augmentation | MVS | Phansidewa | Paschim Madati | TW SITE | Pump House | Vested | 100 | 2 | 2 | 5 | Identified | TG LAND plot no yet to receive from BLLRO
182 | DARJEELING | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME(TSM/018158,SM/15924) | TSM/018158 | SM/15924 | Augmentation | MVS | Kharibari | Maynaguri | 2nd TW Site | Pump House | Private | 21 | 12 | 516 | 3 | Identified | Direct Purchase proposal sent to HQ 1ST LOT
183 | DARJEELING | Sona Chandi Piped Water Supply Scheme (TSM/015203,SM/13436) | TSM/015203 | SM/13436 | New | MVS | Kharibari | Sona Chandi | TW SITE | Pump House | Vested | 75 | 2 | 2 | 3 | Identified | TG land under Satish Chandra Tea Estate, Plot no yet to receive from BLLRO,NOC awaited
184 | DARJEELING | Pathar Hirhirar Chhat Piped Water Supply Scheme (TSM/015192,SM/13508) | TSM/015192 | SM/13508 | New | MVS | Phansidewa | Pathar Hirhirar Chhat | TW SITE | Pump House | Vested | 26 | 0 | 0 | 3 | Identified | TG Land
185 | DARJEELING | Khoklong Piped Water Supply Scheme (TSM/015200,SM/13437) | TSM/015200 | SM/13437 | New | MVS | Matigara | Khok Long Chaat | TW SITE | Pump House | Vested | 9 | 0 | 0 | 5 | Identified | null
186 | DARJEELING | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME(TSM/009121,SM/10026) | TSM/009121 | SM/10026 | Augmentation | SVS | Naxalbari | Uttar Bagdogra (CT) | TW SITE | Pump House | Private | 93 | 0 | 0 | 3 | Not Identified | null
187 | DARJEELING | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010334,SM/16753) | TSM/010334 | SM/16753 | New | MVS | Naxalbari | Siubar | TW SITE | Pump House | Private | 14 | 169 | 301 | 3 | Identified | Direct purchase proposal to be initiated, khatian to be confirmed
188 | DARJEELING | Augmentation of Chuchur Muchur Piped Water Supply Scheme (TSM/015197,SM/13427) | TSM/015197 | SM/13427 | Augmentation | MVS | Kharibari | Chuchur Muchur | TW SITE | Pump House | Vested | 72 | 2 | 28 | 20 | Possessed | TG LAND Resumption is in process
189 | DARJEELING | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME(TSM/010338,SM/11786) | TSM/010338 | SM/11786 | New | MVS | Matigara | Dumriguri Chhat | TW SITE | Pump House | Vested | 63 | 1 | 26 | 5 | Identified | null
190 | DARJEELING | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME(TSM/010338,SM/11786) | TSM/010338 | SM/11786 | New | MVS | Matigara | Khaprail | TW SITE | Pump House | Private | 14 | 1552 | 442 | 3 | Identified | null
191 | DARJEELING | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009575,SM/10183) | TSM/009575 | SM/10183 | Augmentation | MVS | Naxalbari | Kamala | TW SITE | Pump House | Private | 22 | 1124 | 590 | 3 | Identified | Direct Purchase proposal sent to HQ 1ST lot construction started
192 | DARJEELING | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME(TSM/010338,SM/11786) | TSM/010338 | SM/11786 | New | MVS | Matigara | Khaprail | OHR SITE | OHR | Donated | 14 | 1075 | 123 | 33 | Identified | null
193 | DARJEELING | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009575,SM/10183) | TSM/009575 | SM/10183 | Augmentation | MVS | Naxalbari | Budhkaran | TW SITE | Pump House | Private | 25 | 977 | 674 | 5 | Identified | Direct Purchase proposal sent to HQ 2nd lot construction started
194 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Naxalbari | Chhota Ganja | tw site | Pump House | Vested | 16 | 1 | 35 | 3 | Possessed | null
195 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Matigara | Galmakhari | TW SITE | Pump House | Vested | 32 | 0 | 0 | 0 | Identified | null
196 | DARJEELING | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II )(TSM/010333,SM/18614) | TSM/010333 | SM/18614 | New | MVS | Phansidewa | Abhiram | TW SITE | Pump House | Vested | 67 | 4 | 461 | 5 | Identified | TG land under Gangaram TG ,Resumption Proposal to be initiated
197 | DARJEELING | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME(TSM/009124,SM/10025) | TSM/009124 | SM/10025 | Augmentation | MVS | Phansidewa | Lahugaon | TW SITE | Pump House | Vested | 104 | 4036 | 3297 | 3 | Possessed | Writ of possesion received in favour of PHED.
198 | DARJEELING | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme(TSM/015190,SM/13391) | TSM/015190 | SM/13391 | Augmentation | MVS | Phansidewa | Baramala | OHR SITE | OHR | Vested | 53 | 2 | 11 | 19 | Possessed | HANSQUA TG NOC RECEIVED ,RESUMPTION OF LAND IS IN PROCESS
199 | DARJEELING | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme(TSM/015189,SM/13394) | TSM/015189 | SM/13394 | Augmentation | SVS | Phansidewa | Gangaram Tea Garden | OHR SITE | OHR | Vested | 31 | 2 | 77 | 33 | Identified | TG land under GANGARAM TG Resumption is in process
200 | DARJEELING | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME (TSM/018448,SM/18385) | TSM/018448 | SM/18385 | Augmentation | MVS | Matigara | Sisabari | TW SITE | Pump House | Vested | 41 | 3843 | 92 | 3 | Identified | Writ of possesion received in favour of PHED
201 | DARJEELING | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009579,SM/10477) | TSM/009579 | SM/10477 | Augmentation | MVS | Kharibari | Gandagal | TW SITE | Pump House | Private | 3 | 812 | 787 | 3 | Identified | Direct Purchase proposal sent to HQ 1 St Lot, Cabinet approval received.
202 | DARJEELING | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME.(TSM/010966,SM/14517) | TSM/010966 | SM/14517 | Augmentation | MVS | Matigara | Baniakhari | at Nimai Mouza jl 57 | OHR | Vested | 55 | 1 | 127 | 16 | Identified | land under demajote Primary SchoolNOC awaited
203 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Naxalbari | Pataram | TW SITE | Pump House | Donated | 17 | 20 | 219 | 3 | Possessed | null
204 | DARJEELING | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III)(TSM/010325,SM/14150) | TSM/010325 | SM/14150 | New | MVS | Phansidewa | Chaupukuria | TW SITE Z2 | Pump House | Vested | 2 | 0 | 0 | 0 | Identified | null
205 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Kharibari | Nazir | TW SITE | Pump House | Vested | 67 | 128 | 531 | 3 | Possessed | null
206 | DARJEELING | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME(TSM/018460,SM/18386) | TSM/018460 | SM/18386 | Augmentation | MVS | Matigara | Pelku | TW SITE | Pump House | Vested | 73 | 2129 | 483 | 7 | Possessed | Writ of possesion received in favour of PHED
207 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Kharibari | Guabari | TW SITE | Pump House | Vested | 69 | 1 | 468 | 3 | Possessed | null
208 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND(TSM/010032,SM/10470) | TSM/010032 | SM/10470 | New | MVS | Kharibari | Badalbhita | TW SITE | Pump House | Vested | 64 | 1 | 479 | 3 | Possessed | null
209 | DARJEELING | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME (TSM/010329,SM/14846) | TSM/010329 | SM/14846 | New | MVS | Kharibari | Chunilal | TW SITE | Pump House | Vested | 12 | 77 | 407 | 3 | Identified | Writ of possession received in fever of PHED,IDT Done.
210 | DARJEELING | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME (TSM/010329,SM/14846) | TSM/010329 | SM/14846 | New | MVS | Kharibari | Chunilal | OHR SITE | OHR | Vested | 12 | 77 | 786 | 24 | Identified | Writ of possession received in fever of PHED,IDT Done.
211 | DARJEELING | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME (TSM/020161,SM/15273) | TSM/020161 | SM/15273 | Augmentation | MVS | Phansidewa | Bhalamanashi | TW SITE | Pump House | Vested | 50 | 0 | 0 | 5 | Identified | TG LAND
212 | DARJEELING | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME(TSM/011534,SM/12034) | TSM/011534 | SM/12034 | Augmentation | MVS | Phansidewa | Purbba Madati | TW SITE | Pump House | Vested | 108 | 0 | 0 | 5 | Identified | TG LAND
213 | DARJEELING | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (TSM/010337,SM/12751) | TSM/010337 | SM/12751 | New | MVS | Matigara | Mohorgon Tea Garden | OHR SITE | Pump House | Vested | 30 | 4 | 537 | 33 | Possessed | Writ of possesion received in favour of PHED
214 | DARJEELING | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME.(TSM/009125,SM/09828) | TSM/009125 | SM/09828 | Augmentation | MVS | Matigara | Jhauguri | TW SITE | Pump House | Private | 22 | 1548 | 196 | 3 | Identified | Direct purchase proposal sent to HQ 2nd lot, Construction started
215 | DARJEELING | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME.(TSM/009125,SM/09828) | TSM/009125 | SM/09828 | Augmentation | MVS | Matigara | Panchakulguri | TW SITE | Pump House | Private | 59 | 2399 | 86 | 3 | Identified | Direct purchase proposal sent to HQ 2nd lot, Construction started
216 | DARJEELING | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME.(TSM/009125,SM/09828) | TSM/009125 | SM/09828 | Augmentation | MVS | Matigara | Panchakulguri | OHR SITE | OHR | Vested | 59 | 3343 | 568 | 33 | Possessed | Writ of possesion received in favour of PHED
217 | DARJEELING | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME(TSM/009579,SM/10477) | TSM/009579 | SM/10477 | Augmentation | MVS | Kharibari | Uttar Ramdhan | TW SITE | Pump House | Private | 2 | 1199 | 454 | 3 | Identified | Direct Purchase proposal sent to HQ 4rt lot.
218 | DARJEELING | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME(TSM/011533,SM/12037) | TSM/011533 | SM/12037 | Augmentation | SVS | Phansidewa | Paschim Madati | TW SITE | Pump House | Vested | 100 | 277 | 5693 | 3 | Identified | TG LAND NOC RECEIVED RESUMPTION YET TO INITIATED
219 | DARJEELING | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME(TSM/009576,SM/10107) | TSM/009576 | SM/10107 | Augmentation | MVS | Matigara | Rajpairi | TW | OHR | Private | 24 | 2478 | 716 | 20 | Identified | Direct purchase proposal sent to HQ 3rd lot
220 | DARJEELING | Augmentation of Hatidoba Piped Water Supply Scheme (TSM/015198,SM/13428) | TSM/015198 | SM/13428 | Augmentation | SVS | Kharibari | Hatidoba | TW SITE | Pump House | Private | 63 | 204 | 221 | 3 | Identified | null
221 | DARJEELING | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME (TSM/020167,SM/15269) | TSM/020167 | SM/15269 | Augmentation | MVS | Phansidewa | Nirmmal | TW SITE | Pump House | Private | 73 | 1229 | 849 | 5 | Identified | Direct Purchase proposal to be initiated
222 | DARJEELING | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME(TSM/009466,SM/10724) | TSM/009466 | SM/10724 | Augmentation | SVS | Phansidewa | Paschim Bansgaon Kismat | OHR Z1 | OHR | Vested | 99 | 1264 | 984 | 33 | Possessed | Writ of possesion received in favour of PHED
223 | DARJEELING | Augmentation of Rangali Piped Water Supply Scheme (TSM/015199,SM/13429) | TSM/015199 | SM/13429 | Augmentation | SVS | Kharibari | Rangali | TW SITE | Pump House | Private | 54 | 545 | 333 | 3 | Identified | Direct Purchase proposal to be initiated
224 | DARJEELING | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME (TSM/020169,SM/15270) | TSM/020169 | SM/15270 | Augmentation | MVS | Naxalbari | Mahasing | TW SITE | Pump House | Private | 52 | 91 | 362 | 5 | Identified | Joint visit with BLLRO awaited