## A3- Land Parcel Status
A3- Land Parcel Status
SL No | District | Scheme Name | Scheme TSM Code | Scheme SM Code | Scheme Category | Scheme Coverage Type | Block | Village | Location | Purpose | Type | J.L. No. | Khatian No. | Plot No. | Area (in decimal) | Status | Remarks
1 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Ranabindul Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012760,SM/12462) | TSM/012760 | SM/12462 | New | SVS | Bansihari | Ranabindul | null | Pump House | Private | 131 | 114 | 198 | 2 | Identified | null
2 | DAKSHIN DINAJPUR | MAHADIPUR Piped Water Supply Scheme(TSM/014998,SM/16251) | TSM/014998 | SM/16251 | New | MVS | Balurghat | Mahadipur | Near Chingishpur Bridge | OHR | Vested | 281 | 1 | 765 | 33 | Possessed | For Head work site of PWSS
3 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bodra Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012927,SM/12853) | TSM/012927 | SM/12853 | New | SVS | Kumarganj | Bodra | null | Pump House | Private | 123 | 23 | 228 | 2 | Identified | null
4 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Harirampur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012717,SM/12612) | TSM/012717 | SM/12612 | New | SVS | Balurghat | Harirampur | null | Pump House | Private | 212 | 274 | 102 | 2 | Identified | null
5 | DAKSHIN DINAJPUR | AMAI PIPED WATER SUPPLY SCHEME(TSM/011883,SM/11963) | TSM/011883 | SM/11963 | New | MVS | Bansihari | Amai | null | OHR | Donated | 265 | 615 | 514 | 31 | Possessed | null
6 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Maulai Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012856,SM/12941) | TSM/012856 | SM/12941 | New | SVS | Kushmundi | Maulai | null | Pump House | Private | 172 | 122 | 353 | 2 | Identified | null
7 | DAKSHIN DINAJPUR | Source Augmentation of Dangram Piped Water Supply Scheme under Balurghat Division, PHE Dte.(TSM/016072,SM/16562) | TSM/016072 | SM/16562 | Augmentation | MVS | Harirampur | Bora | null | Pump House | Donated | 61 | 293 | 96 | 10 | Possessed | null
8 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dharail Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012724,SM/12615) | TSM/012724 | SM/12615 | New | SVS | Balurghat | Dharail | null | Pump House | Private | 68 | 62 | 664 | 2 | Identified | null
9 | DAKSHIN DINAJPUR | Augmentation of Ground Water Based Kamarpara Piped Water Supply Scheme(TSM/014570,SM/18631) | TSM/014570 | SM/18631 | Augmentation | MVS | Balurghat | Kutubpur | null | OHR | Donated | 254 | 145 | 67 | 22 | Possessed | null
10 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Cherapara Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012880,SM/12920) | TSM/012880 | SM/12920 | New | SVS | Kushmundi | Cherapara | null | Pump House | Private | 43 | 261 | 300 | 2 | Identified | null
11 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kashimpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012891,SM/12923) | TSM/012891 | SM/12923 | New | SVS | Kushmundi | Kashimpur | null | Pump House | Private | 46 | 359 | 379 | 2 | Identified | null
12 | DAKSHIN DINAJPUR | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Ranipur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/013380,SM/12926) | TSM/013380 | SM/12926 | New | SVS | Kushmundi | Ranipur | null | Pump House | Private | 42 | 883 | 69 | 2 | Identified | null
13 | DAKSHIN DINAJPUR | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME(TSM/017436,SM/18434) | TSM/017436 | SM/18434 | New | MVS | Kumarganj | Tazpur | null | OHR | Donated | 186 | 94 | 18 | 31 | Possessed | Registration of land in favour of PHED yet to do after start of work as requested by concern landowner. NOC has taken from the land owner approved by VWSC and Block administration.
14 | DAKSHIN DINAJPUR | Baragram PWSS in Banshihari Block in Dakshin Dinajpur(TSM/011705,SM/11670) | TSM/011705 | SM/11670 | New | MVS | Bansihari | Baragram | near Baragram | OHR | Vested | 129 | 1 | 2069 | 33 | Possessed | null
15 | DAKSHIN DINAJPUR | TRIKUL Piped Water Supply Scheme(TSM/014305,SM/12817) | TSM/014305 | SM/12817 | New | MVS | Balurghat | Trikul | null | OHR | Donated | 75 | 246 | 383 | 33 | Possessed | null
16 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Taksail Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012672,SM/12553) | TSM/012672 | SM/12553 | New | SVS | Balurghat | Taksail | null | Pump House | Private | 19 | 68 | 665 | 2 | Identified | null
17 | DAKSHIN DINAJPUR | MARGRAM Piped Water Supply Scheme(TSM/015069,SM/16269) | TSM/015069 | SM/16269 | New | MVS | Balurghat | Chhiail | null | OHR | Private | 241 | 256 | 248 | 3 | Possessed | null
18 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uttar Mulahati Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/013026,SM/12962) | TSM/013026 | SM/12962 | New | SVS | Harirampur | Uttar Mulahati | near Uttar Mulahati | Pump House | Vested | 54 | 1 | 118 | 5 | Identified | null
19 | DAKSHIN DINAJPUR | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur.(TSM/013190,SM/14104) | TSM/013190 | SM/14104 | New | MVS | Kushmundi | Titihi | null | OHR | Donated | 15 | 246 | 244 | 33 | Possessed | null
20 | DAKSHIN DINAJPUR | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Barail Mouza of Kushmandii Block in the District of Dakshin Dinajpur.(TSM/013384,SM/12929) | TSM/013384 | SM/12929 | New | SVS | Kushmundi | Barail | null | Pump House | Donated | 59 | 458 | 657 | 2 | Identified | null
21 | DAKSHIN DINAJPUR | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block(TSM/005981,SM/07089) | TSM/005981 | SM/07089 | Retrofitting | MVS | Harirampur | Bagichapur | null | OHR | Private | 17 | 102 | 17 | 2 | Possessed | null
22 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chakismail Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012686,SM/12559) | TSM/012686 | SM/12559 | New | SVS | Balurghat | Chakismail | null | Pump House | Private | 283 | 97 | 236 | 2 | Identified | null
23 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Itakhor Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012899,SM/12944) | TSM/012899 | SM/12944 | New | SVS | Harirampur | Itakhor | null | OHR | Vested | 25 | 1 | 293 | 2 | Identified | null
24 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Tursail Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012721,SM/12614) | TSM/012721 | SM/12614 | New | SVS | Balurghat | Tursail | null | Pump House | Private | 247 | 145 | 245 | 2 | Identified | null
25 | DAKSHIN DINAJPUR | DHULATAIR Piped Water Supply Scheme(TSM/014386,SM/12819) | TSM/014386 | SM/12819 | New | MVS | Balurghat | Dhulatair | null | OHR | Donated | 29 | 269 | 32 | 34 | Possessed | null
26 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Pasoya Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013104,SM/12973) | TSM/013104 | SM/12973 | New | SVS | Kumarganj | Pasoya | null | Pump House | Private | 201 | 48 | 1 | 2 | Identified | null
27 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sankarpur Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012777,SM/12474) | TSM/012777 | SM/12474 | New | SVS | Bansihari | Sankarpur | null | Pump House | Private | 160 | 154 | 167 | 2 | Identified | null
28 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Radhakrishnapur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013107,SM/12974) | TSM/013107 | SM/12974 | New | SVS | Kumarganj | Radhakrishnpur | null | Pump House | Private | 129 | 98 | 165 | 2 | Identified | null
29 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bamnahar Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012706,SM/12609) | TSM/012706 | SM/12609 | New | SVS | Balurghat | Bamnahar | null | Pump House | Private | 221 | 112 | 196 | 2 | Identified | null
30 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Baghna Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012879,SM/12919) | TSM/012879 | SM/12919 | New | SVS | Kushmundi | Baghna | null | Pump House | Private | 52 | 186 | 29 | 2 | Identified | null
31 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Barakhail Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012616,SM/12537) | TSM/012616 | SM/12537 | New | SVS | Balurghat | Barakhail | null | Pump House | Donated | 257 | 345 | 98 | 2 | Identified | null
32 | DAKSHIN DINAJPUR | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur.(TSM/012004,SM/11950) | TSM/012004 | SM/11950 | New | MVS | Harirampur | Bagbari | null | OHR | Donated | 37 | 2174 | 2102 | 33 | Possessed | null
33 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kutubpur Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012640,SM/12540) | TSM/012640 | SM/12540 | New | SVS | Balurghat | Kutubpur | null | Pump House | Vested | 254 | 1 | 192 | 2 | Identified | null
34 | DAKSHIN DINAJPUR | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur.(TSM/011751,SM/11951) | TSM/011751 | SM/11951 | New | MVS | Bansihari | Kelna | null | OHR | Donated | 120 | 120 | 473 | 34 | Possessed | null
35 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Satais Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012702,SM/12606) | TSM/012702 | SM/12606 | New | SVS | Balurghat | Satais | null | Pump House | Private | 245 | 3 | 59 | 2 | Identified | null
36 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Satihar Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012703,SM/12607) | TSM/012703 | SM/12607 | New | SVS | Balurghat | Satihar | null | Pump House | Private | 159 | 217 | 19 | 2 | Identified | null
37 | DAKSHIN DINAJPUR | DASUL Piped Water Supply Scheme(TSM/014362,SM/12810) | TSM/014362 | SM/12810 | New | MVS | Balurghat | Dasul | null | OHR | Donated | 194 | 231 | 1116 | 33 | Possessed | null
38 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uddhabpur (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012910,SM/12952) | TSM/012910 | SM/12952 | New | SVS | Harirampur | Uddhabpur (I) | null | Pump House | Private | 189 | 182 | 635 | 2 | Identified | null
39 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Matizapur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012932,SM/12858) | TSM/012932 | SM/12858 | New | SVS | Kumarganj | Matizapur | null | Pump House | Private | 141 | 131 | 127 | 2 | Identified | null
40 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dhadarang Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012894,SM/12931) | TSM/012894 | SM/12931 | New | SVS | Kushmundi | Dhadarang | null | Pump House | Private | 55 | 60 | 73 | 2 | Identified | null
41 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Basudebpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012855,SM/12940) | TSM/012855 | SM/12940 | New | SVS | Kushmundi | Basudebpur | null | Pump House | Private | 171 | 199 | 231 | 2 | Identified | null
42 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Krishna Charan Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012914,SM/12955) | TSM/012914 | SM/12955 | New | SVS | Harirampur | Krishna Charan | null | Pump House | Vested | 86 | 1 | 110 | 2 | Identified | null
43 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dahuakuri Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012756,SM/12460) | TSM/012756 | SM/12460 | New | SVS | Bansihari | Dahuakuri | null | Pump House | Private | 122 | 267 | 405 | 2 | Identified | null
44 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bhikanpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012832,SM/13192) | TSM/012832 | SM/13192 | New | SVS | Kushmundi | Bhikanpur | null | Pump House | Private | 101 | 350 | 234 | 2 | Identified | null
45 | DAKSHIN DINAJPUR | Augmentation of Dhiltail Piped Water Supply Scheme in Banshihari Block of Dakshin Dinajpur District.(TSM/015236,SM/13829) | TSM/015236 | SM/13829 | Augmentation | MVS | Bansihari | Dhiltail | null | OHR | Donated | 247 | 67 | 95 | 16 | Possessed | null
46 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jotgora Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012900,SM/12945) | TSM/012900 | SM/12945 | New | SVS | Harirampur | Jotgora | null | Pump House | Vested | 102 | 1 | 141 | 2 | Identified | null
47 | DAKSHIN DINAJPUR | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME(TSM/017436,SM/18434) | TSM/017436 | SM/18434 | New | MVS | Kumarganj | Paik Jhara | null | OHR | Donated | 113 | 74 | 49 | 33 | Possessed | Registration of land in favour of PHED yet to do after start of work as requested by concern landowner. NOC has taken from the land owner approved by VWSC and Block administration.
48 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Charla Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012904,SM/12948) | TSM/012904 | SM/12948 | New | SVS | Harirampur | Charla | null | Pump House | Private | 104 | 96 | 104 | 2 | Identified | null
49 | DAKSHIN DINAJPUR | GURKHAIR Piped Water Supply Scheme at Harirampur Block(TSM/012011,SM/12050) | TSM/012011 | SM/12050 | New | MVS | Harirampur | Kakihar | null | OHR | Donated | 99 | 272 | 271 | 33 | Possessed | null
50 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jamirail Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012866,SM/12913) | TSM/012866 | SM/12913 | New | SVS | Kushmundi | Jamirail | null | Pump House | Private | 6 | 225 | 253 | 2 | Identified | null
51 | DAKSHIN DINAJPUR | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME(TSM/017436,SM/18434) | TSM/017436 | SM/18434 | New | MVS | Kumarganj | Udaypur | null | OHR | Donated | 105 | 144 | 138 | 33 | Possessed | Registration of land in favour of PHED yet to do after start of work as requested by concern landowner. NOC has taken from the land owner approved by VWSC and Block administration.
52 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sardarpur Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012761,SM/12463) | TSM/012761 | SM/12463 | New | SVS | Bansihari | Sardarpur | null | Pump House | Private | 130 | 338 | 550 | 2 | Identified | null
53 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Palashdanga Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012730,SM/12618) | TSM/012730 | SM/12618 | New | SVS | Balurghat | Palashdanga | null | Pump House | Private | 70 | 48 | 82 | 2 | Identified | null
54 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nikharpara Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012902,SM/12946) | TSM/012902 | SM/12946 | New | SVS | Harirampur | Nikharpara | null | Pump House | Vested | 144 | 1 | 76 | 2 | Identified | null
55 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mahabari Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012787,SM/12478) | TSM/012787 | SM/12478 | New | SVS | Bansihari | Mahabari | null | Pump House | Private | 190 | 112 | 218 | 2 | Identified | null
56 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Baramahar Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012903,SM/12947) | TSM/012903 | SM/12947 | New | SVS | Harirampur | Baramahar | null | Pump House | Vested | 2 | 1 | 145 | 2 | Identified | null
57 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jaherpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012885,SM/12921) | TSM/012885 | SM/12921 | New | SVS | Kushmundi | Jaherpur | null | Pump House | Private | 34 | 455 | 10 | 2 | Identified | null
58 | DAKSHIN DINAJPUR | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME(TSM/017436,SM/18434) | TSM/017436 | SM/18434 | New | MVS | Kumarganj | Azadpur | null | OHR | Donated | 4 | 192 | 9 | 33 | Possessed | Registration of land in favour of PHED yet to do after start of work as requested by concern landowner. NOC has taken from the land owner approved by VWSC and Block administration.
59 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uttar Srirampur Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012767,SM/12468) | TSM/012767 | SM/12468 | New | SVS | Bansihari | Uttar Srirampur | null | Pump House | Private | 243 | 477 | 117 | 2 | Identified | null
60 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kalancha Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012890,SM/12922) | TSM/012890 | SM/12922 | New | SVS | Kushmundi | Kalancha | null | Pump House | Private | 26 | 234 | 139 | 2 | Identified | null
61 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Kharika Dangi | null | Pump House | Vested | 254 | 1 | 487 | 2 | Identified | null
62 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Raghunathpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012835,SM/13194) | TSM/012835 | SM/13194 | New | SVS | Kushmundi | Raghunathpur | null | Pump House | Private | 110 | 221 | 247 | 2 | Identified | null
63 | DAKSHIN DINAJPUR | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur.(TSM/014408,SM/12703) | TSM/014408 | SM/12703 | New | MVS | Balurghat | Atair | Near Atair | OHR | Vested | 152 | 1 | 416 | 5 | Possessed | null
64 | DAKSHIN DINAJPUR | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur.(TSM/014478,SM/12705) | TSM/014478 | SM/12705 | New | MVS | Balurghat | Barakali | null | OHR | Private | 216 | 240 | 49 | 34 | Possessed | null
65 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Saiyadpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013177,SM/12978) | TSM/013177 | SM/12978 | New | SVS | Kumarganj | Saiyadpur | null | Pump House | Private | 153 | 121 | 256 | 2 | Identified | null
66 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Tulsipur Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012643,SM/12542) | TSM/012643 | SM/12542 | New | SVS | Balurghat | Tulsipur | null | Pump House | Vested | 255 | 1 | 71 | 2 | Identified | null
67 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nij Raghunathpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012873,SM/12915) | TSM/012873 | SM/12915 | New | SVS | Kushmundi | Nij Raghunathpur | null | Pump House | Private | 2 | 141 | 108 | 2 | Identified | null
68 | DAKSHIN DINAJPUR | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur.(TSM/013060,SM/14101) | TSM/013060 | SM/14101 | New | MVS | Kushmundi | Kharikadighi | null | OHR | Donated | 32 | 186 | 169 | 33 | Possessed | null
69 | DAKSHIN DINAJPUR | PANCHHATA Piped Water Supply Scheme at Kushmundi Block(TSM/013076,SM/12055) | TSM/013076 | SM/12055 | New | MVS | Kushmundi | Ramchandrapur | null | OHR | Vested | 218 | 1 | 225 | 33 | Possessed | null
70 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak Sirdhar Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012687,SM/12560) | TSM/012687 | SM/12560 | New | SVS | Balurghat | Chak Sridhar | null | Pump House | Private | 143 | 148 | 256 | 2 | Identified | null
71 | DAKSHIN DINAJPUR | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur.(TSM/013122,SM/14102) | TSM/013122 | SM/14102 | New | MVS | Kushmundi | Maligaon | null | OHR | Donated | 200 | 407 | 443 | 33 | Possessed | null
72 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Purbba Maheshpur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012670,SM/12552) | TSM/012670 | SM/12552 | New | SVS | Balurghat | Purbba Maheshpur | null | Pump House | Private | 33 | 32 | 284 | 2 | Identified | null
73 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Baje Chahatpur (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012907,SM/12950) | TSM/012907 | SM/12950 | New | SVS | Harirampur | Baje Chahatpur (I) | null | Pump House | Private | 200 | 198 | 631 | 2 | Identified | null
74 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Asrafpur Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012911,SM/12953) | TSM/012911 | SM/12953 | New | SVS | Harirampur | Asrafpur | null | Pump House | Private | 94 | 645 | 65 | 2 | Identified | null
75 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nadipur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013185,SM/12981) | TSM/013185 | SM/12981 | New | SVS | Kumarganj | Nadipur | null | Pump House | Private | 176 | 121 | 456 | 2 | Identified | null
76 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jugati Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012895,SM/12932) | TSM/012895 | SM/12932 | New | SVS | Kushmundi | Jugati | null | Pump House | Private | 19 | 176 | 103 | 2 | Identified | null
77 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Langal Bhanga Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012896,SM/12933) | TSM/012896 | SM/12933 | New | SVS | Kushmundi | Langal Bhanga | null | Pump House | Private | 67 | 415 | 37 | 2 | Identified | null
78 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Kumarganj, Kushmandi & Tapan Block in the District of Dakshin Dinajpur.(TSM/010107,SM/10646) | TSM/010107 | SM/10646 | New | MVS | Kumarganj | Paik Jhara | null | Pump House | Donated | 113 | 123 | 1478 | 2 | Identified | null
79 | DAKSHIN DINAJPUR | DILKUNTHI Piped Water Supply Scheme at Bansihari Block(TSM/013332,SM/12063) | TSM/013332 | SM/12063 | New | MVS | Bansihari | Dilkhanthi | null | OHR | Donated | 269 | 185 | 142 | 64 | Possessed | null
80 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Ojantor Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012766,SM/12467) | TSM/012766 | SM/12467 | New | SVS | Bansihari | Ojantor | null | Pump House | Private | 232 | 546 | 115 | 2 | Identified | null
81 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak-Behetair Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012929,SM/12855) | TSM/012929 | SM/12855 | New | SVS | Kumarganj | Chak-Behatair | null | Pump House | Private | 185 | 114 | 208 | 2 | Identified | null
82 | DAKSHIN DINAJPUR | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block(TSM/013134,SM/12060) | TSM/013134 | SM/12060 | New | MVS | Kushmundi | Saraihat Bajedonor | null | OHR | Donated | 7 | 5 | 160 | 33 | Possessed | null
83 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jagannathpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012931,SM/12857) | TSM/012931 | SM/12857 | New | SVS | Kumarganj | Jagannathpur | null | Pump House | Private | 191 | 425 | 485 | 2 | Identified | null
84 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mominpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012933,SM/12859) | TSM/012933 | SM/12859 | New | SVS | Kumarganj | Mominpur | null | Pump House | Private | 140 | 267 | 79 | 2 | Identified | null
85 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mastahar Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012872,SM/12914) | TSM/012872 | SM/12914 | New | SVS | Kushmundi | Mastahar | null | Pump House | Private | 3 | 352 | 18 | 2 | Identified | null
86 | DAKSHIN DINAJPUR | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR.(TSM/013547,SM/12241) | TSM/013547 | SM/12241 | New | MVS | Balurghat | Durllabhpur | null | OHR | Donated | 58 | 269 | 32 | 33 | Possessed | null
87 | DAKSHIN DINAJPUR | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur.(TSM/013113,SM/14103) | TSM/013113 | SM/14103 | New | MVS | Kushmundi | Dhakdhol | null | OHR | Donated | 115 | 1268 | 718 | 33 | Possessed | null
88 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Krishnagar Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013069,SM/12971) | TSM/013069 | SM/12971 | New | SVS | Kumarganj | Krisnagar | null | Pump House | Private | 213 | 156 | 651 | 2 | Identified | null
89 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Debrabari Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012692,SM/12601) | TSM/012692 | SM/12601 | New | SVS | Balurghat | Debrabari | null | Pump House | Private | 169 | 162 | 149 | 2 | Identified | null
90 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bishnupur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012925,SM/12852) | TSM/012925 | SM/12852 | New | SVS | Kumarganj | Bishnupur | null | Pump House | Private | 142 | 132 | 336 | 2 | Identified | null
91 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak Bhagaban Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012928,SM/12854) | TSM/012928 | SM/12854 | New | SVS | Kumarganj | Chak Bhagaban | null | Pump House | Private | 145 | 444 | 17 | 2 | Identified | null
92 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Anarpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013043,SM/12964) | TSM/013043 | SM/12964 | New | SVS | Kumarganj | Anarpur | null | Pump House | Private | 128 | 146 | 14 | 2 | Identified | null
93 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gayespur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012930,SM/12856) | TSM/012930 | SM/12856 | New | SVS | Kumarganj | Gayespur | gayeshpur ssk | Pump House | Donated | 144 | 1 | 1234 | 2 | Identified | null
94 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chausha Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013183,SM/12980) | TSM/013183 | SM/12980 | New | SVS | Kumarganj | Chausha | Near Chausha FP School | Pump House | Donated | 165 | 598 | 97 | 2 | Identified | null
95 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Piakhan Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012755,SM/12459) | TSM/012755 | SM/12459 | New | SVS | Balurghat | Piakhan | null | Pump House | Vested | 205 | 1 | 234 | 2 | Identified | null
96 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nituttarpara Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012874,SM/12916) | TSM/012874 | SM/12916 | New | SVS | Kushmundi | Nituttarpara | null | Pump House | Private | 82 | 737 | 601 | 2 | Identified | null
97 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Rankhanpara Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012776,SM/12473) | TSM/012776 | SM/12473 | New | SVS | Bansihari | Rankhanpara | null | Pump House | Private | 158 | 55 | 151 | 2 | Identified | null
98 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chandipur Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012645,SM/12543) | TSM/012645 | SM/12543 | New | SVS | Balurghat | Chandipur | null | Pump House | Private | 40 | 235 | 89 | 2 | Identified | null
99 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bayrapara Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012938,SM/12862) | TSM/012938 | SM/12862 | New | SVS | Kumarganj | Bayrapara | null | Pump House | Private | 74 | 306 | 192 | 2 | Identified | null
100 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chingra Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012634,SM/12539) | TSM/012634 | SM/12539 | New | SVS | Balurghat | Chingra | null | Pump House | Vested | 251 | 1 | 244 | 2 | Identified | null
101 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kodla Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/013402,SM/12605) | TSM/013402 | SM/12605 | New | SVS | Balurghat | Kodla | null | Pump House | Private | 259 | 9 | 176 | 2 | Identified | null
102 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kamdebpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012945,SM/12868) | TSM/012945 | SM/12868 | New | SVS | Kumarganj | Kamdebpur | null | Pump House | Private | 9 | 6 | 122 | 2 | Identified | null
103 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gunjarpur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012714,SM/12611) | TSM/012714 | SM/12611 | New | SVS | Balurghat | Gunjarpur | null | Pump House | Vested | 250 | 1 | 274 | 2 | Identified | null
104 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Phulat (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012908,SM/12951) | TSM/012908 | SM/12951 | New | SVS | Harirampur | Phulat (I) | null | Pump House | Private | 182 | 304 | 294 | 2 | Identified | null
105 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Kasitara | null | Pump House | Vested | 249 | 1 | 565 | 2 | Identified | null
106 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chandradaula Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012678,SM/12555) | TSM/012678 | SM/12555 | New | SVS | Balurghat | Chandradaula | null | Pump House | Private | 104 | 221 | 359 | 2 | Identified | null
107 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sarenbari Mouza of Hili Block in the District of Dakshin Dinajpur.(TSM/013027,SM/12963) | TSM/013027 | SM/12963 | New | SVS | Hilli | Sarenbari | null | Pump House | Private | 58 | 56 | 914 | 2 | Identified | null
108 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Chechrakuri | null | Pump House | Vested | 261 | 1 | 216 | 2 | Identified | null
109 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak Khetab Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012684,SM/12558) | TSM/012684 | SM/12558 | New | SVS | Balurghat | Chak Khetab | null | Pump House | Private | 282 | 241 | 142 | 2 | Identified | null
110 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Chenchoir | null | Pump House | Vested | 263 | 1 | 254 | 2 | Identified | null
111 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Birampur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012893,SM/12930) | TSM/012893 | SM/12930 | New | SVS | Kushmundi | Birampur | null | Pump House | Private | 66 | 122 | 188 | 2 | Identified | null
112 | DAKSHIN DINAJPUR | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District.(TSM/010064,SM/10471) | TSM/010064 | SM/10471 | Augmentation | MVS | Balurghat | Patiram | Patiram Chowrangi | OHR | Donated | 187 | 256 | 43 | 16 | Possessed | null
113 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nayapara Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012897,SM/12934) | TSM/012897 | SM/12934 | New | SVS | Kushmundi | Nayapara | null | Pump House | Private | 57 | 127 | 71 | 2 | Identified | null
114 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak-Bansi Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013048,SM/12966) | TSM/013048 | SM/12966 | New | SVS | Kumarganj | Chak-Bansi | null | Pump House | Private | 204 | 318 | 141 | 2 | Identified | null
115 | DAKSHIN DINAJPUR | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I)(TSM/009226,SM/10024) | TSM/009226 | SM/10024 | Retrofitting | MVS | Gangarampur | Durgaramchak | Near Durgaram Chowk | OHR | Vested | 194 | 1 | 120 | 18 | Possessed | null
116 | DAKSHIN DINAJPUR | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME(TSM/012731,SM/15483) | TSM/012731 | SM/15483 | New | MVS | Harirampur | Baje Banagram (I) | null | OHR | Donated | 98 | 163 | 795 | 33 | Possessed | null
117 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uttar Shibrampur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012675,SM/12554) | TSM/012675 | SM/12554 | New | SVS | Balurghat | Uttar Sibrampur | null | Pump House | Private | 16 | 184 | 189 | 2 | Identified | null
118 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chhota Faizullapur Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012781,SM/12477) | TSM/012781 | SM/12477 | New | SVS | Bansihari | Chhota Faizullapur | null | Pump House | Private | 183 | 318 | 92 | 2 | Identified | null
119 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Samaspur Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012788,SM/12479) | TSM/012788 | SM/12479 | New | SVS | Bansihari | Samaspur | null | Pump House | Private | 187 | 172 | 129 | 2 | Identified | null
120 | DAKSHIN DINAJPUR | Restoration of Pipe Line in for Retrofitting of FHTC under Jaharpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM).(TSM/015879,SM/15202) | TSM/015879 | SM/15202 | Augmentation | MVS | Bansihari | Suripukur | null | Pump House | Donated | 220 | 456 | 765 | 2 | Possessed | null
121 | DAKSHIN DINAJPUR | BALDU Piped Water Supply Scheme at Harirampur Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur.(TSM/013519,SM/14105) | TSM/013519 | SM/14105 | New | MVS | Harirampur | Pinglu (I) | null | OHR | Donated | 195 | 348 | 316 | 33 | Possessed | null
122 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Shibpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012946,SM/12869) | TSM/012946 | SM/12869 | New | SVS | Kumarganj | Shibpur | null | Pump House | Private | 3 | 141 | 235 | 2 | Identified | null
123 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Vstair Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012790,SM/12480) | TSM/012790 | SM/12480 | New | SVS | Bansihari | Vstair | null | Pump House | Private | 268 | 292 | 88 | 2 | Identified | null
124 | DAKSHIN DINAJPUR | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sindur Muchhi Mouza of Kushmandii Block in the District of Dakshin Dinajpur.(TSM/013383,SM/12928) | TSM/013383 | SM/12928 | New | SVS | Kushmundi | Sindur Muchhi | null | Pump House | Private | 28 | 1 | 378 | 2 | Identified | null
125 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Barajhara Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012762,SM/12464) | TSM/012762 | SM/12464 | New | SVS | Bansihari | Barajhara | null | Pump House | Private | 234 | 257 | 141 | 2 | Identified | null
126 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gerul Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012770,SM/12469) | TSM/012770 | SM/12469 | New | SVS | Bansihari | Gerul | null | Pump House | Private | 169 | 291 | 0 | 2 | Identified | null
127 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Saidpur Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012651,SM/12546) | TSM/012651 | SM/12546 | New | SVS | Balurghat | Saidpur | null | Pump House | Private | 45 | 55 | 884 | 2 | Identified | null
128 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bikuch Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012653,SM/12547) | TSM/012653 | SM/12547 | New | SVS | Balurghat | Bikuch | null | Pump House | Private | 21 | 350 | 169 | 2 | Identified | null
129 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jotbasanta Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012912,SM/12954) | TSM/012912 | SM/12954 | New | SVS | Harirampur | Jotbasanta | null | Pump House | Private | 76 | 6 | 625 | 2 | Identified | null
130 | DAKSHIN DINAJPUR | PANCHHATA Piped Water Supply Scheme at Kushmundi Block(TSM/013076,SM/12055) | TSM/013076 | SM/12055 | New | MVS | Kushmundi | Ramchandrapur | near Ramchandrapur | OHR | Vested | 218 | 1 | 511 | 29 | Possessed | null
131 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gorahar Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012667,SM/12550) | TSM/012667 | SM/12550 | New | SVS | Balurghat | Gorahar | null | Pump House | Private | 3 | 78 | 321 | 2 | Identified | null
132 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dangapara Belua (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/013017,SM/12959) | TSM/013017 | SM/12959 | New | SVS | Harirampur | Dangapara Belua (I) | null | Pump House | Private | 103 | 47 | 562 | 2 | Identified | null
133 | DAKSHIN DINAJPUR | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur.(TSM/011659,SM/11636) | TSM/011659 | SM/11636 | New | MVS | Bansihari | Naopara | near Naopara | OHR | Vested | 238 | 1 | 211 | 32 | Possessed | For Head Work Site PWSS
134 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gunsi Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013057,SM/12969) | TSM/013057 | SM/12969 | New | SVS | Kumarganj | Gunsi | null | Pump House | Private | 218 | 64 | 101 | 2 | Identified | null
135 | DAKSHIN DINAJPUR | SOBRASYAMPUR PIPED WATER SUPPLY SCHEME(TSM/014531,SM/13092) | TSM/014531 | SM/13092 | New | MVS | Balurghat | Sobrasyampur | null | OHR | Private | 298 | 75 | 937 | 33 | Possessed | null
136 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Hatisala Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012694,SM/12602) | TSM/012694 | SM/12602 | New | SVS | Balurghat | Hatisala | null | Pump House | Private | 147 | 35 | 197 | 2 | Identified | null
137 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Balurghat & Banshihari Block in the District of Dakshin Dinajpur.(TSM/010105,SM/10644) | TSM/010105 | SM/10644 | New | MVS | Balurghat | Chak Daulat | null | Pump House | Vested | 233 | 1 | 172 | 2 | Identified | null
138 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jangalpur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012696,SM/12603) | TSM/012696 | SM/12603 | New | SVS | Balurghat | Jangalpur | null | Pump House | Vested | 146 | 1 | 221 | 2 | Identified | null
139 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Sadullapur | null | Pump House | Vested | 127 | 1 | 325 | 2 | Identified | null
140 | DAKSHIN DINAJPUR | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte.(TSM/011985,SM/11929) | TSM/011985 | SM/11929 | New | MVS | Harirampur | Sundail | null | OHR | Donated | 24 | 26 | 213 | 33 | Possessed | null
141 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Bad Basudebpur | null | Pump House | Private | 121 | 90 | 213 | 2 | Identified | null
142 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Keotsar Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012699,SM/12604) | TSM/012699 | SM/12604 | New | SVS | Balurghat | Keotsar | null | Pump House | Private | 170 | 738 | 61 | 2 | Identified | null
143 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chakpara Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012661,SM/12548) | TSM/012661 | SM/12548 | New | SVS | Balurghat | Chakpara | null | Pump House | Donated | 25 | 1076 | 435 | 2 | Identified | null
144 | DAKSHIN DINAJPUR | Source Augmentation of Deulbari PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte.(TSM/016346,SM/16207) | TSM/016346 | SM/16207 | Augmentation | MVS | Kushmundi | Punat | null | Pump House | Donated | 149 | 936 | 103 | 5 | Possessed | null
145 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chiknaikuri Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012664,SM/12549) | TSM/012664 | SM/12549 | New | SVS | Balurghat | Chiknaikuri | null | Pump House | Private | 6 | 73 | 155 | 2 | Identified | null
146 | DAKSHIN DINAJPUR | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME(TSM/017436,SM/18434) | TSM/017436 | SM/18434 | New | MVS | Kumarganj | Porajhar | null | OHR | Donated | 174 | 499 | 246 | 33 | Possessed | null
147 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kasthagar Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012668,SM/12551) | TSM/012668 | SM/12551 | New | SVS | Balurghat | Kashtagar | null | Pump House | Private | 36 | 38 | 136 | 2 | Identified | null
148 | DAKSHIN DINAJPUR | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur.(TSM/014408,SM/12703) | TSM/014408 | SM/12703 | New | MVS | Balurghat | Krisnapur | null | Pump House | Private | 153 | 43 | 14 | 33 | Possessed | null
149 | DAKSHIN DINAJPUR | JANTIGRAM Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur.(TSM/014494,SM/12706) | TSM/014494 | SM/12706 | New | MVS | Balurghat | Kamalpukur | null | Pump House | Private | 161 | 238 | 145 | 1 | Possessed | null
150 | DAKSHIN DINAJPUR | BOLLA Piped Water Supply Scheme(TSM/014315,SM/12811) | TSM/014315 | SM/12811 | New | MVS | Balurghat | Bolla | null | OHR | Donated | 22 | 487 | 88 | 33 | Possessed | null
151 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dasarai Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012708,SM/12610) | TSM/012708 | SM/12610 | New | SVS | Balurghat | Dasarai | null | Pump House | Private | 208 | 108 | 194 | 2 | Identified | null
152 | DAKSHIN DINAJPUR | Source Augmentation of Nawapara Piped Water Supply Scheme under Balurghat Division, PHE Dte.(TSM/016324,SM/16208) | TSM/016324 | SM/16208 | Augmentation | MVS | Hilli | Purbba Krishnapur | null | Pump House | Donated | 3 | 876 | 345 | 7 | Possessed | null
153 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Manipur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012720,SM/12613) | TSM/012720 | SM/12613 | New | SVS | Balurghat | Manipur | null | Pump House | Private | 246 | 70 | 49 | 2 | Identified | null
154 | DAKSHIN DINAJPUR | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur.(TSM/013174,SM/14106) | TSM/013174 | SM/14106 | New | MVS | Kushmundi | Udaypur | null | OHR | Donated | 174 | 2512 | 439 | 33 | Possessed | null
155 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Madanpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012920,SM/12849) | TSM/012920 | SM/12849 | New | SVS | Kumarganj | Madanpur | null | Pump House | Private | 87 | 85 | 324 | 2 | Identified | null
156 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kadmathail Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012736,SM/12620) | TSM/012736 | SM/12620 | New | SVS | Balurghat | Kadmathail | null | Pump House | Private | 184 | 82 | 181 | 2 | Identified | null
157 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kismat Jasahar Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012738,SM/12622) | TSM/012738 | SM/12622 | New | SVS | Balurghat | Kismat Jasahar | null | Pump House | Private | 204 | 215 | 30 | 2 | Identified | null
158 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Darajpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013187,SM/12982) | TSM/013187 | SM/12982 | New | SVS | Kumarganj | Darajpur | null | Pump House | Private | 83 | 47 | 828 | 2 | Identified | null
159 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Madhyamkarai Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012834,SM/13193) | TSM/012834 | SM/13193 | New | SVS | Kushmundi | Madhyamkarai | null | Pump House | Private | 111 | 905 | 184 | 2 | Identified | null
160 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Lakshmipur Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012915,SM/12956) | TSM/012915 | SM/12956 | New | SVS | Harirampur | Lakshmipur | null | Pump House | Private | 63 | 12 | 27 | 2 | Identified | null
161 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mahakhor Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012917,SM/12957) | TSM/012917 | SM/12957 | New | SVS | Harirampur | Mahakhor | null | Pump House | Private | 78 | 15 | 143 | 2 | Identified | null
162 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jiapur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012726,SM/12616) | TSM/012726 | SM/12616 | New | SVS | Balurghat | Jiapur | null | Pump House | Private | 69 | 91 | 105 | 2 | Identified | null
163 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kasipur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012737,SM/12621) | TSM/012737 | SM/12621 | New | SVS | Balurghat | Kasipur | null | Pump House | Private | 203 | 198 | 186 | 2 | Identified | null
164 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gobarta Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012940,SM/12864) | TSM/012940 | SM/12864 | New | SVS | Kumarganj | Gobarta | null | Pump House | Private | 89 | 1027 | 194 | 2 | Identified | null
165 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uchhana Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012943,SM/12866) | TSM/012943 | SM/12866 | New | SVS | Kumarganj | Uchhana | null | Pump House | Private | 76 | 547 | 49 | 2 | Identified | null
166 | DAKSHIN DINAJPUR | MUSAN Piped Water Supply Scheme at Harirampur Block(TSM/012014,SM/12052) | TSM/012014 | SM/12052 | New | MVS | Harirampur | Jamuna (I) | null | OHR | Donated | 185 | 203 | 308 | 33 | Possessed | null
167 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Katnapara Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012947,SM/12870) | TSM/012947 | SM/12870 | New | SVS | Kumarganj | Katnapara | null | Pump House | Private | 23 | 36 | 323 | 2 | Identified | null
168 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jaydebpur Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012794,SM/12481) | TSM/012794 | SM/12481 | New | SVS | Bansihari | Jaydebpur | null | Pump House | Private | 260 | 222 | 258 | 2 | Identified | null
169 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kajialsi Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/013344,SM/12545) | TSM/013344 | SM/12545 | New | SVS | Balurghat | Kajialsi | null | Pump House | Private | 46 | 300 | 97 | 2 | Identified | null
170 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Lakshmantara Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012827,SM/13188) | TSM/012827 | SM/13188 | New | SVS | Kushmundi | Lakshmantara | null | Pump House | Private | 50 | 175 | 276 | 2 | Identified | null
171 | DAKSHIN DINAJPUR | JARAIL Piped Water Supply Scheme at Kushmundi Block(TSM/013052,SM/12056) | TSM/013052 | SM/12056 | New | MVS | Kushmundi | Tejihar | null | OHR | Donated | 51 | 529 | 407 | 33 | Possessed | null
172 | DAKSHIN DINAJPUR | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block(TSM/013181,SM/12062) | TSM/013181 | SM/12062 | New | MVS | Kushmundi | Mahishakuri | null | OHR | Donated | 183 | 257 | 82 | 33 | Possessed | null
173 | DAKSHIN DINAJPUR | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte.(TSM/011983,SM/11930) | TSM/011983 | SM/11930 | New | MVS | Harirampur | Kokil | null | OHR | Donated | 83 | 594 | 419 | 33 | Possessed | null
174 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Rajapur Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012759,SM/12461) | TSM/012759 | SM/12461 | New | SVS | Bansihari | Rajapur | null | Pump House | Donated | 171 | 135 | 548 | 2 | Identified | null
175 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Banshihari, Gangarampur, Harirampur, Hili & Kumarganj Block in the District of Dakshin Dinajpur.(TSM/010106,SM/10813) | TSM/010106 | SM/10813 | New | MVS | Hilli | Chak Maniko | null | Pump House | Vested | 76 | 1 | 225 | 2 | Identified | null
176 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Porabagdol Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012875,SM/12917) | TSM/012875 | SM/12917 | New | SVS | Kushmundi | Porabagdol | null | Pump House | Private | 86 | 81 | 16 | 2 | Identified | null
177 | DAKSHIN DINAJPUR | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II)(TSM/011528,SM/13351) | TSM/011528 | SM/13351 | Augmentation | MVS | Hilli | Chapahat | null | OHR | Donated | 37 | 1146 | 84 | 10 | Possessed | null
178 | DAKSHIN DINAJPUR | SHYAMPUR PIPED WATER SUPPLY SCHEME(TSM/011902,SM/11962) | TSM/011902 | SM/11962 | New | MVS | Bansihari | Sarai | null | OHR | Donated | 195 | 225 | 852 | 33 | Possessed | null
179 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bejebikair Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012763,SM/12465) | TSM/012763 | SM/12465 | New | SVS | Bansihari | Bejebikair | null | Pump House | Private | 246 | 135 | 123 | 2 | Identified | null
180 | DAKSHIN DINAJPUR | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District.(TSM/009294,SM/09834) | TSM/009294 | SM/09834 | Augmentation | MVS | Kumarganj | Agachha | null | OHR | Private | 52 | 359 | 73 | 16 | Possessed | null
181 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Elankuri Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012765,SM/12466) | TSM/012765 | SM/12466 | New | SVS | Bansihari | Elankuri | null | Pump House | Private | 237 | 257 | 141 | 2 | Identified | null
182 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chandmoua Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013049,SM/12967) | TSM/013049 | SM/12967 | New | SVS | Kumarganj | Chandmoua | null | Pump House | Private | 205 | 194 | 93 | 2 | Identified | null
183 | DAKSHIN DINAJPUR | DHULATAIR Piped Water Supply Scheme(TSM/014386,SM/12819) | TSM/014386 | SM/12819 | New | MVS | Balurghat | Hariharpur | near hariharpur | Pump House | Vested | 32 | 1 | 1144 | 5 | Possessed | null
184 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Rajdhara Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012923,SM/12850) | TSM/012923 | SM/12850 | New | SVS | Kumarganj | Rajdhara | null | Pump House | Private | 39 | 122 | 254 | 2 | Identified | null
185 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jadupur Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012772,SM/12470) | TSM/012772 | SM/12470 | New | SVS | Bansihari | Jadupur | null | Pump House | Private | 159 | 157 | 90 | 2 | Identified | null
186 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dhaul Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012680,SM/12556) | TSM/012680 | SM/12556 | New | SVS | Balurghat | Dhaul | null | Pump House | Private | 103 | 89 | 754 | 2 | Identified | null
187 | DAKSHIN DINAJPUR | Revised Detailed Project Report for Pond Based Piped Water Supply Scheme using Nandan Bil for Elahabad Mouza.(TSM/009352,SM/10288) | TSM/009352 | SM/10288 | Augmentation | SVS | Bansihari | Elahabad | null | Pump House | Private | 230 | 477 | 117 | 2 | Possessed | null
188 | DAKSHIN DINAJPUR | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME(TSM/014637,SM/13091) | TSM/014637 | SM/13091 | New | MVS | Hilli | Purbba Mustafapur | null | OHR | Donated | 72 | 629 | 276 | 33 | Possessed | null
189 | DAKSHIN DINAJPUR | Source Augmentation of Bagduar Piped Water Supply Scheme at Bansihari Block under Balurghat Division PHE Dte.(TSM/017106,SM/15558) | TSM/017106 | SM/15558 | Augmentation | SVS | Bansihari | Bagduar | Near Bagduar Football Ground | Pump House | Vested | 281 | 1 | 2346 | 7 | Possessed | null
190 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak Ramnarayan Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012732,SM/12619) | TSM/012732 | SM/12619 | New | SVS | Balurghat | Chak Ramnarayan | null | Pump House | Vested | 197 | 1 | 144 | 2 | Identified | null
191 | DAKSHIN DINAJPUR | JANTIGRAM Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur.(TSM/014494,SM/12706) | TSM/014494 | SM/12706 | New | MVS | Balurghat | Sonkair | null | OHR | Private | 160 | 178 | 675 | 3 | Possessed | null
192 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Paschim Mustafapur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012682,SM/12557) | TSM/012682 | SM/12557 | New | SVS | Balurghat | Paschim Mustafapur | null | Pump House | Private | 97 | 82 | 882 | 2 | Identified | null
193 | DAKSHIN DINAJPUR | CHAKLA Piped Water Supply Scheme at Harirampur Block(TSM/011982,SM/12049) | TSM/011982 | SM/12049 | New | MVS | Harirampur | Chakla | null | OHR | Donated | 114 | 129 | 97 | 33 | Possessed | null
194 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Majhina Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012729,SM/12617) | TSM/012729 | SM/12617 | New | SVS | Balurghat | Majhina | null | Pump House | Private | 73 | 70 | 686 | 2 | Identified | null
195 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Par Sahazadpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012941,SM/12865) | TSM/012941 | SM/12865 | New | SVS | Kumarganj | Par Sahazadpur | null | Pump House | Private | 49 | 111 | 125 | 2 | Identified | null
196 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Matra Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012739,SM/12623) | TSM/012739 | SM/12623 | New | SVS | Balurghat | Matra | null | Pump House | Private | 183 | 271 | 238 | 2 | Identified | null
197 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Rajapur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012876,SM/12918) | TSM/012876 | SM/12918 | New | SVS | Kushmundi | Rajapur | null | Pump House | Private | 5 | 404 | 244 | 2 | Identified | null
198 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chapapara Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012823,SM/13185) | TSM/012823 | SM/13185 | New | SVS | Kushmundi | Chapapara | null | Pump House | Private | 49 | 75 | 157 | 2 | Identified | null
199 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dhandail Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012824,SM/13186) | TSM/012824 | SM/13186 | New | SVS | Kushmundi | Dhandail | null | Pump House | Private | 150 | 250 | 227 | 2 | Identified | null
200 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chhiashi Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012633,SM/12538) | TSM/012633 | SM/12538 | New | SVS | Balurghat | Chhiashi | null | Pump House | Private | 264 | 278 | 64 | 2 | Identified | null
201 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uchhakapur Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012705,SM/12608) | TSM/012705 | SM/12608 | New | SVS | Balurghat | Uchhakapur | null | Pump House | Private | 244 | 43 | 210 | 2 | Identified | null
202 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Banshra Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013045,SM/12965) | TSM/013045 | SM/12965 | New | SVS | Kumarganj | Banshra | null | Pump House | Private | 132 | 321 | 718 | 2 | Identified | null
203 | DAKSHIN DINAJPUR | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District.(TSM/011765,SM/11851) | TSM/011765 | SM/11851 | New | MVS | Bansihari | Paschim Chandipur | null | OHR | Donated | 126 | 126 | 200 | 31 | Possessed | null
204 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gopalpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013056,SM/12968) | TSM/013056 | SM/12968 | New | SVS | Kumarganj | Gopalpur | null | Pump House | Private | 206 | 131 | 127 | 2 | Identified | null
205 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Saraipur Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/012858,SM/12943) | TSM/012858 | SM/12943 | New | SVS | Kushmundi | Saraipur | null | Pump House | Private | 178 | 474 | 87 | 2 | Identified | null
206 | DAKSHIN DINAJPUR | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I)(TSM/009226,SM/10024) | TSM/009226 | SM/10024 | Retrofitting | MVS | Gangarampur | Mathurapur | Near mathurapur | OHR | Vested | 141 | 1 | 1116 | 18 | Possessed | for Head work site Pwss
207 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nahara Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013070,SM/12972) | TSM/013070 | SM/12972 | New | SVS | Kumarganj | Nahara | null | Pump House | Private | 134 | 267 | 12 | 2 | Identified | null
208 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mudafat Kochapara Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/013020,SM/12961) | TSM/013020 | SM/12961 | New | SVS | Harirampur | Mudafat Kochpara | null | Pump House | Private | 42 | 16 | 146 | 2 | Identified | null
209 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Khandara Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/013059,SM/12970) | TSM/013059 | SM/12970 | New | SVS | Kumarganj | Khandara | null | Pump House | Private | 133 | 17 | 19 | 2 | Identified | null
210 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Sulapanipur | null | Pump House | Private | 270 | 254 | 389 | 2 | Identified | null
211 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Muradpur | null | Pump House | Private | 118 | 148 | 167 | 2 | Identified | null
212 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Abjalpur (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012905,SM/12949) | TSM/012905 | SM/12949 | New | SVS | Harirampur | Abjalpur (I) | null | Pump House | Private | 191 | 158 | 167 | 2 | Identified | null
213 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Jnanbai | null | Pump House | Vested | 272 | 1 | 265 | 2 | Identified | null
214 | DAKSHIN DINAJPUR | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME(TSM/014637,SM/13091) | TSM/014637 | SM/13091 | New | MVS | Hilli | Purbba Mustafapur | null | Pump House | Donated | 72 | 834 | 778 | 8 | Possessed | null
215 | DAKSHIN DINAJPUR | JANGALPUR PWSS(TSM/014518,SM/18632) | TSM/014518 | SM/18632 | New | MVS | Balurghat | Jangalpur | null | OHR | Vested | 146 | 1 | 66 | 35 | Possessed | null
216 | DAKSHIN DINAJPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur.(TSM/010108,SM/10645) | TSM/010108 | SM/10645 | New | MVS | Tapan | Hardail | null | Pump House | Private | 151 | 106 | 116 | 2 | Identified | null
217 | DAKSHIN DINAJPUR | UTTAR KHANPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur.(TSM/014389,SM/12702) | TSM/014389 | SM/12702 | New | MVS | Balurghat | Uttar Khanpur | null | Pump House | Private | 207 | 520 | 268 | 5 | Possessed | null
218 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sanihara Mouza of Balurghat Block in the District of Dakshin Dinajpur(TSM/012642,SM/12541) | TSM/012642 | SM/12541 | New | SVS | Balurghat | Sanihara | null | Pump House | Vested | 276 | 1 | 274 | 2 | Identified | null
219 | DAKSHIN DINAJPUR | UTTAR KHANPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur.(TSM/014389,SM/12702) | TSM/014389 | SM/12702 | New | MVS | Balurghat | Chak Daulat | null | OHR | Private | 233 | 240 | 49 | 33 | Possessed | null
220 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nehal Mouza of Harirampur Block in the District of Dakshin Dinajpur.(TSM/012919,SM/12958) | TSM/012919 | SM/12958 | New | SVS | Harirampur | Nehal | null | Pump House | Private | 95 | 1639 | 171 | 2 | Identified | null
221 | DAKSHIN DINAJPUR | BOALDER PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR.(TSM/013551,SM/12244) | TSM/013551 | SM/12244 | New | MVS | Balurghat | Boaldar | null | OHR | Donated | 64 | 402 | 188 | 33 | Possessed | null
222 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kuarsai Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012774,SM/12471) | TSM/012774 | SM/12471 | New | SVS | Bansihari | Kuarsai | null | Pump House | Private | 271 | 249 | 167 | 2 | Identified | null
223 | DAKSHIN DINAJPUR | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Poradanga Mouza of Kushmandi Block in the District of Dakshin Dinajpur.(TSM/013379,SM/12925) | TSM/013379 | SM/12925 | New | SVS | Kushmundi | Poradanga | null | Pump House | Private | 30 | 1 | 143 | 2 | Identified | null
224 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bajerupahat Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012778,SM/12475) | TSM/012778 | SM/12475 | New | SVS | Bansihari | Bajerupahat | null | Pump House | Private | 185 | 79 | 785 | 2 | Identified | null
225 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chaurapara Mouza of Balurghat Block in the District of Dakshin Dinajpur.(TSM/012689,SM/12600) | TSM/012689 | SM/12600 | New | SVS | Balurghat | Chaurapara | null | Pump House | Private | 168 | 113 | 105 | 2 | Identified | null
226 | DAKSHIN DINAJPUR | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Silimpur Mouza of Kushmandii Block in the District of Dakshin Dinajpur.(TSM/013382,SM/12927) | TSM/013382 | SM/12927 | New | SVS | Kushmundi | Silimpur | null | Pump House | Private | 41 | 593 | 126 | 2 | Identified | null
227 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Paharpur Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012775,SM/12472) | TSM/012775 | SM/12472 | New | SVS | Bansihari | Paharpur | null | Pump House | Private | 167 | 213 | 223 | 2 | Identified | null
228 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Biralipara Mouza of Bansihari Block in the District of Dakshin Dinajpur.(TSM/012779,SM/12476) | TSM/012779 | SM/12476 | New | SVS | Bansihari | Biralipara | null | Pump House | Private | 154 | 495 | 554 | 2 | Identified | null
229 | DAKSHIN DINAJPUR | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Panitara Mouza of Kumarganj Block in the District of Dakshin Dinajpur.(TSM/012949,SM/12872) | TSM/012949 | SM/12872 | New | SVS | Kumarganj | Panitara | null | Pump House | Private | 31 | 82 | 129 | 2 | Identified | null